## Sheet1
DELIVERABLE REFERENCE | CAT | DLV REF. P1: CONTRACT CODE | DLV REF. P2: UNIT CODE | DLV REF. P3: DOC/DLV TYPE | DLV REF. P4: ENGINEERING CODE | DLV REF. P5: SERIAL NUMBER | CLIENT REFERENCE | WEIGHT | MANUFACTURING WEIGHT | TITLE | MILESTONE CHAIN | DBS | WBS | FREE CRITERIA 1 | FREE CRITERIA 2 | FREE CRITERIA 3 | FREE CRITERIA 4 | MSCODE | CUMULATIVE | MANUFACTURING CUMULATIVE | PBS | OBS | INITIAL PLAN DATE | REVISED PLAN DATE | FORECAST DATE | ACTUAL DATE | PLANNING SYSTEM IMPORT DATE | DMS/MMS IMPORT DATE | DRAFT PLAN DATE | SIMULATION PLAN DATE
200883C-000-CN-0190-5000 | [D] | 200883C | 0 | CN | 190 | 5000 |  | 1 |  | Yuri Phase 0 - Rigging Design (DELETED 3-Aug-22) | Code: E0303 | CIV | 000PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2023-07-30 | 2023-07-30 | 2022-07-29 | 2022-07-29
200883C-000-CN-0190-5000 | [D] | 200883C | 0 | CN | 190 | 5000 |  | 1 |  | Yuri Phase 0 - Rigging Design (DELETED 3-Aug-22) | Code: E0303 | CIV | 000PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2023-08-30 | 2023-08-30 | 2022-07-29 | 2022-07-29
200883C-000-CN-0190-5000 | [D] | 200883C | 0 | CN | 190 | 5000 |  | 1 |  | Yuri Phase 0 - Rigging Design (DELETED 3-Aug-22) | Code: E0303 | CIV | 000PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2023-09-29 | 2023-09-29 | 2022-07-29 | 2022-07-29
200883C-000-CN-1621-4000 | [D] | 200883C | 0 | CN | 1621 | 4000 |  | 21 |  | Yuri Phase 0 - Electrical Cable Sizing Calculation Note - H2 | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-08-16 | 2022-08-16 | 2022-07-23 | 2022-07-23
200883C-000-CN-1621-4000 | [D] | 200883C | 0 | CN | 1621 | 4000 |  | 21 |  | Yuri Phase 0 - Electrical Cable Sizing Calculation Note - H2 | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-09-06 | 2022-09-06 | 2022-07-26 | 2022-07-26
200883C-000-CN-1621-4000 | [D] | 200883C | 0 | CN | 1621 | 4000 |  | 21 |  | Yuri Phase 0 - Electrical Cable Sizing Calculation Note - H2 | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-10-18 | 2022-10-18 | 2022-08-26 | 2022-08-26
200883C-000-CN-1626-4000 | [D] | 200883C | 0 | CN | 1626 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Load List | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-06-14
200883C-000-CN-1626-4000 | [D] | 200883C | 0 | CN | 1626 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Load List | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-20 | 2022-06-20 | 2022-06-23 | 2022-06-23
200883C-000-CN-1626-4000 | [D] | 200883C | 0 | CN | 1626 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Load List | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-000-CN-1626-4001 | [D] | 200883C | 0 | CN | 1626 | 4001 |  | 21 |  | Yuri Phase 0 - Lightning Risk Assessment | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-09-28 | 2022-09-28 | 2022-06-15 | 2022-06-15
200883C-000-CN-1626-4001 | [D] | 200883C | 0 | CN | 1626 | 4001 |  | 21 |  | Yuri Phase 0 - Lightning Risk Assessment | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-10-04 | 2022-10-04 | 2022-10-04
200883C-000-CN-1626-4001 | [D] | 200883C | 0 | CN | 1626 | 4001 |  | 21 |  | Yuri Phase 0 - Lightning Risk Assessment | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-11-08 | 2022-11-08 | 2022-11-08
200883C-000-CN-1631-4000 | [D] | 200883C | 0 | CN | 1631 | 4000 |  | 41 |  | Yuri Phase 0 - Lighting System Calculation | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-000-CN-1631-4000 | [D] | 200883C | 0 | CN | 1631 | 4000 |  | 41 |  | Yuri Phase 0 - Lighting System Calculation | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-000-CN-1631-4000 | [D] | 200883C | 0 | CN | 1631 | 4000 |  | 41 |  | Yuri Phase 0 - Lighting System Calculation | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-000-CN-1671-4000 | [D] | 200883C | 0 | CN | 1671 | 4000 |  | 21 |  | Yuri Phase 0 - AC UPS Load Estimation - Rectifier Sizing | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-09 | 2022-06-09 | 2022-06-09 | 2022-06-09
200883C-000-CN-1671-4000 | [D] | 200883C | 0 | CN | 1671 | 4000 |  | 21 |  | Yuri Phase 0 - AC UPS Load Estimation - Rectifier Sizing | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-06-27 | 2022-06-27
200883C-000-CN-1671-4000 | [D] | 200883C | 0 | CN | 1671 | 4000 |  | 21 |  | Yuri Phase 0 - AC UPS Load Estimation - Rectifier Sizing | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-07-27 | 2022-07-27 | 2022-08-19 | 2022-08-19
200883C-000-CN-1671-4001 | [D] | 200883C | 0 | CN | 1671 | 4001 |  | 21 |  | Yuri Phase 0 - DC UPS Load Estimation - Rectifier Sizing | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-09 | 2022-06-09 | 2022-06-09 | 2022-06-09
200883C-000-CN-1671-4001 | [D] | 200883C | 0 | CN | 1671 | 4001 |  | 21 |  | Yuri Phase 0 - DC UPS Load Estimation - Rectifier Sizing | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-06-27 | 2022-06-27
200883C-000-CN-1671-4001 | [D] | 200883C | 0 | CN | 1671 | 4001 |  | 21 |  | Yuri Phase 0 - DC UPS Load Estimation - Rectifier Sizing | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-07-27 | 2022-07-27 | 2022-08-19 | 2022-08-19
200883C-000-CN-1901-1000 | [D] | 200883C | 0 | CN | 1901 | 1000 |  | 20 |  | Yuri Phase 0 - Safety and Risk Calculations | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-08-01 | 2022-08-01 | 2022-08-22
200883C-000-CN-1901-1000 | [D] | 200883C | 0 | CN | 1901 | 1000 |  | 20 |  | Yuri Phase 0 - Safety and Risk Calculations | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-08-19 | 2022-08-19 | 2022-09-09
200883C-000-CN-1901-1000 | [D] | 200883C | 0 | CN | 1901 | 1000 |  | 20 |  | Yuri Phase 0 - Safety and Risk Calculations | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-09-16 | 2022-09-16 | 2022-10-10
200883C-000-CN-1901-4000 | [D] | 200883C | 0 | CN | 1901 | 4000 |  | 44 |  | Yuri Phase 0 - Fire Water Demand Calculation | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-07-05 | 2022-07-05 | 2022-06-15 | 2022-06-15
200883C-000-CN-1901-4000 | [D] | 200883C | 0 | CN | 1901 | 4000 |  | 44 |  | Yuri Phase 0 - Fire Water Demand Calculation | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-07-11 | 2022-07-11 | 2022-06-30 | 2022-06-30
200883C-000-CN-1901-4000 | [D] | 200883C | 0 | CN | 1901 | 4000 |  | 44 |  | Yuri Phase 0 - Fire Water Demand Calculation | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2022-10-04 | 2022-10-04 | 2022-10-04
200883C-000-CN-1901-4000 | [D] | 200883C | 0 | CN | 1901 | 4000 |  | 44 |  | Yuri Phase 0 - Fire Water Demand Calculation | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-02-02 | 2023-02-02 | 2023-02-02
200883C-000-DQP-4000-XXXX | [D] | 200883C | 0 | DQP | 4000 | XXXX |  | 16 |  | Discipline Quality Plan | Code: E0201 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-000-DQP-4000-XXXX | [D] | 200883C | 0 | DQP | 4000 | XXXX |  | 16 |  | Discipline Quality Plan | Code: E0201 | INS | 000H2 |  |  |  |  | IFI | 100 |  |  | MINS | 2022-06-25 | 2022-06-25 | 2022-08-19 | 2022-08-19
200883C-000-DQP-4001-XXXX | [D] | 200883C | 0 | DQP | 4001 | XXXX |  | 12 |  | Yuri Phase 0 - Piping Discipline Quality and HSE Plan | Code: E0201 | PIP | 000H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-05-30 | 2022-05-30 | 2022-05-15 | 2022-05-15
200883C-000-DQP-4001-XXXX | [D] | 200883C | 0 | DQP | 4001 | XXXX |  | 12 |  | Yuri Phase 0 - Piping Discipline Quality and HSE Plan | Code: E0201 | PIP | 000H2 |  |  |  |  | IFI | 100 |  |  | MPIP | 2022-06-15 | 2022-06-15 | 2022-06-25 | 2022-06-25
200883C-000-DQP-5000 | [D] | 200883C | 0 | DQP |  | 5000 |  | 1 |  | Yuri Phase 0 - Software Quality Plan (DELETED 3-Aug-22) | Code: E0303 | INS | 000PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-05-31 | 2022-05-31 | 2022-05-31 | 2022-05-31
200883C-000-DQP-5000 | [D] | 200883C | 0 | DQP |  | 5000 |  | 1 |  | Yuri Phase 0 - Software Quality Plan (DELETED 3-Aug-22) | Code: E0303 | INS | 000PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-06-30 | 2022-06-30 | 2022-07-29 | 2022-07-29
200883C-000-DQP-5000 | [D] | 200883C | 0 | DQP |  | 5000 |  | 1 |  | Yuri Phase 0 - Software Quality Plan (DELETED 3-Aug-22) | Code: E0303 | INS | 000PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-07-30 | 2022-07-30 | 2022-07-29 | 2022-07-29
200883C-000-DW-0900-5000 | [D] | 200883C | 0 | DW | 900 | 5000 |  | 1 |  | Yuri Phase 0 - Rigging Arrangement Detail (DELETED 3-Aug-22) | Code: E0303 | CIV | 000PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2023-07-31 | 2023-07-31 | 2022-07-29 | 2022-07-29
200883C-000-DW-0900-5000 | [D] | 200883C | 0 | DW | 900 | 5000 |  | 1 |  | Yuri Phase 0 - Rigging Arrangement Detail (DELETED 3-Aug-22) | Code: E0303 | CIV | 000PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2023-08-30 | 2023-08-30 | 2022-07-29 | 2022-07-29
200883C-000-DW-0900-5000 | [D] | 200883C | 0 | DW | 900 | 5000 |  | 1 |  | Yuri Phase 0 - Rigging Arrangement Detail (DELETED 3-Aug-22) | Code: E0303 | CIV | 000PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2023-09-29 | 2023-09-29 | 2022-07-29 | 2022-07-29
200883C-000-DW-1360-4000 | [D] | 200883C | 0 | DW | 1360 | 4000 |  | 90 |  | Yuri Phase 0-Special Support Collection | Code: E0203 | PIP | 000H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2023-01-15 | 2023-01-15 | 2023-01-15
200883C-000-DW-1360-4000 | [D] | 200883C | 0 | DW | 1360 | 4000 |  | 90 |  | Yuri Phase 0-Special Support Collection | Code: E0203 | PIP | 000H2 |  |  |  |  | IFC | 100 |  |  | MPIP | 2023-01-23 | 2023-01-23 | 2023-01-23
200883C-000-DW-1512-1000 | [D] | 200883C | 0 | DW | 1512 | 1000 |  | 40 |  | Yuri Phase 0 - Yuri-YPF Interconnection Block Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | AINS | 2022-05-02 | 2022-05-02 | 2022-05-02 | 2022-05-02
200883C-000-DW-1512-1000 | [D] | 200883C | 0 | DW | 1512 | 1000 |  | 40 |  | Yuri Phase 0 - Yuri-YPF Interconnection Block Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | AINS | 2022-06-15 | 2022-06-15 | 2022-08-13 | 2022-08-13
200883C-000-DW-1512-1000 | [D] | 200883C | 0 | DW | 1512 | 1000 |  | 40 |  | Yuri Phase 0 - Yuri-YPF Interconnection Block Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | AINS | 2022-12-30 | 2022-12-30 | 2022-08-15 | 2022-08-15
200883C-000-DW-1512-4000 | [D] | 200883C | 0 | DW | 1512 | 4000 |  | 95 |  | Yuri Phase 0 - Instrumentation And Control ICS Architecture Block Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-23 | 2022-08-23 | 2022-06-09 | 2022-06-09
200883C-000-DW-1512-4000 | [D] | 200883C | 0 | DW | 1512 | 4000 |  | 95 |  | Yuri Phase 0 - Instrumentation And Control ICS Architecture Block Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-08-29 | 2022-08-29 | 2022-06-09 | 2022-06-09
200883C-000-DW-1512-4000 | [D] | 200883C | 0 | DW | 1512 | 4000 |  | 95 |  | Yuri Phase 0 - Instrumentation And Control ICS Architecture Block Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2022-12-15 | 2022-12-15 | 2022-12-15
200883C-000-DW-1512-4001 | [D] | 200883C | 0 | DW | 1512 | 4001 |  | 32 |  | Yuri Phase 0 - ICS Cable Block Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2023-01-12 | 2023-01-12 | 2023-01-12
200883C-000-DW-1512-4001 | [D] | 200883C | 0 | DW | 1512 | 4001 |  | 32 |  | Yuri Phase 0 - ICS Cable Block Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2023-01-18 | 2023-01-18 | 2023-01-18
200883C-000-DW-1512-4001 | [D] | 200883C | 0 | DW | 1512 | 4001 |  | 32 |  | Yuri Phase 0 - ICS Cable Block Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-000-DW-1512-4002 | [D] | 200883C | 0 | DW | 1512 | 4002 |  | 32 |  | Yuri Phase 0 - Serial connections cable block diagram | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-000-DW-1512-4002 | [D] | 200883C | 0 | DW | 1512 | 4002 |  | 32 |  | Yuri Phase 0 - Serial connections cable block diagram | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-12-19 | 2022-12-19 | 2022-12-19
200883C-000-DW-1512-4002 | [D] | 200883C | 0 | DW | 1512 | 4002 |  | 32 |  | Yuri Phase 0 - Serial connections cable block diagram | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2023-02-28 | 2023-02-28 | 2023-02-28
200883C-000-DW-1512-4003 | [D] | 200883C | 0 | DW | 1512 | 4003 |  | 32 |  | Yuri Phase 0 - Instrument Electrolyser block Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-000-DW-1512-4003 | [D] | 200883C | 0 | DW | 1512 | 4003 |  | 32 |  | Yuri Phase 0 - Instrument Electrolyser block Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-12-19 | 2022-12-19 | 2022-12-19
200883C-000-DW-1512-4003 | [D] | 200883C | 0 | DW | 1512 | 4003 |  | 32 |  | Yuri Phase 0 - Instrument Electrolyser block Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2023-01-16 | 2023-01-16 | 2023-01-16
200883C-000-DW-1512-4004 | [D] | 200883C | 0 | DW | 1512 | 4004 |  | 26 |  | Yuri Phase 0 - Instrument Power Supply Distribution | Code: E0311 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-000-DW-1512-4004 | [D] | 200883C | 0 | DW | 1512 | 4004 |  | 26 |  | Yuri Phase 0 - Instrument Power Supply Distribution | Code: E0311 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-12-15 | 2022-12-15 | 2022-12-15
200883C-000-DW-1512-4004 | [D] | 200883C | 0 | DW | 1512 | 4004 |  | 26 |  | Yuri Phase 0 - Instrument Power Supply Distribution | Code: E0311 | INS | 000H2 |  |  |  |  | IFU | 100 |  |  | MINS | 2023-02-27 | 2023-02-27 | 2023-02-27
200883C-000-DW-1522-4000 | [D] | 200883C | 0 | DW | 1522 | 4000 |  | 16 |  | Yuri Phase 0 - Instrument and Control Typical Instrument Earthing | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-06-09 | 2022-06-09 | 2022-06-09 | 2022-06-09
200883C-000-DW-1522-4000 | [D] | 200883C | 0 | DW | 1522 | 4000 |  | 16 |  | Yuri Phase 0 - Instrument and Control Typical Instrument Earthing | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-06-15 | 2022-06-15 | 2022-07-29 | 2022-07-29
200883C-000-DW-1522-4000 | [D] | 200883C | 0 | DW | 1522 | 4000 |  | 16 |  | Yuri Phase 0 - Instrument and Control Typical Instrument Earthing | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-000-DW-1523-4000 | [D] | 200883C | 0 | DW | 1523 | 4000 |  | 79 |  | Yuri Phase 0 - Control Room Layout | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-06-15 | 2022-06-15 | 2022-06-15 | 2022-06-15
200883C-000-DW-1523-4000 | [D] | 200883C | 0 | DW | 1523 | 4000 |  | 79 |  | Yuri Phase 0 - Control Room Layout | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-06-30 | 2022-06-30 | 2022-07-04 | 2022-07-04
200883C-000-DW-1523-4000 | [D] | 200883C | 0 | DW | 1523 | 4000 |  | 79 |  | Yuri Phase 0 - Control Room Layout | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2022-11-15 | 2022-11-15 | 2022-11-15
200883C-000-DW-1525-4000 | [D] | 200883C | 0 | DW | 1525 | 4000 |  | 32 |  | Yuri Phase 0 - Instrument Loop Drawings | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2023-02-10 | 2023-02-10 | 2023-02-10
200883C-000-DW-1525-4000 | [D] | 200883C | 0 | DW | 1525 | 4000 |  | 32 |  | Yuri Phase 0 - Instrument Loop Drawings | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2023-02-23 | 2023-02-23 | 2023-02-23
200883C-000-DW-1525-4000 | [D] | 200883C | 0 | DW | 1525 | 4000 |  | 32 |  | Yuri Phase 0 - Instrument Loop Drawings | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2023-03-16 | 2023-03-16 | 2023-03-16
200883C-000-DW-1532-0001 | [D] | 200883C | 0 | DW | 1532 | 1 |  | 1 |  | Yuri Phase 0 - Access Control System Architecture Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | AINS |  | 2022-09-02 | 2022-08-13 | 2022-08-13
200883C-000-DW-1532-0001 | [D] | 200883C | 0 | DW | 1532 | 1 |  | 1 |  | Yuri Phase 0 - Access Control System Architecture Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | AINS |  | 2022-09-23 | 2022-08-15 | 2022-08-15
200883C-000-DW-1532-0001 | [D] | 200883C | 0 | DW | 1532 | 1 |  | 1 |  | Yuri Phase 0 - Access Control System Architecture Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | AINS |  | 2022-10-07 | 2022-10-07
200883C-000-DW-1532-4000 | [D] | 200883C | 0 | DW | 1532 | 4000 |  | 48 |  | Yuri Phase 0 - CCTV Installation Drawing | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2023-04-18 | 2023-04-18 | 2023-04-18
200883C-000-DW-1532-4000 | [D] | 200883C | 0 | DW | 1532 | 4000 |  | 48 |  | Yuri Phase 0 - CCTV Installation Drawing | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2023-04-24 | 2023-04-24 | 2023-04-24
200883C-000-DW-1532-4000 | [D] | 200883C | 0 | DW | 1532 | 4000 |  | 48 |  | Yuri Phase 0 - CCTV Installation Drawing | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2023-05-15 | 2023-05-15 | 2023-05-15
200883C-000-DW-1532-4001 | [D] | 200883C | 0 | DW | 1532 | 4001 |  | 32 |  | Yuri Phase 0 - CCTV Cable Block Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2023-02-10 | 2023-02-10 | 2023-02-10
200883C-000-DW-1532-4001 | [D] | 200883C | 0 | DW | 1532 | 4001 |  | 32 |  | Yuri Phase 0 - CCTV Cable Block Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-000-DW-1532-4001 | [D] | 200883C | 0 | DW | 1532 | 4001 |  | 32 |  | Yuri Phase 0 - CCTV Cable Block Diagram | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2023-03-16 | 2023-03-16 | 2023-03-16
200883C-000-DW-1552-4000 | [D] | 200883C | 0 | DW | 1552 | 4000 |  | 41 |  | Yuri Phase 0 - Instrument Level Sketches | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-000-DW-1552-4000 | [D] | 200883C | 0 | DW | 1552 | 4000 |  | 41 |  | Yuri Phase 0 - Instrument Level Sketches | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-000-DW-1552-4000 | [D] | 200883C | 0 | DW | 1552 | 4000 |  | 41 |  | Yuri Phase 0 - Instrument Level Sketches | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2023-02-23 | 2023-02-23 | 2023-02-23
200883C-000-DW-1572-4000 | [D] | 200883C | 0 | DW | 1572 | 4000 |  | 63 |  | Yuri Phase 0 - Instrument Cable Tray Layout | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-000-DW-1572-4000 | [D] | 200883C | 0 | DW | 1572 | 4000 |  | 63 |  | Yuri Phase 0 - Instrument Cable Tray Layout | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-12-21 | 2022-12-21 | 2022-12-21
200883C-000-DW-1572-4000 | [D] | 200883C | 0 | DW | 1572 | 4000 |  | 63 |  | Yuri Phase 0 - Instrument Cable Tray Layout | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2023-02-23 | 2023-02-23 | 2023-02-23
200883C-000-DW-1572-5000 | [D] | 200883C | 0 | DW | 1572 | 5000 |  | 40 |  | Yuri Phase 0 - Fiber Optic Cable Connection Diagram | Code: E0303 | INS | 000PV |  |  |  |  | STA | 10 |  |  | MFINS | 2023-01-16 | 2023-01-16 | 2023-01-16
200883C-000-DW-1572-5000 | [D] | 200883C | 0 | DW | 1572 | 5000 |  | 40 |  | Yuri Phase 0 - Fiber Optic Cable Connection Diagram | Code: E0303 | INS | 000PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2023-02-15 | 2023-02-15 | 2023-02-15
200883C-000-DW-1572-5000 | [D] | 200883C | 0 | DW | 1572 | 5000 |  | 40 |  | Yuri Phase 0 - Fiber Optic Cable Connection Diagram | Code: E0303 | INS | 000PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2023-03-17 | 2023-03-17 | 2023-03-17
200883C-000-DW-1573-4000 | [D] | 200883C | 0 | DW | 1573 | 4000 |  | 63 |  | Yuri Phase 0 - ICS JB Wiring Drawings | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-000-DW-1573-4000 | [D] | 200883C | 0 | DW | 1573 | 4000 |  | 63 |  | Yuri Phase 0 - ICS JB Wiring Drawings | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-12-13 | 2022-12-13 | 2022-12-13
200883C-000-DW-1573-4000 | [D] | 200883C | 0 | DW | 1573 | 4000 |  | 63 |  | Yuri Phase 0 - ICS JB Wiring Drawings | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2023-02-27 | 2023-02-27 | 2023-02-27
200883C-000-DW-1574-1000 | [D] | 200883C | 0 | DW | 1574 | 1000 |  | 1 |  | Yuri Phase 0 - CCTV Location Drawing | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | AINS |  | 2022-09-02 | 2022-08-13 | 2022-08-13
200883C-000-DW-1574-1000 | [D] | 200883C | 0 | DW | 1574 | 1000 |  | 1 |  | Yuri Phase 0 - CCTV Location Drawing | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | AINS |  | 2022-09-23 | 2022-08-15 | 2022-08-15
200883C-000-DW-1574-1000 | [D] | 200883C | 0 | DW | 1574 | 1000 |  | 1 |  | Yuri Phase 0 - CCTV Location Drawing | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | AINS |  | 2022-10-07 | 2022-10-07
200883C-000-DW-1574-4000 | [D] | 200883C | 0 | DW | 1574 | 4000 |  | 48 |  | Yuri Phase 0 - Instrument Field Layout | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-000-DW-1574-4000 | [D] | 200883C | 0 | DW | 1574 | 4000 |  | 48 |  | Yuri Phase 0 - Instrument Field Layout | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-12-09 | 2022-12-09 | 2022-12-09
200883C-000-DW-1574-4000 | [D] | 200883C | 0 | DW | 1574 | 4000 |  | 48 |  | Yuri Phase 0 - Instrument Field Layout | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2023-02-22 | 2023-02-22 | 2023-02-22
200883C-000-DW-1574-4001 | [D] | 200883C | 0 | DW | 1574 | 4001 |  | 48 |  | Yuri Phase 0 - FandG Field Layout | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-000-DW-1574-4001 | [D] | 200883C | 0 | DW | 1574 | 4001 |  | 48 |  | Yuri Phase 0 - FandG Field Layout | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-12-09 | 2022-12-09 | 2022-12-09
200883C-000-DW-1574-4001 | [D] | 200883C | 0 | DW | 1574 | 4001 |  | 48 |  | Yuri Phase 0 - FandG Field Layout | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2023-02-20 | 2023-02-20 | 2023-02-20
200883C-000-DW-1575-4000 | [D] | 200883C | 0 | DW | 1575 | 4000 |  | 48 |  | Yuri Phase 0 - Instrument Air Layout | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-000-DW-1575-4000 | [D] | 200883C | 0 | DW | 1575 | 4000 |  | 48 |  | Yuri Phase 0 - Instrument Air Layout | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-12-13 | 2022-12-13 | 2022-12-13
200883C-000-DW-1575-4000 | [D] | 200883C | 0 | DW | 1575 | 4000 |  | 48 |  | Yuri Phase 0 - Instrument Air Layout | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2023-02-20 | 2023-02-20 | 2023-02-20
200883C-000-DW-1576-4000 | [D] | 200883C | 0 | DW | 1576 | 4000 |  | 95 |  | Yuri Phase 0 - Pneumatic and Process Hook-Up Drawings | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-000-DW-1576-4000 | [D] | 200883C | 0 | DW | 1576 | 4000 |  | 95 |  | Yuri Phase 0 - Pneumatic and Process Hook-Up Drawings | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-09-19 | 2022-09-19 | 2022-09-19
200883C-000-DW-1576-4000 | [D] | 200883C | 0 | DW | 1576 | 4000 |  | 95 |  | Yuri Phase 0 - Pneumatic and Process Hook-Up Drawings | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2023-02-23 | 2023-02-23 | 2023-02-23
200883C-000-DW-1576-4001 | [D] | 200883C | 0 | DW | 1576 | 4001 |  | 48 |  | Yuri Phase 0 - Instrument Supports Mounting Details | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-09-07 | 2022-09-07 | 2022-09-07
200883C-000-DW-1576-4001 | [D] | 200883C | 0 | DW | 1576 | 4001 |  | 48 |  | Yuri Phase 0 - Instrument Supports Mounting Details | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-000-DW-1576-4001 | [D] | 200883C | 0 | DW | 1576 | 4001 |  | 48 |  | Yuri Phase 0 - Instrument Supports Mounting Details | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | MINS | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-000-DW-1622-4000 | [D] | 200883C | 0 | DW | 1622 | 4000 |  | 61 |  | Yuri Phase 0 - Main Power Layout Drawings | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-000-DW-1622-4000 | [D] | 200883C | 0 | DW | 1622 | 4000 |  | 61 |  | Yuri Phase 0 - Main Power Layout Drawings | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-10-02 | 2022-10-02 | 2022-10-02
200883C-000-DW-1622-4000 | [D] | 200883C | 0 | DW | 1622 | 4000 |  | 61 |  | Yuri Phase 0 - Main Power Layout Drawings | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2023-01-23 | 2023-01-23 | 2023-01-23
200883C-000-DW-1633-4000 | [D] | 200883C | 0 | DW | 1633 | 4000 |  | 41 |  | Yuri Phase 0 - Lighting Circuit Interconnection Block Diagrams | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-10-15 | 2022-10-15 | 2022-10-15
200883C-000-DW-1633-4000 | [D] | 200883C | 0 | DW | 1633 | 4000 |  | 41 |  | Yuri Phase 0 - Lighting Circuit Interconnection Block Diagrams | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-10-30 | 2022-10-30 | 2022-10-30
200883C-000-DW-1633-4000 | [D] | 200883C | 0 | DW | 1633 | 4000 |  | 41 |  | Yuri Phase 0 - Lighting Circuit Interconnection Block Diagrams | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-11-27 | 2022-11-27 | 2022-11-27
200883C-000-DW-1652-4000 | [D] | 200883C | 0 | DW | 1652 | 4000 |  | 41 |  | Yuri Phase 0 - AC UPS Key Single Line Diagram | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-01 | 2022-07-01 | 2022-07-01 | 2022-07-01
200883C-000-DW-1652-4000 | [D] | 200883C | 0 | DW | 1652 | 4000 |  | 41 |  | Yuri Phase 0 - AC UPS Key Single Line Diagram | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-07-07 | 2022-07-07 | 2022-07-08 | 2022-07-08
200883C-000-DW-1652-4000 | [D] | 200883C | 0 | DW | 1652 | 4000 |  | 41 |  | Yuri Phase 0 - AC UPS Key Single Line Diagram | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-08-11 | 2022-08-11 | 2022-08-19 | 2022-08-19
200883C-000-DW-1652-4001 | [D] | 200883C | 0 | DW | 1652 | 4001 |  | 41 |  | Yuri Phase 0 - DC Charger Unit Single Line Diagram | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-01 | 2022-07-01 | 2022-07-01 | 2022-07-01
200883C-000-DW-1652-4001 | [D] | 200883C | 0 | DW | 1652 | 4001 |  | 41 |  | Yuri Phase 0 - DC Charger Unit Single Line Diagram | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-07-07 | 2022-07-07 | 2022-07-08 | 2022-07-08
200883C-000-DW-1652-4001 | [D] | 200883C | 0 | DW | 1652 | 4001 |  | 41 |  | Yuri Phase 0 - DC Charger Unit Single Line Diagram | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-08-11 | 2022-08-11 | 2022-07-29 | 2022-07-29
200883C-000-DW-1652-4002 | [D] | 200883C | 0 | DW | 1652 | 4002 |  | 41 |  | Yuri Phase 0 - Main Earthing Single Line Diagram | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-01 | 2022-07-01 | 2022-06-28 | 2022-06-28
200883C-000-DW-1652-4002 | [D] | 200883C | 0 | DW | 1652 | 4002 |  | 41 |  | Yuri Phase 0 - Main Earthing Single Line Diagram | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-07-07 | 2022-07-07 | 2022-06-28 | 2022-06-28
200883C-000-DW-1652-4002 | [D] | 200883C | 0 | DW | 1652 | 4002 |  | 41 |  | Yuri Phase 0 - Main Earthing Single Line Diagram | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-08-11 | 2022-08-11 | 2022-07-29 | 2022-07-29
200883C-000-DW-1652-4003 | [D] | 200883C | 0 | DW | 1652 | 4003 |  | 61 |  | Yuri Phase 0 - Overall Key Single Line Diagram | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-04 | 2022-06-04 | 2022-06-09 | 2022-06-09
200883C-000-DW-1652-4003 | [D] | 200883C | 0 | DW | 1652 | 4003 |  | 61 |  | Yuri Phase 0 - Overall Key Single Line Diagram | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-09 | 2022-06-09 | 2022-06-16 | 2022-06-16
200883C-000-DW-1652-4003 | [D] | 200883C | 0 | DW | 1652 | 4003 |  | 61 |  | Yuri Phase 0 - Overall Key Single Line Diagram | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-06-24 | 2022-06-24 | 2022-07-29 | 2022-07-29
200883C-000-DW-1652-4004 | [D] | 200883C | 0 | DW | 1652 | 4004 |  | 41 |  | Yuri Phase 0 - Electrical Symbols Single Line Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-01 | 2022-07-01 | 2022-06-07 | 2022-06-07
200883C-000-DW-1652-4004 | [D] | 200883C | 0 | DW | 1652 | 4004 |  | 41 |  | Yuri Phase 0 - Electrical Symbols Single Line Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-07-07 | 2022-07-07 | 2022-06-07 | 2022-06-07
200883C-000-DW-1652-4004 | [D] | 200883C | 0 | DW | 1652 | 4004 |  | 41 |  | Yuri Phase 0 - Electrical Symbols Single Line Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-08-06 | 2022-08-06 | 2022-07-29 | 2022-07-29
200883C-000-DW-1663-4000 | [D] | 200883C | 0 | DW | 1663 | 4000 |  | 41 |  | Yuri Phase 0 - HV Single Line And Protection Metering Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-01 | 2022-07-01 | 2022-05-18 | 2022-05-18
200883C-000-DW-1663-4000 | [D] | 200883C | 0 | DW | 1663 | 4000 |  | 41 |  | Yuri Phase 0 - HV Single Line And Protection Metering Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-07-07 | 2022-07-07 | 2022-06-03 | 2022-06-03
200883C-000-DW-1663-4000 | [D] | 200883C | 0 | DW | 1663 | 4000 |  | 41 |  | Yuri Phase 0 - HV Single Line And Protection Metering Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-08-06 | 2022-08-06 | 2022-08-05 | 2022-08-05
200883C-000-DW-1663-4001 | [D] | 200883C | 0 | DW | 1663 | 4001 |  | 41 |  | Yuri Phase 0 - LV Single Line And Protection Metering Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-01 | 2022-07-01 | 2022-06-23 | 2022-06-23
200883C-000-DW-1663-4001 | [D] | 200883C | 0 | DW | 1663 | 4001 |  | 41 |  | Yuri Phase 0 - LV Single Line And Protection Metering Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-07-07 | 2022-07-07 | 2022-06-23 | 2022-06-23
200883C-000-DW-1663-4001 | [D] | 200883C | 0 | DW | 1663 | 4001 |  | 41 |  | Yuri Phase 0 - LV Single Line And Protection Metering Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-08-06 | 2022-08-06 | 2022-07-29 | 2022-07-29
200883C-000-DW-1665-4000 | [D] | 200883C | 0 | DW | 1665 | 4000 |  | 41 |  | Yuri Phase 0 - AC UPS System Interconnection Block Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-10-03 | 2022-10-03 | 2022-10-03
200883C-000-DW-1665-4000 | [D] | 200883C | 0 | DW | 1665 | 4000 |  | 41 |  | Yuri Phase 0 - AC UPS System Interconnection Block Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-10-10 | 2022-10-10 | 2022-10-10
200883C-000-DW-1665-4000 | [D] | 200883C | 0 | DW | 1665 | 4000 |  | 41 |  | Yuri Phase 0 - AC UPS System Interconnection Block Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-11-07 | 2022-11-07 | 2022-11-07
200883C-000-DW-1665-4001 | [D] | 200883C | 0 | DW | 1665 | 4001 |  | 41 |  | Yuri Phase 0 - DC UPS Interconnection Block Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-10-13 | 2022-10-13 | 2022-10-13
200883C-000-DW-1665-4001 | [D] | 200883C | 0 | DW | 1665 | 4001 |  | 41 |  | Yuri Phase 0 - DC UPS Interconnection Block Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-10-20 | 2022-10-20 | 2022-10-20
200883C-000-DW-1665-4001 | [D] | 200883C | 0 | DW | 1665 | 4001 |  | 41 |  | Yuri Phase 0 - DC UPS Interconnection Block Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-11-17 | 2022-11-17 | 2022-11-17
200883C-000-DW-1665-4002 | [D] | 200883C | 0 | DW | 1665 | 4002 |  | 41 |  | Yuri Phase 0 - Small Power Circuit Interconnection Block Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-10-23 | 2022-10-23 | 2022-10-23
200883C-000-DW-1665-4002 | [D] | 200883C | 0 | DW | 1665 | 4002 |  | 41 |  | Yuri Phase 0 - Small Power Circuit Interconnection Block Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-10-30 | 2022-10-30 | 2022-10-30
200883C-000-DW-1665-4002 | [D] | 200883C | 0 | DW | 1665 | 4002 |  | 41 |  | Yuri Phase 0 - Small Power Circuit Interconnection Block Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-11-27 | 2022-11-27 | 2022-11-27
200883C-000-DW-1665-4003 | [D] | 200883C | 0 | DW | 1665 | 4003 |  | 41 |  | Yuri Phase 0 - HV Switchboard Interconnection Block Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-09-24 | 2022-09-24 | 2022-09-24
200883C-000-DW-1665-4003 | [D] | 200883C | 0 | DW | 1665 | 4003 |  | 41 |  | Yuri Phase 0 - HV Switchboard Interconnection Block Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-10-01 | 2022-10-01 | 2022-10-01
200883C-000-DW-1665-4003 | [D] | 200883C | 0 | DW | 1665 | 4003 |  | 41 |  | Yuri Phase 0 - HV Switchboard Interconnection Block Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-10-29 | 2022-10-29 | 2022-10-29
200883C-000-DW-1665-4004 | [D] | 200883C | 0 | DW | 1665 | 4004 |  | 41 |  | Yuri Phase 0 - LV Switchboard Interconnection Block Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-09-28 | 2022-09-28 | 2022-09-28
200883C-000-DW-1665-4004 | [D] | 200883C | 0 | DW | 1665 | 4004 |  | 41 |  | Yuri Phase 0 - LV Switchboard Interconnection Block Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-10-05 | 2022-10-05 | 2022-10-05
200883C-000-DW-1665-4004 | [D] | 200883C | 0 | DW | 1665 | 4004 |  | 41 |  | Yuri Phase 0 - LV Switchboard Interconnection Block Diagrams | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-11-02 | 2022-11-02 | 2022-11-02
200883C-000-DW-1802-4000 | [D] | 200883C | 0 | DW | 1802 | 4000 |  | 46 |  | General Notes - Structural Steel Fabrication | Code: E0301 | STR | 000H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-05-27 | 2022-05-27 | 2022-06-15 | 2022-06-15
200883C-000-DW-1802-4000 | [D] | 200883C | 0 | DW | 1802 | 4000 |  | 46 |  | General Notes - Structural Steel Fabrication | Code: E0301 | STR | 000H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-06-15 | 2022-06-15 | 2022-06-27 | 2022-06-27
200883C-000-DW-1802-4000 | [D] | 200883C | 0 | DW | 1802 | 4000 |  | 46 |  | General Notes - Structural Steel Fabrication | Code: E0301 | STR | 000H2 |  |  |  |  | IFD | 100 |  |  | MSTR | 2022-07-13 | 2022-07-13 | 2022-08-10 | 2022-08-10
200883C-000-DW-1802-4001 | [D] | 200883C | 0 | DW | 1802 | 4001 |  | 46 |  | General Notes - Structural Installation | Code: E0301 | STR | 000H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-05-27 | 2022-05-27 | 2022-06-15 | 2022-06-15
200883C-000-DW-1802-4001 | [D] | 200883C | 0 | DW | 1802 | 4001 |  | 46 |  | General Notes - Structural Installation | Code: E0301 | STR | 000H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-06-15 | 2022-06-15 | 2022-06-27 | 2022-06-27
200883C-000-DW-1802-4001 | [D] | 200883C | 0 | DW | 1802 | 4001 |  | 46 |  | General Notes - Structural Installation | Code: E0301 | STR | 000H2 |  |  |  |  | IFD | 100 |  |  | MSTR | 2022-07-13 | 2022-07-13 | 2022-07-14 | 2022-07-14
200883C-000-DW-1920-4000 | [D] | 200883C | 0 | DW | 1920 | 4000 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 1 | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-07-25 | 2022-07-25 | 2022-07-25 | 2022-07-25
200883C-000-DW-1920-4000 | [D] | 200883C | 0 | DW | 1920 | 4000 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 1 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-08-08 | 2022-08-08 | 2022-08-08
200883C-000-DW-1920-4000 | [D] | 200883C | 0 | DW | 1920 | 4000 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 1 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2022-10-14 | 2022-10-14 | 2022-10-14
200883C-000-DW-1920-4000 | [D] | 200883C | 0 | DW | 1920 | 4000 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 1 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-02-06 | 2023-02-06 | 2023-02-06
200883C-000-DW-1920-4001 | [D] | 200883C | 0 | DW | 1920 | 4001 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 2 | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-07-25 | 2022-07-25 | 2022-07-25 | 2022-07-25
200883C-000-DW-1920-4001 | [D] | 200883C | 0 | DW | 1920 | 4001 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 2 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-08-08 | 2022-08-08 | 2022-08-08
200883C-000-DW-1920-4001 | [D] | 200883C | 0 | DW | 1920 | 4001 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 2 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2022-10-14 | 2022-10-14 | 2022-10-14
200883C-000-DW-1920-4001 | [D] | 200883C | 0 | DW | 1920 | 4001 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 2 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-02-06 | 2023-02-06 | 2023-02-06
200883C-000-DW-1920-4002 | [D] | 200883C | 0 | DW | 1920 | 4002 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 3 | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-07-25 | 2022-07-25 | 2022-07-25 | 2022-07-25
200883C-000-DW-1920-4002 | [D] | 200883C | 0 | DW | 1920 | 4002 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 3 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-08-08 | 2022-08-08 | 2022-08-08
200883C-000-DW-1920-4002 | [D] | 200883C | 0 | DW | 1920 | 4002 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 3 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2022-10-14 | 2022-10-14 | 2022-10-14
200883C-000-DW-1920-4002 | [D] | 200883C | 0 | DW | 1920 | 4002 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 3 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-02-06 | 2023-02-06 | 2023-02-06
200883C-000-DW-1920-4003 | [D] | 200883C | 0 | DW | 1920 | 4003 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 4 | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-07-25 | 2022-07-25 | 2022-07-25 | 2022-07-25
200883C-000-DW-1920-4003 | [D] | 200883C | 0 | DW | 1920 | 4003 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 4 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-08-08 | 2022-08-08 | 2022-08-08
200883C-000-DW-1920-4003 | [D] | 200883C | 0 | DW | 1920 | 4003 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 4 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2022-10-14 | 2022-10-14 | 2022-10-14
200883C-000-DW-1920-4003 | [D] | 200883C | 0 | DW | 1920 | 4003 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 4 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-02-06 | 2023-02-06 | 2023-02-06
200883C-000-DW-1933-4000 | [D] | 200883C | 0 | DW | 1933 | 4000 |  | 36 |  | Yuri Phase 0 - Fire Fighting And Safety Equipment Layout Drawings - Sheet 1 | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-12-22 | 2022-12-22 | 2022-12-22
200883C-000-DW-1933-4000 | [D] | 200883C | 0 | DW | 1933 | 4000 |  | 36 |  | Yuri Phase 0 - Fire Fighting And Safety Equipment Layout Drawings - Sheet 1 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-12-28 | 2022-12-28 | 2022-12-28
200883C-000-DW-1933-4000 | [D] | 200883C | 0 | DW | 1933 | 4000 |  | 36 |  | Yuri Phase 0 - Fire Fighting And Safety Equipment Layout Drawings - Sheet 1 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2023-01-18 | 2023-01-18 | 2023-01-18
200883C-000-DW-1933-4000 | [D] | 200883C | 0 | DW | 1933 | 4000 |  | 36 |  | Yuri Phase 0 - Fire Fighting And Safety Equipment Layout Drawings - Sheet 1 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-02-23 | 2023-02-23 | 2023-02-23
200883C-000-DW-1933-4001 | [D] | 200883C | 0 | DW | 1933 | 4001 |  | 36 |  | Yuri Phase 0 - Fire Fighting And Safety Equipment Layout Drawings - Sheet 2 | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-12-22 | 2022-12-22 | 2022-12-22
200883C-000-DW-1933-4001 | [D] | 200883C | 0 | DW | 1933 | 4001 |  | 36 |  | Yuri Phase 0 - Fire Fighting And Safety Equipment Layout Drawings - Sheet 2 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-12-28 | 2022-12-28 | 2022-12-28
200883C-000-DW-1933-4001 | [D] | 200883C | 0 | DW | 1933 | 4001 |  | 36 |  | Yuri Phase 0 - Fire Fighting And Safety Equipment Layout Drawings - Sheet 2 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2023-01-18 | 2023-01-18 | 2023-01-18
200883C-000-DW-1933-4001 | [D] | 200883C | 0 | DW | 1933 | 4001 |  | 36 |  | Yuri Phase 0 - Fire Fighting And Safety Equipment Layout Drawings - Sheet 2 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-02-23 | 2023-02-23 | 2023-02-23
200883C-000-DW-1940-4000 | [D] | 200883C | 0 | DW | 1940 | 4000 |  | 44 |  | Yuri Phase 0 - Fire Zone Drawings | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-06-28 | 2022-06-28 | 2022-06-30 | 2022-06-30
200883C-000-DW-1940-4000 | [D] | 200883C | 0 | DW | 1940 | 4000 |  | 44 |  | Yuri Phase 0 - Fire Zone Drawings | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-07-04 | 2022-07-04 | 2022-06-30 | 2022-06-30
200883C-000-DW-1940-4000 | [D] | 200883C | 0 | DW | 1940 | 4000 |  | 44 |  | Yuri Phase 0 - Fire Zone Drawings | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2022-10-14 | 2022-10-14 | 2022-10-14
200883C-000-DW-1940-4000 | [D] | 200883C | 0 | DW | 1940 | 4000 |  | 44 |  | Yuri Phase 0 - Fire Zone Drawings | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-01-25 | 2023-01-25 | 2023-01-25
200883C-000-DW-1950-4000 | [D] | 200883C | 0 | DW | 1950 | 4000 |  | 44 |  | Yuri Phase 0 - Fire and Gas Detector Layout Drawings | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-07-18 | 2022-07-18 | 2022-07-18 | 2022-07-18
200883C-000-DW-1950-4000 | [D] | 200883C | 0 | DW | 1950 | 4000 |  | 44 |  | Yuri Phase 0 - Fire and Gas Detector Layout Drawings | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-07-22 | 2022-07-22 | 2022-08-19 | 2022-08-19
200883C-000-DW-1950-4000 | [D] | 200883C | 0 | DW | 1950 | 4000 |  | 44 |  | Yuri Phase 0 - Fire and Gas Detector Layout Drawings | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2022-10-12 | 2022-10-12 | 2022-10-12
200883C-000-DW-1950-4000 | [D] | 200883C | 0 | DW | 1950 | 4000 |  | 44 |  | Yuri Phase 0 - Fire and Gas Detector Layout Drawings | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-02-02 | 2023-02-02 | 2023-02-02
200883C-000-DW-1960-4000 | [D] | 200883C | 0 | DW | 1960 | 4000 |  | 29 |  | Yuri Phase 0 - Escape Route and Safety Equipment Layout - Sheet 1 | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-12-15 | 2022-12-15 | 2022-12-15
200883C-000-DW-1960-4000 | [D] | 200883C | 0 | DW | 1960 | 4000 |  | 29 |  | Yuri Phase 0 - Escape Route and Safety Equipment Layout - Sheet 1 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-12-21 | 2022-12-21 | 2022-12-21
200883C-000-DW-1960-4000 | [D] | 200883C | 0 | DW | 1960 | 4000 |  | 29 |  | Yuri Phase 0 - Escape Route and Safety Equipment Layout - Sheet 1 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2023-01-11 | 2023-01-11 | 2023-01-11
200883C-000-DW-1960-4000 | [D] | 200883C | 0 | DW | 1960 | 4000 |  | 29 |  | Yuri Phase 0 - Escape Route and Safety Equipment Layout - Sheet 1 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-02-23 | 2023-02-23 | 2023-02-23
200883C-000-DW-1960-4001 | [D] | 200883C | 0 | DW | 1960 | 4001 |  | 29 |  | Yuri Phase 0 - Escape Route and Safety Equipment Layout - Sheet 2 | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-12-15 | 2022-12-15 | 2022-12-15
200883C-000-DW-1960-4001 | [D] | 200883C | 0 | DW | 1960 | 4001 |  | 29 |  | Yuri Phase 0 - Escape Route and Safety Equipment Layout - Sheet 2 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-12-21 | 2022-12-21 | 2022-12-21
200883C-000-DW-1960-4001 | [D] | 200883C | 0 | DW | 1960 | 4001 |  | 29 |  | Yuri Phase 0 - Escape Route and Safety Equipment Layout - Sheet 2 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2023-01-11 | 2023-01-11 | 2023-01-11
200883C-000-DW-1960-4001 | [D] | 200883C | 0 | DW | 1960 | 4001 |  | 29 |  | Yuri Phase 0 - Escape Route and Safety Equipment Layout - Sheet 2 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-02-23 | 2023-02-23 | 2023-02-23
200883C-000-DW-1965-4000 | [D] | 200883C | 0 | DW | 1965 | 4000 |  | 29 |  | Yuri Phase 0 - Safety Sign Layout Drawings | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-12-22 | 2022-12-22 | 2022-12-22
200883C-000-DW-1965-4000 | [D] | 200883C | 0 | DW | 1965 | 4000 |  | 29 |  | Yuri Phase 0 - Safety Sign Layout Drawings | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-12-28 | 2022-12-28 | 2022-12-28
200883C-000-DW-1965-4000 | [D] | 200883C | 0 | DW | 1965 | 4000 |  | 29 |  | Yuri Phase 0 - Safety Sign Layout Drawings | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2023-01-18 | 2023-01-18 | 2023-01-18
200883C-000-DW-1965-4000 | [D] | 200883C | 0 | DW | 1965 | 4000 |  | 29 |  | Yuri Phase 0 - Safety Sign Layout Drawings | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-03-02 | 2023-03-02 | 2023-03-02
200883C-000-JSC-1800-5000 | [D] | 200883C | 0 | JSC | 1800 | 5000 |  | 1 |  | Yuri Phase 0 - Specification for Fence (PV and H2 plant) (DELETED 3-Aug-22) | Code: E0303 | CIV | 000PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-05-31 | 2022-05-31 | 2022-05-31 | 2022-05-31
200883C-000-JSC-1800-5000 | [D] | 200883C | 0 | JSC | 1800 | 5000 |  | 1 |  | Yuri Phase 0 - Specification for Fence (PV and H2 plant) (DELETED 3-Aug-22) | Code: E0303 | CIV | 000PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-07-29 | 2022-07-29
200883C-000-JSC-1800-5000 | [D] | 200883C | 0 | JSC | 1800 | 5000 |  | 1 |  | Yuri Phase 0 - Specification for Fence (PV and H2 plant) (DELETED 3-Aug-22) | Code: E0303 | CIV | 000PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-29 | 2022-07-29
200883C-000-JSD-0000-4100 | [D] | 200883C | 0 | JSD | 0 | 4100 |  | 47 |  | Yuri Phase 0 – Process Basis Of Design | Code: E0301 | PRO | 000H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-05-06 | 2022-05-06
200883C-000-JSD-0000-4100 | [D] | 200883C | 0 | JSD | 0 | 4100 |  | 47 |  | Yuri Phase 0 – Process Basis Of Design | Code: E0301 | PRO | 000H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-05-24 | 2022-05-24 | 2022-05-06 | 2022-05-06
200883C-000-JSD-0000-4100 | [D] | 200883C | 0 | JSD | 0 | 4100 |  | 47 |  | Yuri Phase 0 – Process Basis Of Design | Code: E0301 | PRO | 000H2 |  |  |  |  | IFD | 100 |  |  | MPRO | 2022-06-21 | 2022-06-21 | 2022-07-20 | 2022-07-20
200883C-000-JSD-1300-4001 | [D] | 200883C | 0 | JSD | 1300 | 4001 |  | 23 |  | Yuri Phase 0-Stress Design Basis | Code: E0301 | PIP | 000H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-05-30 | 2022-05-30 | 2022-06-10 | 2022-06-10
200883C-000-JSD-1300-4001 | [D] | 200883C | 0 | JSD | 1300 | 4001 |  | 23 |  | Yuri Phase 0-Stress Design Basis | Code: E0301 | PIP | 000H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2022-06-10 | 2022-06-10 | 2022-06-21 | 2022-06-21
200883C-000-JSD-1300-4001 | [D] | 200883C | 0 | JSD | 1300 | 4001 |  | 23 |  | Yuri Phase 0-Stress Design Basis | Code: E0301 | PIP | 000H2 |  |  |  |  | IFD | 100 |  |  | MPIP | 2022-07-08 | 2022-07-08 | 2022-07-23 | 2022-07-23
200883C-000-JSD-1300-4002 | [D] | 200883C | 0 | JSD | 1300 | 4002 |  | 90 |  | Yuri Phase 0-Piping Material Specification | Code: E0301 | PIP | 000H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-06-06 | 2022-06-06 | 2022-06-21 | 2022-06-21
200883C-000-JSD-1300-4002 | [D] | 200883C | 0 | JSD | 1300 | 4002 |  | 90 |  | Yuri Phase 0-Piping Material Specification | Code: E0301 | PIP | 000H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2022-06-24 | 2022-06-24 | 2022-06-21 | 2022-06-21
200883C-000-JSD-1300-4002 | [D] | 200883C | 0 | JSD | 1300 | 4002 |  | 90 |  | Yuri Phase 0-Piping Material Specification | Code: E0301 | PIP | 000H2 |  |  |  |  | IFD | 100 |  |  | MPIP | 2022-07-22 | 2022-07-22 | 2022-07-28 | 2022-07-28
200883C-000-JSD-1300-4004 | [D] | 200883C | 0 | JSD | 1300 | 4004 |  | 23 |  | Yuri Phase 0-Piping Support Standard | Code: E0301 | PIP | 000H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-05-20 | 2022-05-20 | 2022-05-27 | 2022-05-27
200883C-000-JSD-1300-4004 | [D] | 200883C | 0 | JSD | 1300 | 4004 |  | 23 |  | Yuri Phase 0-Piping Support Standard | Code: E0301 | PIP | 000H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2022-05-27 | 2022-05-27 | 2022-06-14 | 2022-06-14
200883C-000-JSD-1300-4004 | [D] | 200883C | 0 | JSD | 1300 | 4004 |  | 23 |  | Yuri Phase 0-Piping Support Standard | Code: E0301 | PIP | 000H2 |  |  |  |  | IFD | 100 |  |  | MPIP | 2022-06-24 | 2022-06-24 | 2022-07-22 | 2022-07-22
200883C-000-JSD-1300-4005 | [D] | 200883C | 0 | JSD | 1300 | 4005 |  | 12 |  | Yuri Phase 0- Coating and Painting Specification | Code: E0301 | PIP | 000H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-06-06 | 2022-06-06 | 2022-06-06 | 2022-06-06
200883C-000-JSD-1300-4005 | [D] | 200883C | 0 | JSD | 1300 | 4005 |  | 12 |  | Yuri Phase 0- Coating and Painting Specification | Code: E0301 | PIP | 000H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2022-06-13 | 2022-06-13 | 2022-07-25 | 2022-07-25
200883C-000-JSD-1300-4005 | [D] | 200883C | 0 | JSD | 1300 | 4005 |  | 12 |  | Yuri Phase 0- Coating and Painting Specification | Code: E0301 | PIP | 000H2 |  |  |  |  | IFD | 100 |  |  | MPIP | 2022-07-11 | 2022-07-11 | 2022-07-25 | 2022-07-25
200883C-000-JSD-1300-4006 | [D] | 200883C | 0 | JSD | 1300 | 4006 |  | 12 |  | Yuri Phase 0-Insulation Specification | Code: E0301 | PIP | 000H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-08-19 | 2022-08-19 | 2022-08-19 | 2022-08-19
200883C-000-JSD-1300-4006 | [D] | 200883C | 0 | JSD | 1300 | 4006 |  | 12 |  | Yuri Phase 0-Insulation Specification | Code: E0301 | PIP | 000H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2022-08-26 | 2022-08-26 | 2022-08-26
200883C-000-JSD-1300-4006 | [D] | 200883C | 0 | JSD | 1300 | 4006 |  | 12 |  | Yuri Phase 0-Insulation Specification | Code: E0301 | PIP | 000H2 |  |  |  |  | IFD | 100 |  |  | MPIP | 2022-09-23 | 2022-09-23 | 2022-09-23
200883C-000-JSD-1500-1000 | [D] | 200883C | 0 | JSD | 1500 | 1000 |  | 40 |  | Yuri Phase 0 - Instrument and Control Basis Of Design | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | AINS | 2022-05-02 | 2022-05-02 | 2022-05-18 | 2022-05-18
200883C-000-JSD-1500-1000 | [D] | 200883C | 0 | JSD | 1500 | 1000 |  | 40 |  | Yuri Phase 0 - Instrument and Control Basis Of Design | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | AINS | 2022-05-20 | 2022-05-20 | 2022-05-18 | 2022-05-18
200883C-000-JSD-1500-1000 | [D] | 200883C | 0 | JSD | 1500 | 1000 |  | 40 |  | Yuri Phase 0 - Instrument and Control Basis Of Design | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | AINS | 2022-08-31 | 2022-08-31 | 2022-08-15 | 2022-08-15
200883C-000-JSD-1510-1000 | [D] | 200883C | 0 | JSD | 1510 | 1000 |  | 40 |  | Yuri Phase 0 - ICS Typical Loop Definition | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | AINS | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-000-JSD-1510-1000 | [D] | 200883C | 0 | JSD | 1510 | 1000 |  | 40 |  | Yuri Phase 0 - ICS Typical Loop Definition | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | AINS | 2022-08-13 | 2022-08-13 | 2022-09-02
200883C-000-JSD-1510-1000 | [D] | 200883C | 0 | JSD | 1510 | 1000 |  | 40 |  | Yuri Phase 0 - ICS Typical Loop Definition | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | AINS | 2022-09-10 | 2022-09-10 | 2022-10-03
200883C-000-JSD-1510-1001 | [D] | 200883C | 0 | JSD | 1510 | 1001 |  | 240 |  | Yuri Phase 0 - ICS Control Narrative | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | AINS | 2022-08-30 | 2022-08-30 | 2022-10-18
200883C-000-JSD-1510-1001 | [D] | 200883C | 0 | JSD | 1510 | 1001 |  | 240 |  | Yuri Phase 0 - ICS Control Narrative | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | AINS | 2022-09-19 | 2022-09-19 | 2022-11-07
200883C-000-JSD-1510-1001 | [D] | 200883C | 0 | JSD | 1510 | 1001 |  | 240 |  | Yuri Phase 0 - ICS Control Narrative | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | AINS | 2022-10-18 | 2022-10-18 | 2022-12-05
200883C-000-JSD-1510-1002 | [D] | 200883C | 0 | JSD | 1510 | 1002 |  | 80 |  | Yuri Phase 0 - Cyber Security Dossier | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | AINS | 2022-09-20 | 2022-09-20 | 2022-11-08
200883C-000-JSD-1510-1002 | [D] | 200883C | 0 | JSD | 1510 | 1002 |  | 80 |  | Yuri Phase 0 - Cyber Security Dossier | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | AINS | 2022-10-11 | 2022-10-11 | 2022-11-28
200883C-000-JSD-1510-1002 | [D] | 200883C | 0 | JSD | 1510 | 1002 |  | 80 |  | Yuri Phase 0 - Cyber Security Dossier | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | AINS | 2022-11-08 | 2022-11-08 | 2023-01-03
200883C-000-JSD-1510-1003 | [D] | 200883C | 0 | JSD | 1510 | 1003 |  | 120 |  | Yuri Phase 0 - ICS Alarm Management Specification | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | AINS | 2022-04-02 | 2022-04-02 | 2022-04-02 | 2022-04-02
200883C-000-JSD-1510-1003 | [D] | 200883C | 0 | JSD | 1510 | 1003 |  | 120 |  | Yuri Phase 0 - ICS Alarm Management Specification | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | AINS | 2022-07-16 | 2022-07-16 | 2022-10-25
200883C-000-JSD-1510-1003 | [D] | 200883C | 0 | JSD | 1510 | 1003 |  | 120 |  | Yuri Phase 0 - ICS Alarm Management Specification | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | AINS | 2022-09-30 | 2022-09-30 | 2022-11-18
200883C-000-JSD-1600-1000 | [D] | 200883C | 0 | JSD | 1600 | 1000 |  | 40 |  | Yuri Phase 0 - Electrical Design Basis (BOD) | Code: E0304 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | AELE | 2022-04-02 | 2022-04-02 | 2022-05-16 | 2022-05-16
200883C-000-JSD-1600-1000 | [D] | 200883C | 0 | JSD | 1600 | 1000 |  | 40 |  | Yuri Phase 0 - Electrical Design Basis (BOD) | Code: E0304 | ELE | 000H2 |  |  |  |  | IFD | 70 |  |  | AELE | 2022-04-22 | 2022-04-22 | 2022-05-16 | 2022-05-16
200883C-000-JSD-1600-1000 | [D] | 200883C | 0 | JSD | 1600 | 1000 |  | 40 |  | Yuri Phase 0 - Electrical Design Basis (BOD) | Code: E0304 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | AELE | 2022-07-31 | 2022-07-31 | 2022-08-29
200883C-000-JSD-1600-1001 | [D] | 200883C | 0 | JSD | 1600 | 1001 |  | 60 |  | Yuri Phase 0 - EEHA Management Plan | Code: E0304 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | AELE | 2022-05-30 | 2022-05-30 | 2022-06-30 | 2022-06-30
200883C-000-JSD-1600-1001 | [D] | 200883C | 0 | JSD | 1600 | 1001 |  | 60 |  | Yuri Phase 0 - EEHA Management Plan | Code: E0304 | ELE | 000H2 |  |  |  |  | IFD | 70 |  |  | AELE | 2022-06-20 | 2022-06-20 | 2022-06-30 | 2022-06-30
200883C-000-JSD-1600-1001 | [D] | 200883C | 0 | JSD | 1600 | 1001 |  | 60 |  | Yuri Phase 0 - EEHA Management Plan | Code: E0304 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | AELE | 2022-08-31 | 2022-08-31 | 2022-08-25 | 2022-08-25
200883C-000-JSD-1600-4000 | [D] | 200883C | 0 | JSD | 1600 | 4000 |  | 41 |  | Yuri Phase 0 - Earthing Philosophy | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-06 | 2022-06-06 | 2022-06-06 | 2022-06-06
200883C-000-JSD-1600-4000 | [D] | 200883C | 0 | JSD | 1600 | 4000 |  | 41 |  | Yuri Phase 0 - Earthing Philosophy | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-10 | 2022-06-10 | 2022-07-29 | 2022-07-29
200883C-000-JSD-1600-4000 | [D] | 200883C | 0 | JSD | 1600 | 4000 |  | 41 |  | Yuri Phase 0 - Earthing Philosophy | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-08 | 2022-07-08 | 2022-08-23 | 2022-08-23
200883C-000-JSD-1700-2000 | [D] | 200883C | 0 | JSD | 1700 | 2000 |  | 99 |  | Yuri Phase 0 - Basis of Design - Concrete Works And Foundations | Code: E0301 | CIV | 000H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-05-25 | 2022-05-25 | 2022-05-31 | 2022-05-31
200883C-000-JSD-1700-2000 | [D] | 200883C | 0 | JSD | 1700 | 2000 |  | 99 |  | Yuri Phase 0 - Basis of Design - Concrete Works And Foundations | Code: E0301 | CIV | 000H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-05-31 | 2022-05-31 | 2022-06-09 | 2022-06-09
200883C-000-JSD-1700-2000 | [D] | 200883C | 0 | JSD | 1700 | 2000 |  | 99 |  | Yuri Phase 0 - Basis of Design - Concrete Works And Foundations | Code: E0301 | CIV | 000H2 |  |  |  |  | IFD | 100 |  |  | BCIV | 2022-06-28 | 2022-06-28 | 2022-07-29 | 2022-07-29
200883C-000-JSD-1800-1000 | [D] | 200883C | 0 | JSD | 1800 | 1000 |  | 40 |  | Yuri Phase 0 - Basis of Design - Steel Structures | Code: E0303 | STR | 000H2 |  |  |  |  | STA | 10 |  |  | ASTR | 2022-04-02 | 2022-04-02 | 2022-05-06 | 2022-05-06
200883C-000-JSD-1800-1000 | [D] | 200883C | 0 | JSD | 1800 | 1000 |  | 40 |  | Yuri Phase 0 - Basis of Design - Steel Structures | Code: E0303 | STR | 000H2 |  |  |  |  | IFR | 70 |  |  | ASTR | 2022-04-22 | 2022-04-22 | 2022-05-06 | 2022-05-06
200883C-000-JSD-1800-1000 | [D] | 200883C | 0 | JSD | 1800 | 1000 |  | 40 |  | Yuri Phase 0 - Basis of Design - Steel Structures | Code: E0303 | STR | 000H2 |  |  |  |  | IFC | 100 |  |  | ASTR | 2022-08-31 | 2022-08-31 | 2022-08-25 | 2022-08-25
200883C-000-JSD-1900-1000 | [D] | 200883C | 0 | JSD | 1900 | 1000 |  | 20 |  | Yuri Phase 0 - Safety Philosophy | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-06-28 | 2022-06-28 | 2022-06-30 | 2022-06-30
200883C-000-JSD-1900-1000 | [D] | 200883C | 0 | JSD | 1900 | 1000 |  | 20 |  | Yuri Phase 0 - Safety Philosophy | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-07-18 | 2022-07-18 | 2022-06-30 | 2022-06-30
200883C-000-JSD-1900-1000 | [D] | 200883C | 0 | JSD | 1900 | 1000 |  | 20 |  | Yuri Phase 0 - Safety Philosophy | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-08-15 | 2022-08-15 | 2022-08-29
200883C-000-JSD-6300-1000 | [D] | 200883C | 0 | JSD | 6300 | 1000 |  | 80 |  | Yuri Phase 0 - General Specification for General Equipment and Piping Welding - Fabrication and Inspection | Code: E0303 | MEC | 000H2 |  |  |  |  | STA | 10 |  |  | AMEC | 2022-07-08 | 2022-07-08 | 2022-07-08
200883C-000-JSD-6300-1000 | [D] | 200883C | 0 | JSD | 6300 | 1000 |  | 80 |  | Yuri Phase 0 - General Specification for General Equipment and Piping Welding - Fabrication and Inspection | Code: E0303 | MEC | 000H2 |  |  |  |  | IFR | 70 |  |  | AMEC | 2022-08-31 | 2022-08-31 | 2022-08-31
200883C-000-JSD-6300-1000 | [D] | 200883C | 0 | JSD | 6300 | 1000 |  | 80 |  | Yuri Phase 0 - General Specification for General Equipment and Piping Welding - Fabrication and Inspection | Code: E0303 | MEC | 000H2 |  |  |  |  | IFC | 100 |  |  | AMEC | 2022-11-30 | 2022-11-30 | 2022-11-30
200883C-000-JSS-1300-4000 | [D] | 200883C | 0 | JSS | 1300 | 4000 |  | 12 |  | Yuri Phase 0-Technical Notes for marking of Piping Materials | Code: E0301 | PIP | 000H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-06-18 | 2022-06-18 | 2022-06-25 | 2022-06-25
200883C-000-JSS-1300-4000 | [D] | 200883C | 0 | JSS | 1300 | 4000 |  | 12 |  | Yuri Phase 0-Technical Notes for marking of Piping Materials | Code: E0301 | PIP | 000H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2022-06-25 | 2022-06-25 | 2022-06-27 | 2022-06-27
200883C-000-JSS-1300-4000 | [D] | 200883C | 0 | JSS | 1300 | 4000 |  | 12 |  | Yuri Phase 0-Technical Notes for marking of Piping Materials | Code: E0301 | PIP | 000H2 |  |  |  |  | IFD | 100 |  |  | MPIP | 2022-07-23 | 2022-07-23 | 2022-08-22 | 2022-08-22
200883C-000-JSS-1310-4000 | [D] | 200883C | 0 | JSS | 1310 | 4000 |  | 12 |  | Yuri Phase 0-Technical Notes for Valves | Code: E0301 | PIP | 000H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-06-18 | 2022-06-18 | 2022-06-16 | 2022-06-16
200883C-000-JSS-1310-4000 | [D] | 200883C | 0 | JSS | 1310 | 4000 |  | 12 |  | Yuri Phase 0-Technical Notes for Valves | Code: E0301 | PIP | 000H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2022-06-25 | 2022-06-25 | 2022-06-16 | 2022-06-16
200883C-000-JSS-1310-4000 | [D] | 200883C | 0 | JSS | 1310 | 4000 |  | 12 |  | Yuri Phase 0-Technical Notes for Valves | Code: E0301 | PIP | 000H2 |  |  |  |  | IFD | 100 |  |  | MPIP | 2022-07-23 | 2022-07-23 | 2022-07-21 | 2022-07-21
200883C-000-JSS-1320-4000 | [D] | 200883C | 0 | JSS | 1320 | 4000 |  | 12 |  | Yuri Phase 0-Technical Notes for Pipes & Fittings | Code: E0301 | PIP | 000H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-06-18 | 2022-06-18 | 2022-06-16 | 2022-06-16
200883C-000-JSS-1320-4000 | [D] | 200883C | 0 | JSS | 1320 | 4000 |  | 12 |  | Yuri Phase 0-Technical Notes for Pipes & Fittings | Code: E0301 | PIP | 000H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2022-06-25 | 2022-06-25 | 2022-06-16 | 2022-06-16
200883C-000-JSS-1320-4000 | [D] | 200883C | 0 | JSS | 1320 | 4000 |  | 12 |  | Yuri Phase 0-Technical Notes for Pipes & Fittings | Code: E0301 | PIP | 000H2 |  |  |  |  | IFD | 100 |  |  | MPIP | 2022-07-23 | 2022-07-23 | 2022-07-21 | 2022-07-21
200883C-000-JSS-1394-4000 | [D] | 200883C | 0 | JSS | 1394 | 4000 |  | 12 |  | Yuri Phase 0-Technical Notes for felxible hoses, Quick connect coupler & adaptor | Code: E0301 | PIP | 000H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-06-18 | 2022-06-18 | 2022-06-18 | 2022-06-18
200883C-000-JSS-1394-4000 | [D] | 200883C | 0 | JSS | 1394 | 4000 |  | 12 |  | Yuri Phase 0-Technical Notes for felxible hoses, Quick connect coupler & adaptor | Code: E0301 | PIP | 000H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2022-06-25 | 2022-06-25 | 2022-07-14 | 2022-07-14
200883C-000-JSS-1394-4000 | [D] | 200883C | 0 | JSS | 1394 | 4000 |  | 12 |  | Yuri Phase 0-Technical Notes for felxible hoses, Quick connect coupler & adaptor | Code: E0301 | PIP | 000H2 |  |  |  |  | IFD | 100 |  |  | MPIP | 2022-07-23 | 2022-07-23 | 2022-08-05 | 2022-08-05
200883C-000-JSS-1395-4000 | [D] | 200883C | 0 | JSS | 1395 | 4000 |  | 12 |  | Yuri Phase 0-Technical Notes of Strainer | Code: E0301 | PIP | 000H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-06-18 | 2022-06-18 | 2022-06-18 | 2022-06-18
200883C-000-JSS-1395-4000 | [D] | 200883C | 0 | JSS | 1395 | 4000 |  | 12 |  | Yuri Phase 0-Technical Notes of Strainer | Code: E0301 | PIP | 000H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2022-06-25 | 2022-06-25 | 2022-07-14 | 2022-07-14
200883C-000-JSS-1395-4000 | [D] | 200883C | 0 | JSS | 1395 | 4000 |  | 12 |  | Yuri Phase 0-Technical Notes of Strainer | Code: E0301 | PIP | 000H2 |  |  |  |  | IFD | 100 |  |  | MPIP | 2022-07-23 | 2022-07-23 | 2022-08-05 | 2022-08-05
200883C-000-JSS-1510-5000 | [D] | 200883C | 0 | JSS | 1510 | 5000 |  | 1 |  | Yuri Phase 0 - Technical Data Sheet of RTU (DELETED 3-Aug-22) | Code: E0303 | INS | 000PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-04-03 | 2022-04-03 | 2022-05-01 | 2022-05-01
200883C-000-JSS-1510-5000 | [D] | 200883C | 0 | JSS | 1510 | 5000 |  | 1 |  | Yuri Phase 0 - Technical Data Sheet of RTU (DELETED 3-Aug-22) | Code: E0303 | INS | 000PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-05-03 | 2022-05-03 | 2022-06-30 | 2022-06-30
200883C-000-JSS-1510-5000 | [D] | 200883C | 0 | JSS | 1510 | 5000 |  | 1 |  | Yuri Phase 0 - Technical Data Sheet of RTU (DELETED 3-Aug-22) | Code: E0303 | INS | 000PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-06-02 | 2022-06-02 | 2022-07-29 | 2022-07-29
200883C-000-JSS-1511-1000 | [D] | 200883C | 0 | JSS | 1511 | 1000 |  | 120 |  | Yuri Phase 0 – Specification for ICS and SCADA System | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | AINS | 2022-05-02 | 2022-05-02 | 2022-05-20 | 2022-05-20
200883C-000-JSS-1511-1000 | [D] | 200883C | 0 | JSS | 1511 | 1000 |  | 120 |  | Yuri Phase 0 – Specification for ICS and SCADA System | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | AINS | 2022-05-20 | 2022-05-20 | 2022-06-09 | 2022-06-09
200883C-000-JSS-1511-1000 | [D] | 200883C | 0 | JSS | 1511 | 1000 |  | 120 |  | Yuri Phase 0 – Specification for ICS and SCADA System | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | AINS | 2022-06-20 | 2022-06-20 | 2022-08-30
200883C-000-JSS-1574-5000 | [D] | 200883C | 0 | JSS | 1574 | 5000 |  | 40 |  | Yuri Phase 0 - FO Cable Datasheet | Code: E0303 | INS | 000PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-05-16 | 2022-05-16 | 2022-05-16 | 2022-05-16
200883C-000-JSS-1574-5000 | [D] | 200883C | 0 | JSS | 1574 | 5000 |  | 40 |  | Yuri Phase 0 - FO Cable Datasheet | Code: E0303 | INS | 000PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-06-15 | 2022-06-15 | 2022-08-29
200883C-000-JSS-1574-5000 | [D] | 200883C | 0 | JSS | 1574 | 5000 |  | 40 |  | Yuri Phase 0 - FO Cable Datasheet | Code: E0303 | INS | 000PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-07-15 | 2022-07-15 | 2022-09-08
200883C-000-JSS-1620-4000 | [D] | 200883C | 0 | JSS | 1620 | 4000 |  | 21 |  | Yuri Phase 0 - General Electrical Installation Requirements | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-06 | 2022-06-06 | 2022-06-06 | 2022-06-06
200883C-000-JSS-1620-4000 | [D] | 200883C | 0 | JSS | 1620 | 4000 |  | 21 |  | Yuri Phase 0 - General Electrical Installation Requirements | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-10 | 2022-06-10 | 2022-07-29 | 2022-07-29
200883C-000-JSS-1620-4000 | [D] | 200883C | 0 | JSS | 1620 | 4000 |  | 21 |  | Yuri Phase 0 - General Electrical Installation Requirements | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-08 | 2022-07-08 | 2022-08-22
200883C-000-JSS-1620-4001 | [D] | 200883C | 0 | JSS | 1620 | 4001 |  | 21 |  | Yuri Phase 0 - Specification for Bulk Material | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-09 | 2022-06-09 | 2022-06-09 | 2022-06-09
200883C-000-JSS-1620-4001 | [D] | 200883C | 0 | JSS | 1620 | 4001 |  | 21 |  | Yuri Phase 0 - Specification for Bulk Material | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-07-13 | 2022-07-13
200883C-000-JSS-1620-4001 | [D] | 200883C | 0 | JSS | 1620 | 4001 |  | 21 |  | Yuri Phase 0 - Specification for Bulk Material | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-06 | 2022-07-06 | 2022-08-03 | 2022-08-03
200883C-000-JSS-1621-4000 | [D] | 200883C | 0 | JSS | 1621 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Power And Control Cables | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-06 | 2022-06-06 | 2022-06-10 | 2022-06-10
200883C-000-JSS-1621-4000 | [D] | 200883C | 0 | JSS | 1621 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Power And Control Cables | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-10 | 2022-06-10 | 2022-06-10 | 2022-06-10
200883C-000-JSS-1621-4000 | [D] | 200883C | 0 | JSS | 1621 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Power And Control Cables | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-01 | 2022-07-01 | 2022-08-01 | 2022-08-01
200883C-000-JSS-1628-4000 | [D] | 200883C | 0 | JSS | 1628 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Power Distribution Boards | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-09 | 2022-06-09 | 2022-06-09 | 2022-06-09
200883C-000-JSS-1628-4000 | [D] | 200883C | 0 | JSS | 1628 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Power Distribution Boards | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-07-13 | 2022-07-13
200883C-000-JSS-1628-4000 | [D] | 200883C | 0 | JSS | 1628 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Power Distribution Boards | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-06 | 2022-07-06 | 2022-08-03 | 2022-08-03
200883C-000-JSS-1641-4000 | [D] | 200883C | 0 | JSS | 1641 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Neutral Grounding Resistor | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-05-25 | 2022-05-25 | 2022-05-31 | 2022-05-31
200883C-000-JSS-1641-4000 | [D] | 200883C | 0 | JSS | 1641 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Neutral Grounding Resistor | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-05-31 | 2022-05-31 | 2022-06-07 | 2022-06-07
200883C-000-JSS-1641-4000 | [D] | 200883C | 0 | JSS | 1641 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Neutral Grounding Resistor | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-06-21 | 2022-06-21 | 2022-07-29 | 2022-07-29
200883C-000-JSS-1652-4000 | [D] | 200883C | 0 | JSS | 1652 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for HV Switchgear | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-05-25 | 2022-05-25 | 2022-05-30 | 2022-05-30
200883C-000-JSS-1652-4000 | [D] | 200883C | 0 | JSS | 1652 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for HV Switchgear | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-05-31 | 2022-05-31 | 2022-05-30 | 2022-05-30
200883C-000-JSS-1652-4000 | [D] | 200883C | 0 | JSS | 1652 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for HV Switchgear | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-06-21 | 2022-06-21 | 2022-07-29 | 2022-07-29
200883C-000-JSS-1654-4000 | [D] | 200883C | 0 | JSS | 1654 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for LV Switchgear | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-05-25 | 2022-05-25 | 2022-05-31 | 2022-05-31
200883C-000-JSS-1654-4000 | [D] | 200883C | 0 | JSS | 1654 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for LV Switchgear | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-05-31 | 2022-05-31 | 2022-06-01 | 2022-06-01
200883C-000-JSS-1654-4000 | [D] | 200883C | 0 | JSS | 1654 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for LV Switchgear | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-06-21 | 2022-06-21 | 2022-07-29 | 2022-07-29
200883C-000-JSS-1661-4000 | [D] | 200883C | 0 | JSS | 1661 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Variable Speed Drives | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-05-25 | 2022-05-25 | 2022-05-25 | 2022-05-25
200883C-000-JSS-1661-4000 | [D] | 200883C | 0 | JSS | 1661 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Variable Speed Drives | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-05-31 | 2022-05-31 | 2022-07-07 | 2022-07-07
200883C-000-JSS-1661-4000 | [D] | 200883C | 0 | JSS | 1661 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Variable Speed Drives | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-06-21 | 2022-06-21 | 2022-07-29 | 2022-07-29
200883C-000-JSS-1662-4000 | [D] | 200883C | 0 | JSS | 1662 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Numerical Relays | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-05-25 | 2022-05-25 | 2022-05-31 | 2022-05-31
200883C-000-JSS-1662-4000 | [D] | 200883C | 0 | JSS | 1662 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Numerical Relays | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-05-31 | 2022-05-31 | 2022-06-08 | 2022-06-08
200883C-000-JSS-1662-4000 | [D] | 200883C | 0 | JSS | 1662 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Numerical Relays | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-06-21 | 2022-06-21 | 2022-07-29 | 2022-07-29
200883C-000-JSS-1671-4000 | [D] | 200883C | 0 | JSS | 1671 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for AC UPS System | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-09 | 2022-06-09 | 2022-06-15 | 2022-06-15
200883C-000-JSS-1671-4000 | [D] | 200883C | 0 | JSS | 1671 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for AC UPS System | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-06-16 | 2022-06-16
200883C-000-JSS-1671-4000 | [D] | 200883C | 0 | JSS | 1671 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for AC UPS System | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-06 | 2022-07-06 | 2022-08-22 | 2022-08-22
200883C-000-JSS-1672-4000 | [D] | 200883C | 0 | JSS | 1672 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for DC UPS Systems | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-09 | 2022-06-09 | 2022-06-15 | 2022-06-15
200883C-000-JSS-1672-4000 | [D] | 200883C | 0 | JSS | 1672 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for DC UPS Systems | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-06-30 | 2022-06-30
200883C-000-JSS-1672-4000 | [D] | 200883C | 0 | JSS | 1672 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for DC UPS Systems | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-06 | 2022-07-06 | 2022-07-29 | 2022-07-29
200883C-000-JSS-1673-4000 | [D] | 200883C | 0 | JSS | 1673 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for NICD Battery | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-09 | 2022-06-09 | 2022-06-09 | 2022-06-09
200883C-000-JSS-1673-4000 | [D] | 200883C | 0 | JSS | 1673 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for NICD Battery | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-07-12 | 2022-07-12
200883C-000-JSS-1673-4000 | [D] | 200883C | 0 | JSS | 1673 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for NICD Battery | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-06 | 2022-07-06 | 2022-07-12 | 2022-07-12
200883C-000-JSS-1673-4001 | [D] | 200883C | 0 | JSS | 1673 | 4001 |  | 21 |  | Yuri Phase 0 - Specification for VRLA Battery | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-09 | 2022-06-09 | 2022-06-15 | 2022-06-15
200883C-000-JSS-1673-4001 | [D] | 200883C | 0 | JSS | 1673 | 4001 |  | 21 |  | Yuri Phase 0 - Specification for VRLA Battery | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-06-29 | 2022-06-29
200883C-000-JSS-1673-4001 | [D] | 200883C | 0 | JSS | 1673 | 4001 |  | 21 |  | Yuri Phase 0 - Specification for VRLA Battery | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-06 | 2022-07-06 | 2022-07-29 | 2022-07-29
200883C-000-JSS-1680-4000 | [D] | 200883C | 0 | JSS | 1680 | 4000 |  | 21 |  | Yuri Phase 0 - Package Units Electrical Specification | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-06 | 2022-06-06 | 2022-06-10 | 2022-06-10
200883C-000-JSS-1680-4000 | [D] | 200883C | 0 | JSS | 1680 | 4000 |  | 21 |  | Yuri Phase 0 - Package Units Electrical Specification | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-10 | 2022-06-10 | 2022-06-13 | 2022-06-13
200883C-000-JSS-1680-4000 | [D] | 200883C | 0 | JSS | 1680 | 4000 |  | 21 |  | Yuri Phase 0 - Package Units Electrical Specification | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-01 | 2022-07-01 | 2022-07-29 | 2022-07-29
200883C-000-JSS-1691-4000 | [D] | 200883C | 0 | JSS | 1691 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for LV Motors | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-05-25 | 2022-05-25 | 2022-05-16 | 2022-05-16
200883C-000-JSS-1691-4000 | [D] | 200883C | 0 | JSS | 1691 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for LV Motors | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-05-31 | 2022-05-31 | 2022-05-16 | 2022-05-16
200883C-000-JSS-1691-4000 | [D] | 200883C | 0 | JSS | 1691 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for LV Motors | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-06-21 | 2022-06-21 | 2022-07-29 | 2022-07-29
200883C-000-JSS-1800-4000 | [D] | 200883C | 0 | JSS | 1800 | 4000 |  | 62 |  | Specification for Structural Steel Fabrication & Painting for Structures | Code: E0301 | STR | 000H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-05-16 | 2022-05-16 | 2022-06-01 | 2022-06-01
200883C-000-JSS-1800-4000 | [D] | 200883C | 0 | JSS | 1800 | 4000 |  | 62 |  | Specification for Structural Steel Fabrication & Painting for Structures | Code: E0301 | STR | 000H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-05-27 | 2022-05-27 | 2022-06-17 | 2022-06-17
200883C-000-JSS-1800-4000 | [D] | 200883C | 0 | JSS | 1800 | 4000 |  | 62 |  | Specification for Structural Steel Fabrication & Painting for Structures | Code: E0301 | STR | 000H2 |  |  |  |  | IFD | 100 |  |  | MSTR | 2022-06-17 | 2022-06-17 | 2022-08-09 | 2022-08-09
200883C-000-JSS-1900-4000 | [D] | 200883C | 0 | JSS | 1900 | 4000 |  | 44 |  | Yuri Phase 0 - Fire and Gas Detection Specification | Code: E0301 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-07-11 | 2022-07-11 | 2022-07-16 | 2022-07-16
200883C-000-JSS-1900-4000 | [D] | 200883C | 0 | JSS | 1900 | 4000 |  | 44 |  | Yuri Phase 0 - Fire and Gas Detection Specification | Code: E0301 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | MSAF | 2022-07-15 | 2022-07-15 | 2022-07-20
200883C-000-JSS-1900-4000 | [D] | 200883C | 0 | JSS | 1900 | 4000 |  | 44 |  | Yuri Phase 0 - Fire and Gas Detection Specification | Code: E0301 | SAF | 000H2 |  |  |  |  | IFD | 100 |  |  | MSAF | 2022-08-12 | 2022-08-12 | 2022-08-12
200883C-000-JSS-1940-4000 | [D] | 200883C | 0 | JSS | 1940 | 4000 |  | 65 |  | Yuri Phase 0 - Safety Equipment Specification | Code: E0301 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-06-24 | 2022-06-24 | 2022-06-30 | 2022-06-30
200883C-000-JSS-1940-4000 | [D] | 200883C | 0 | JSS | 1940 | 4000 |  | 65 |  | Yuri Phase 0 - Safety Equipment Specification | Code: E0301 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | MSAF | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-000-JSS-1940-4000 | [D] | 200883C | 0 | JSS | 1940 | 4000 |  | 65 |  | Yuri Phase 0 - Safety Equipment Specification | Code: E0301 | SAF | 000H2 |  |  |  |  | IFD | 100 |  |  | MSAF | 2022-07-28 | 2022-07-28 | 2022-07-28
200883C-000-MR-1310-4000 | [D] | 200883C | 0 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Gate Globe Check Needle Valve | Code: E0610 | PIP | 000H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-06 | 2022-09-06 | 2022-09-06
200883C-000-MR-1310-4000 | [D] | 200883C | 0 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Gate Globe Check Needle Valve | Code: E0610 | PIP | 000H2 |  |  |  |  | IFQ | 40 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-000-MR-1310-4000 | [D] | 200883C | 0 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Gate Globe Check Needle Valve | Code: E0610 | PIP | 000H2 |  |  |  |  | IFP | 70 |  |  | MPIP | 2023-01-02 | 2023-01-02 | 2023-01-02
200883C-000-MR-1310-4000 | [D] | 200883C | 0 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Gate Globe Check Needle Valve | Code: E0610 | PIP | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MPIP | 2023-02-06 | 2023-02-06 | 2023-02-06
200883C-000-MR-1310-4000 | [D] | 200883C | 0 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Gate Globe Check Needle Valve | Code: E0610 | PIP | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MPIP | 2023-03-06 | 2023-03-06 | 2023-03-06
200883C-000-MR-1310-4000 | [D] | 200883C | 0 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Gate Globe Check Needle Valve | Code: E0610 | PIP | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MPIP | 2023-04-03 | 2023-04-03 | 2023-04-03
200883C-000-MR-1511-1000 | [D] | 200883C | 0 | MR | 1511 | 1000 |  | 120 |  | Yuri Phase 0 - Material Requisition and Specification For Integrated Control System | Code: E0301 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | AINS | 2022-07-14 | 2022-07-14 | 2022-06-09 | 2022-06-09
200883C-000-MR-1511-1000 | [D] | 200883C | 0 | MR | 1511 | 1000 |  | 120 |  | Yuri Phase 0 - Material Requisition and Specification For Integrated Control System | Code: E0301 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | AINS | 2022-08-03 | 2022-08-03 | 2022-06-09 | 2022-06-09
200883C-000-MR-1511-1000 | [D] | 200883C | 0 | MR | 1511 | 1000 |  | 120 |  | Yuri Phase 0 - Material Requisition and Specification For Integrated Control System | Code: E0301 | INS | 000H2 |  |  |  |  | IFD | 100 |  |  | AINS | 2022-08-31 | 2022-08-31 | 2022-08-31
200883C-000-MR-1531-4000 | [D] | 200883C | 0 | MR | 1531 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet for CCTV | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-11-16 | 2022-11-16 | 2022-11-16
200883C-000-MR-1531-4000 | [D] | 200883C | 0 | MR | 1531 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet for CCTV | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-11-23 | 2022-11-23 | 2022-11-23
200883C-000-MR-1531-4000 | [D] | 200883C | 0 | MR | 1531 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet for CCTV | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2023-03-13 | 2023-03-13 | 2023-03-13
200883C-000-MR-1531-4000 | [D] | 200883C | 0 | MR | 1531 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet for CCTV | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2023-04-10 | 2023-04-10 | 2023-04-10
200883C-000-MR-1531-4000 | [D] | 200883C | 0 | MR | 1531 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet for CCTV | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2023-05-08 | 2023-05-08 | 2023-05-08
200883C-000-MR-1531-4000 | [D] | 200883C | 0 | MR | 1531 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet for CCTV | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-06-05 | 2023-06-05 | 2023-06-05
200883C-000-MR-1533-4000 | [D] | 200883C | 0 | MR | 1533 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Pressure Gauges | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-05 | 2022-07-05 | 2022-07-01 | 2022-07-01
200883C-000-MR-1533-4000 | [D] | 200883C | 0 | MR | 1533 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Pressure Gauges | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-07-12 | 2022-07-12 | 2022-07-23 | 2022-07-23
200883C-000-MR-1533-4000 | [D] | 200883C | 0 | MR | 1533 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Pressure Gauges | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-11-02 | 2022-11-02 | 2022-11-02
200883C-000-MR-1533-4000 | [D] | 200883C | 0 | MR | 1533 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Pressure Gauges | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2022-11-30 | 2022-11-30 | 2022-11-30
200883C-000-MR-1533-4000 | [D] | 200883C | 0 | MR | 1533 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Pressure Gauges | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2022-12-28 | 2022-12-28 | 2022-12-28
200883C-000-MR-1533-4000 | [D] | 200883C | 0 | MR | 1533 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Pressure Gauges | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-01-25 | 2023-01-25 | 2023-01-25
200883C-000-MR-1541-4000 | [D] | 200883C | 0 | MR | 1541 | 4000 |  | 63 |  | Yuri Phase 0 - Material Requisition and Datasheet For Control Valves | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-29 | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-000-MR-1541-4000 | [D] | 200883C | 0 | MR | 1541 | 4000 |  | 63 |  | Yuri Phase 0 - Material Requisition and Datasheet For Control Valves | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-08-05 | 2022-08-05 | 2022-08-22 | 2022-08-22
200883C-000-MR-1541-4000 | [D] | 200883C | 0 | MR | 1541 | 4000 |  | 63 |  | Yuri Phase 0 - Material Requisition and Datasheet For Control Valves | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-11-10 | 2022-11-10 | 2022-11-10
200883C-000-MR-1541-4000 | [D] | 200883C | 0 | MR | 1541 | 4000 |  | 63 |  | Yuri Phase 0 - Material Requisition and Datasheet For Control Valves | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2022-12-08 | 2022-12-08 | 2022-12-08
200883C-000-MR-1541-4000 | [D] | 200883C | 0 | MR | 1541 | 4000 |  | 63 |  | Yuri Phase 0 - Material Requisition and Datasheet For Control Valves | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2023-01-05 | 2023-01-05 | 2023-01-05
200883C-000-MR-1541-4000 | [D] | 200883C | 0 | MR | 1541 | 4000 |  | 63 |  | Yuri Phase 0 - Material Requisition and Datasheet For Control Valves | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-02-02 | 2023-02-02 | 2023-02-02
200883C-000-MR-1543-4000 | [D] | 200883C | 0 | MR | 1543 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For On - Off Valves | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-05 | 2022-07-05 | 2022-07-01 | 2022-07-01
200883C-000-MR-1543-4000 | [D] | 200883C | 0 | MR | 1543 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For On - Off Valves | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-07-12 | 2022-07-12 | 2022-07-21 | 2022-07-21
200883C-000-MR-1543-4000 | [D] | 200883C | 0 | MR | 1543 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For On - Off Valves | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-11-02 | 2022-11-02 | 2022-11-02
200883C-000-MR-1543-4000 | [D] | 200883C | 0 | MR | 1543 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For On - Off Valves | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2022-11-30 | 2022-11-30 | 2022-11-30
200883C-000-MR-1543-4000 | [D] | 200883C | 0 | MR | 1543 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For On - Off Valves | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2022-12-28 | 2022-12-28 | 2022-12-28
200883C-000-MR-1543-4000 | [D] | 200883C | 0 | MR | 1543 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For On - Off Valves | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-01-25 | 2023-01-25 | 2023-01-25
200883C-000-MR-1545-4000 | [D] | 200883C | 0 | MR | 1545 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet For Safety Relief Valves | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-05 | 2022-08-05 | 2022-08-08 | 2022-08-08
200883C-000-MR-1545-4000 | [D] | 200883C | 0 | MR | 1545 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet For Safety Relief Valves | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-08-12 | 2022-08-12 | 2022-08-12
200883C-000-MR-1545-4000 | [D] | 200883C | 0 | MR | 1545 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet For Safety Relief Valves | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-12-05 | 2022-12-05 | 2022-12-05
200883C-000-MR-1545-4000 | [D] | 200883C | 0 | MR | 1545 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet For Safety Relief Valves | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2023-01-02 | 2023-01-02 | 2023-01-02
200883C-000-MR-1545-4000 | [D] | 200883C | 0 | MR | 1545 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet For Safety Relief Valves | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2023-01-30 | 2023-01-30 | 2023-01-30
200883C-000-MR-1545-4000 | [D] | 200883C | 0 | MR | 1545 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet For Safety Relief Valves | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-02-27 | 2023-02-27 | 2023-02-27
200883C-000-MR-1546-4000 | [D] | 200883C | 0 | MR | 1546 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet For Flow Element | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-22 | 2022-07-22 | 2022-07-22 | 2022-07-22
200883C-000-MR-1546-4000 | [D] | 200883C | 0 | MR | 1546 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet For Flow Element | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-07-29 | 2022-07-29 | 2022-08-01 | 2022-08-01
200883C-000-MR-1546-4000 | [D] | 200883C | 0 | MR | 1546 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet For Flow Element | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-11-21 | 2022-11-21 | 2022-11-21
200883C-000-MR-1546-4000 | [D] | 200883C | 0 | MR | 1546 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet For Flow Element | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2022-12-19 | 2022-12-19 | 2022-12-19
200883C-000-MR-1546-4000 | [D] | 200883C | 0 | MR | 1546 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet For Flow Element | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2023-01-16 | 2023-01-16 | 2023-01-16
200883C-000-MR-1546-4000 | [D] | 200883C | 0 | MR | 1546 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet For Flow Element | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-02-13 | 2023-02-13 | 2023-02-13
200883C-000-MR-1547-4000 | [D] | 200883C | 0 | MR | 1547 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Magnetic Flow Meter | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-22 | 2022-07-22 | 2022-07-22 | 2022-07-22
200883C-000-MR-1547-4000 | [D] | 200883C | 0 | MR | 1547 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Magnetic Flow Meter | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-000-MR-1547-4000 | [D] | 200883C | 0 | MR | 1547 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Magnetic Flow Meter | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-11-21 | 2022-11-21 | 2022-11-21
200883C-000-MR-1547-4000 | [D] | 200883C | 0 | MR | 1547 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Magnetic Flow Meter | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2022-12-19 | 2022-12-19 | 2022-12-19
200883C-000-MR-1547-4000 | [D] | 200883C | 0 | MR | 1547 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Magnetic Flow Meter | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2023-01-16 | 2023-01-16 | 2023-01-16
200883C-000-MR-1547-4000 | [D] | 200883C | 0 | MR | 1547 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Magnetic Flow Meter | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-02-13 | 2023-02-13 | 2023-02-13
200883C-000-MR-1552-4000 | [D] | 200883C | 0 | MR | 1552 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Magnetic Level Gauge | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-05 | 2022-07-05 | 2022-06-27 | 2022-06-27
200883C-000-MR-1552-4000 | [D] | 200883C | 0 | MR | 1552 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Magnetic Level Gauge | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-07-12 | 2022-07-12 | 2022-06-27 | 2022-06-27
200883C-000-MR-1552-4000 | [D] | 200883C | 0 | MR | 1552 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Magnetic Level Gauge | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-11-02 | 2022-11-02 | 2022-11-02
200883C-000-MR-1552-4000 | [D] | 200883C | 0 | MR | 1552 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Magnetic Level Gauge | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2022-11-30 | 2022-11-30 | 2022-11-30
200883C-000-MR-1552-4000 | [D] | 200883C | 0 | MR | 1552 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Magnetic Level Gauge | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2022-12-28 | 2022-12-28 | 2022-12-28
200883C-000-MR-1552-4000 | [D] | 200883C | 0 | MR | 1552 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Magnetic Level Gauge | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-01-25 | 2023-01-25 | 2023-01-25
200883C-000-MR-1552-4001 | [D] | 200883C | 0 | MR | 1552 | 4001 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Radar Level transmitter | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-06-20 | 2022-06-20 | 2022-06-20 | 2022-06-20
200883C-000-MR-1552-4001 | [D] | 200883C | 0 | MR | 1552 | 4001 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Radar Level transmitter | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-06-27 | 2022-06-27 | 2022-06-27
200883C-000-MR-1552-4001 | [D] | 200883C | 0 | MR | 1552 | 4001 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Radar Level transmitter | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-10-17 | 2022-10-17 | 2022-10-17
200883C-000-MR-1552-4001 | [D] | 200883C | 0 | MR | 1552 | 4001 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Radar Level transmitter | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2022-11-14 | 2022-11-14 | 2022-11-14
200883C-000-MR-1552-4001 | [D] | 200883C | 0 | MR | 1552 | 4001 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Radar Level transmitter | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2022-12-12 | 2022-12-12 | 2022-12-12
200883C-000-MR-1552-4001 | [D] | 200883C | 0 | MR | 1552 | 4001 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Radar Level transmitter | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-01-09 | 2023-01-09 | 2023-01-09
200883C-000-MR-1553-4000 | [D] | 200883C | 0 | MR | 1553 | 4000 |  | 95 |  | Yuri Phase 0 - Material Requisition and Datasheet For Electronic Transmitters (Pressure , Flow, level , temperature) | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-05 | 2022-07-05 | 2022-07-01 | 2022-07-01
200883C-000-MR-1553-4000 | [D] | 200883C | 0 | MR | 1553 | 4000 |  | 95 |  | Yuri Phase 0 - Material Requisition and Datasheet For Electronic Transmitters (Pressure , Flow, level , temperature) | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-07-12 | 2022-07-12 | 2022-07-22 | 2022-07-22
200883C-000-MR-1553-4000 | [D] | 200883C | 0 | MR | 1553 | 4000 |  | 95 |  | Yuri Phase 0 - Material Requisition and Datasheet For Electronic Transmitters (Pressure , Flow, level , temperature) | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-11-02 | 2022-11-02 | 2022-11-02
200883C-000-MR-1553-4000 | [D] | 200883C | 0 | MR | 1553 | 4000 |  | 95 |  | Yuri Phase 0 - Material Requisition and Datasheet For Electronic Transmitters (Pressure , Flow, level , temperature) | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2022-11-30 | 2022-11-30 | 2022-11-30
200883C-000-MR-1553-4000 | [D] | 200883C | 0 | MR | 1553 | 4000 |  | 95 |  | Yuri Phase 0 - Material Requisition and Datasheet For Electronic Transmitters (Pressure , Flow, level , temperature) | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2022-12-28 | 2022-12-28 | 2022-12-28
200883C-000-MR-1553-4000 | [D] | 200883C | 0 | MR | 1553 | 4000 |  | 95 |  | Yuri Phase 0 - Material Requisition and Datasheet For Electronic Transmitters (Pressure , Flow, level , temperature) | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-01-25 | 2023-01-25 | 2023-01-25
200883C-000-MR-1554-4000 | [D] | 200883C | 0 | MR | 1554 | 4000 |  | 63 |  | Yuri Phase 0 - Material Requisition and Datasheet For Temperature Elements and Gauges | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-06 | 2022-07-06 | 2022-07-01 | 2022-07-01
200883C-000-MR-1554-4000 | [D] | 200883C | 0 | MR | 1554 | 4000 |  | 63 |  | Yuri Phase 0 - Material Requisition and Datasheet For Temperature Elements and Gauges | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-07-13 | 2022-07-13 | 2022-08-01 | 2022-08-01
200883C-000-MR-1554-4000 | [D] | 200883C | 0 | MR | 1554 | 4000 |  | 63 |  | Yuri Phase 0 - Material Requisition and Datasheet For Temperature Elements and Gauges | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-11-02 | 2022-11-02 | 2022-11-02
200883C-000-MR-1554-4000 | [D] | 200883C | 0 | MR | 1554 | 4000 |  | 63 |  | Yuri Phase 0 - Material Requisition and Datasheet For Temperature Elements and Gauges | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2022-11-30 | 2022-11-30 | 2022-11-30
200883C-000-MR-1554-4000 | [D] | 200883C | 0 | MR | 1554 | 4000 |  | 63 |  | Yuri Phase 0 - Material Requisition and Datasheet For Temperature Elements and Gauges | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2022-12-28 | 2022-12-28 | 2022-12-28
200883C-000-MR-1554-4000 | [D] | 200883C | 0 | MR | 1554 | 4000 |  | 63 |  | Yuri Phase 0 - Material Requisition and Datasheet For Temperature Elements and Gauges | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-01-25 | 2023-01-25 | 2023-01-25
200883C-000-MR-1566-4000 | [D] | 200883C | 0 | MR | 1566 | 4000 |  | 70 |  | Yuri Phase 0 - Material Requisition and Datasheet For FandG Detectors | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-15 | 2022-08-15 | 2022-08-15 | 2022-08-15
200883C-000-MR-1566-4000 | [D] | 200883C | 0 | MR | 1566 | 4000 |  | 70 |  | Yuri Phase 0 - Material Requisition and Datasheet For FandG Detectors | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-08-22 | 2022-08-22 | 2022-08-22
200883C-000-MR-1566-4000 | [D] | 200883C | 0 | MR | 1566 | 4000 |  | 70 |  | Yuri Phase 0 - Material Requisition and Datasheet For FandG Detectors | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-12-12 | 2022-12-12 | 2022-12-12
200883C-000-MR-1566-4000 | [D] | 200883C | 0 | MR | 1566 | 4000 |  | 70 |  | Yuri Phase 0 - Material Requisition and Datasheet For FandG Detectors | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2023-01-09 | 2023-01-09 | 2023-01-09
200883C-000-MR-1566-4000 | [D] | 200883C | 0 | MR | 1566 | 4000 |  | 70 |  | Yuri Phase 0 - Material Requisition and Datasheet For FandG Detectors | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2023-02-06 | 2023-02-06 | 2023-02-06
200883C-000-MR-1566-4000 | [D] | 200883C | 0 | MR | 1566 | 4000 |  | 70 |  | Yuri Phase 0 - Material Requisition and Datasheet For FandG Detectors | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-03-06 | 2023-03-06 | 2023-03-06
200883C-000-MR-1572-4000 | [D] | 200883C | 0 | MR | 1572 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Cable Tray And Accessories | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-12-21 | 2022-12-21 | 2022-07-18 | 2022-07-18
200883C-000-MR-1572-4000 | [D] | 200883C | 0 | MR | 1572 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Cable Tray And Accessories | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-12-28 | 2022-12-28 | 2022-07-18 | 2022-07-18
200883C-000-MR-1572-4000 | [D] | 200883C | 0 | MR | 1572 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Cable Tray And Accessories | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2023-04-19 | 2023-04-19 | 2022-07-18 | 2022-07-18
200883C-000-MR-1572-4000 | [D] | 200883C | 0 | MR | 1572 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Cable Tray And Accessories | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2023-05-17 | 2023-05-17 | 2022-07-18 | 2022-07-18
200883C-000-MR-1572-4000 | [D] | 200883C | 0 | MR | 1572 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Cable Tray And Accessories | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2023-06-14 | 2023-06-14 | 2022-07-18 | 2022-07-18
200883C-000-MR-1572-4000 | [D] | 200883C | 0 | MR | 1572 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Cable Tray And Accessories | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-07-12 | 2023-07-12 | 2022-07-18 | 2022-07-18
200883C-000-MR-1572-4001 | [D] | 200883C | 0 | MR | 1572 | 4001 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Tube and Fittings | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-11-30 | 2022-11-30 | 2022-11-30
200883C-000-MR-1572-4001 | [D] | 200883C | 0 | MR | 1572 | 4001 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Tube and Fittings | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-000-MR-1572-4001 | [D] | 200883C | 0 | MR | 1572 | 4001 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Tube and Fittings | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2023-03-16 | 2023-03-16 | 2023-03-16
200883C-000-MR-1572-4001 | [D] | 200883C | 0 | MR | 1572 | 4001 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Tube and Fittings | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2023-04-13 | 2023-04-13 | 2023-04-13
200883C-000-MR-1572-4001 | [D] | 200883C | 0 | MR | 1572 | 4001 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Tube and Fittings | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2023-05-11 | 2023-05-11 | 2023-05-11
200883C-000-MR-1572-4001 | [D] | 200883C | 0 | MR | 1572 | 4001 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Tube and Fittings | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-06-08 | 2023-06-08 | 2023-06-08
200883C-000-MR-1574-4000 | [D] | 200883C | 0 | MR | 1574 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Instrument Cables | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-000-MR-1574-4000 | [D] | 200883C | 0 | MR | 1574 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Instrument Cables | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-09-20 | 2022-09-20 | 2022-09-20
200883C-000-MR-1574-4000 | [D] | 200883C | 0 | MR | 1574 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Instrument Cables | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2023-01-09 | 2023-01-09 | 2023-01-09
200883C-000-MR-1574-4000 | [D] | 200883C | 0 | MR | 1574 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Instrument Cables | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2023-02-06 | 2023-02-06 | 2023-02-06
200883C-000-MR-1574-4000 | [D] | 200883C | 0 | MR | 1574 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Instrument Cables | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2023-03-06 | 2023-03-06 | 2023-03-06
200883C-000-MR-1574-4000 | [D] | 200883C | 0 | MR | 1574 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Instrument Cables | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-04-03 | 2023-04-03 | 2023-04-03
200883C-000-MR-1575-4000 | [D] | 200883C | 0 | MR | 1575 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Junction Boxes and cable glands | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-11-30 | 2022-11-30 | 2022-11-30
200883C-000-MR-1575-4000 | [D] | 200883C | 0 | MR | 1575 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Junction Boxes and cable glands | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-000-MR-1575-4000 | [D] | 200883C | 0 | MR | 1575 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Junction Boxes and cable glands | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2023-03-27 | 2023-03-27 | 2023-03-27
200883C-000-MR-1575-4000 | [D] | 200883C | 0 | MR | 1575 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Junction Boxes and cable glands | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2023-04-24 | 2023-04-24 | 2023-04-24
200883C-000-MR-1575-4000 | [D] | 200883C | 0 | MR | 1575 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Junction Boxes and cable glands | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2023-05-22 | 2023-05-22 | 2023-05-22
200883C-000-MR-1575-4000 | [D] | 200883C | 0 | MR | 1575 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Junction Boxes and cable glands | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-06-19 | 2023-06-19 | 2023-06-19
200883C-000-MR-1584-4000 | [D] | 200883C | 0 | MR | 1584 | 4000 |  | 133 |  | Yuri Phase 0 - Material Requisition and Datasheet For Hydrogen Quality and Metering System | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-06-10 | 2022-06-10 | 2022-06-17 | 2022-06-17
200883C-000-MR-1584-4000 | [D] | 200883C | 0 | MR | 1584 | 4000 |  | 133 |  | Yuri Phase 0 - Material Requisition and Datasheet For Hydrogen Quality and Metering System | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-06-17 | 2022-06-17 | 2022-06-22 | 2022-06-22
200883C-000-MR-1584-4000 | [D] | 200883C | 0 | MR | 1584 | 4000 |  | 133 |  | Yuri Phase 0 - Material Requisition and Datasheet For Hydrogen Quality and Metering System | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-000-MR-1584-4000 | [D] | 200883C | 0 | MR | 1584 | 4000 |  | 133 |  | Yuri Phase 0 - Material Requisition and Datasheet For Hydrogen Quality and Metering System | Code: E0610 | INS | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2022-10-11 | 2022-10-11 | 2022-10-11
200883C-000-MR-1584-4000 | [D] | 200883C | 0 | MR | 1584 | 4000 |  | 133 |  | Yuri Phase 0 - Material Requisition and Datasheet For Hydrogen Quality and Metering System | Code: E0610 | INS | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2022-11-08 | 2022-11-08 | 2022-11-08
200883C-000-MR-1584-4000 | [D] | 200883C | 0 | MR | 1584 | 4000 |  | 133 |  | Yuri Phase 0 - Material Requisition and Datasheet For Hydrogen Quality and Metering System | Code: E0610 | INS | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2022-12-06 | 2022-12-06 | 2022-12-06
200883C-000-MR-1610-4000 | [D] | 200883C | 0 | MR | 1610 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Earthing | Code: E0610 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-08-22 | 2022-08-22 | 2022-08-22 | 2022-08-22
200883C-000-MR-1610-4000 | [D] | 200883C | 0 | MR | 1610 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Earthing | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-000-MR-1610-4000 | [D] | 200883C | 0 | MR | 1610 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Earthing | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-12-19 | 2022-12-19 | 2022-12-19
200883C-000-MR-1610-4000 | [D] | 200883C | 0 | MR | 1610 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Earthing | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MELE | 2023-01-16 | 2023-01-16 | 2023-01-16
200883C-000-MR-1610-4000 | [D] | 200883C | 0 | MR | 1610 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Earthing | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MELE | 2023-02-13 | 2023-02-13 | 2023-02-13
200883C-000-MR-1610-4000 | [D] | 200883C | 0 | MR | 1610 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Earthing | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MELE | 2023-03-13 | 2023-03-13 | 2023-03-13
200883C-000-MR-1620-4000 | [D] | 200883C | 0 | MR | 1620 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Power | Code: E0610 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-08-22 | 2022-08-22 | 2022-08-22 | 2022-08-22
200883C-000-MR-1620-4000 | [D] | 200883C | 0 | MR | 1620 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Power | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-000-MR-1620-4000 | [D] | 200883C | 0 | MR | 1620 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Power | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-12-19 | 2022-12-19 | 2022-12-19
200883C-000-MR-1620-4000 | [D] | 200883C | 0 | MR | 1620 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Power | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MELE | 2023-01-16 | 2023-01-16 | 2023-01-16
200883C-000-MR-1620-4000 | [D] | 200883C | 0 | MR | 1620 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Power | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MELE | 2023-02-13 | 2023-02-13 | 2023-02-13
200883C-000-MR-1620-4000 | [D] | 200883C | 0 | MR | 1620 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Power | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MELE | 2023-03-13 | 2023-03-13 | 2023-03-13
200883C-000-MR-1621-4000 | [D] | 200883C | 0 | MR | 1621 | 4000 |  | 41 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Green field | Code: E0610 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-000-MR-1621-4000 | [D] | 200883C | 0 | MR | 1621 | 4000 |  | 41 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Green field | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-10-04 | 2022-10-04 | 2022-10-04
200883C-000-MR-1621-4000 | [D] | 200883C | 0 | MR | 1621 | 4000 |  | 41 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Green field | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2023-01-23 | 2023-01-23 | 2023-01-23
200883C-000-MR-1621-4000 | [D] | 200883C | 0 | MR | 1621 | 4000 |  | 41 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Green field | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MELE | 2023-02-20 | 2023-02-20 | 2023-02-20
200883C-000-MR-1621-4000 | [D] | 200883C | 0 | MR | 1621 | 4000 |  | 41 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Green field | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MELE | 2023-03-20 | 2023-03-20 | 2023-03-20
200883C-000-MR-1621-4000 | [D] | 200883C | 0 | MR | 1621 | 4000 |  | 41 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Green field | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MELE | 2023-04-17 | 2023-04-17 | 2023-04-17
200883C-000-MR-1623-4000 | [D] | 200883C | 0 | MR | 1623 | 4000 |  | 41 |  | Yuri Phase 0 - Cable Trays And Ladders - Green field | Code: E0610 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-000-MR-1623-4000 | [D] | 200883C | 0 | MR | 1623 | 4000 |  | 41 |  | Yuri Phase 0 - Cable Trays And Ladders - Green field | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-000-MR-1623-4000 | [D] | 200883C | 0 | MR | 1623 | 4000 |  | 41 |  | Yuri Phase 0 - Cable Trays And Ladders - Green field | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2023-03-16 | 2023-03-16 | 2023-03-16
200883C-000-MR-1623-4000 | [D] | 200883C | 0 | MR | 1623 | 4000 |  | 41 |  | Yuri Phase 0 - Cable Trays And Ladders - Green field | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MELE | 2023-04-13 | 2023-04-13 | 2023-04-13
200883C-000-MR-1623-4000 | [D] | 200883C | 0 | MR | 1623 | 4000 |  | 41 |  | Yuri Phase 0 - Cable Trays And Ladders - Green field | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MELE | 2023-05-11 | 2023-05-11 | 2023-05-11
200883C-000-MR-1623-4000 | [D] | 200883C | 0 | MR | 1623 | 4000 |  | 41 |  | Yuri Phase 0 - Cable Trays And Ladders - Green field | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MELE | 2023-06-08 | 2023-06-08 | 2023-06-08
200883C-000-MR-1630-4000 | [D] | 200883C | 0 | MR | 1630 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Lighting | Code: E0610 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-08-22 | 2022-08-22 | 2022-08-22 | 2022-08-22
200883C-000-MR-1630-4000 | [D] | 200883C | 0 | MR | 1630 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Lighting | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-000-MR-1630-4000 | [D] | 200883C | 0 | MR | 1630 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Lighting | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-12-19 | 2022-12-19 | 2022-12-19
200883C-000-MR-1630-4000 | [D] | 200883C | 0 | MR | 1630 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Lighting | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MELE | 2023-01-16 | 2023-01-16 | 2023-01-16
200883C-000-MR-1630-4000 | [D] | 200883C | 0 | MR | 1630 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Lighting | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MELE | 2023-02-13 | 2023-02-13 | 2023-02-13
200883C-000-MR-1630-4000 | [D] | 200883C | 0 | MR | 1630 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Lighting | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MELE | 2023-03-13 | 2023-03-13 | 2023-03-13
200883C-000-MR-1641-4000 | [D] | 200883C | 0 | MR | 1641 | 4000 |  | 81 |  | Yuri Phase 0 - Transformers | Code: E0610 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-20 | 2022-06-20 | 2022-06-20 | 2022-06-20
200883C-000-MR-1641-4000 | [D] | 200883C | 0 | MR | 1641 | 4000 |  | 81 |  | Yuri Phase 0 - Transformers | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-06-27 | 2022-06-27 | 2022-07-20 | 2022-07-20
200883C-000-MR-1641-4000 | [D] | 200883C | 0 | MR | 1641 | 4000 |  | 81 |  | Yuri Phase 0 - Transformers | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-09-16 | 2022-09-16 | 2022-09-16
200883C-000-MR-1641-4000 | [D] | 200883C | 0 | MR | 1641 | 4000 |  | 81 |  | Yuri Phase 0 - Transformers | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MELE | 2022-10-14 | 2022-10-14 | 2022-10-14
200883C-000-MR-1641-4000 | [D] | 200883C | 0 | MR | 1641 | 4000 |  | 81 |  | Yuri Phase 0 - Transformers | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MELE | 2022-11-11 | 2022-11-11 | 2022-11-11
200883C-000-MR-1641-4000 | [D] | 200883C | 0 | MR | 1641 | 4000 |  | 81 |  | Yuri Phase 0 - Transformers | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MELE | 2022-12-09 | 2022-12-09 | 2022-12-09
200883C-000-MR-1641-4001 | [D] | 200883C | 0 | MR | 1641 | 4001 |  | 81 |  | Yuri Phase 0 - Neutral Earthing Resistor | Code: E0610 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-24 | 2022-06-24 | 2022-06-24 | 2022-06-24
200883C-000-MR-1641-4001 | [D] | 200883C | 0 | MR | 1641 | 4001 |  | 81 |  | Yuri Phase 0 - Neutral Earthing Resistor | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-07-01 | 2022-07-01 | 2022-08-02 | 2022-08-02
200883C-000-MR-1641-4001 | [D] | 200883C | 0 | MR | 1641 | 4001 |  | 81 |  | Yuri Phase 0 - Neutral Earthing Resistor | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-10-07 | 2022-10-07 | 2022-08-02 | 2022-08-02
200883C-000-MR-1641-4001 | [D] | 200883C | 0 | MR | 1641 | 4001 |  | 81 |  | Yuri Phase 0 - Neutral Earthing Resistor | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MELE | 2022-11-04 | 2022-11-04 | 2022-08-02 | 2022-08-02
200883C-000-MR-1641-4001 | [D] | 200883C | 0 | MR | 1641 | 4001 |  | 81 |  | Yuri Phase 0 - Neutral Earthing Resistor | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MELE | 2022-12-02 | 2022-12-02 | 2022-08-02 | 2022-08-02
200883C-000-MR-1641-4001 | [D] | 200883C | 0 | MR | 1641 | 4001 |  | 81 |  | Yuri Phase 0 - Neutral Earthing Resistor | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MELE | 2022-12-30 | 2022-12-30 | 2022-08-02 | 2022-08-02
200883C-000-MR-1652-4000 | [D] | 200883C | 0 | MR | 1652 | 4000 |  | 81 |  | Yuri Phase 0 - HV Switchgear | Code: E0610 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-14 | 2022-06-14 | 2022-06-16 | 2022-06-16
200883C-000-MR-1652-4000 | [D] | 200883C | 0 | MR | 1652 | 4000 |  | 81 |  | Yuri Phase 0 - HV Switchgear | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-06-21 | 2022-06-21 | 2022-06-16 | 2022-06-16
200883C-000-MR-1652-4000 | [D] | 200883C | 0 | MR | 1652 | 4000 |  | 81 |  | Yuri Phase 0 - HV Switchgear | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-000-MR-1652-4000 | [D] | 200883C | 0 | MR | 1652 | 4000 |  | 81 |  | Yuri Phase 0 - HV Switchgear | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MELE | 2022-09-20 | 2022-09-20 | 2022-09-20
200883C-000-MR-1652-4000 | [D] | 200883C | 0 | MR | 1652 | 4000 |  | 81 |  | Yuri Phase 0 - HV Switchgear | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MELE | 2022-10-18 | 2022-10-18 | 2022-10-18
200883C-000-MR-1652-4000 | [D] | 200883C | 0 | MR | 1652 | 4000 |  | 81 |  | Yuri Phase 0 - HV Switchgear | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MELE | 2022-11-15 | 2022-11-15 | 2022-11-15
200883C-000-MR-1652-4001 | [D] | 200883C | 0 | MR | 1652 | 4001 |  | 41 |  | Yuri Phase 0 - Switchgear (MV & LV) Modification | Code: E0610 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-13 | 2022-07-13 | 2022-07-16 | 2022-07-16
200883C-000-MR-1652-4001 | [D] | 200883C | 0 | MR | 1652 | 4001 |  | 41 |  | Yuri Phase 0 - Switchgear (MV & LV) Modification | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-07-20 | 2022-07-20 | 2022-08-18 | 2022-08-18
200883C-000-MR-1652-4001 | [D] | 200883C | 0 | MR | 1652 | 4001 |  | 41 |  | Yuri Phase 0 - Switchgear (MV & LV) Modification | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-08-23 | 2022-08-23 | 2022-08-18 | 2022-08-18
200883C-000-MR-1652-4001 | [D] | 200883C | 0 | MR | 1652 | 4001 |  | 41 |  | Yuri Phase 0 - Switchgear (MV & LV) Modification | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MELE | 2022-09-20 | 2022-09-20 | 2022-08-18 | 2022-08-18
200883C-000-MR-1652-4001 | [D] | 200883C | 0 | MR | 1652 | 4001 |  | 41 |  | Yuri Phase 0 - Switchgear (MV & LV) Modification | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MELE | 2022-10-18 | 2022-10-18 | 2022-08-18 | 2022-08-18
200883C-000-MR-1652-4001 | [D] | 200883C | 0 | MR | 1652 | 4001 |  | 41 |  | Yuri Phase 0 - Switchgear (MV & LV) Modification | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MELE | 2022-11-15 | 2022-11-15 | 2022-08-18 | 2022-08-18
200883C-000-MR-1654-4000 | [D] | 200883C | 0 | MR | 1654 | 4000 |  | 81 |  | Yuri Phase 0 - Material Requisition for LV Switchgear | Code: E0610 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-20 | 2022-06-20 | 2022-06-20 | 2022-06-20
200883C-000-MR-1654-4000 | [D] | 200883C | 0 | MR | 1654 | 4000 |  | 81 |  | Yuri Phase 0 - Material Requisition for LV Switchgear | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-06-27 | 2022-06-27 | 2022-07-06 | 2022-07-06
200883C-000-MR-1654-4000 | [D] | 200883C | 0 | MR | 1654 | 4000 |  | 81 |  | Yuri Phase 0 - Material Requisition for LV Switchgear | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-000-MR-1654-4000 | [D] | 200883C | 0 | MR | 1654 | 4000 |  | 81 |  | Yuri Phase 0 - Material Requisition for LV Switchgear | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MELE | 2022-09-20 | 2022-09-20 | 2022-09-20
200883C-000-MR-1654-4000 | [D] | 200883C | 0 | MR | 1654 | 4000 |  | 81 |  | Yuri Phase 0 - Material Requisition for LV Switchgear | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MELE | 2022-10-18 | 2022-10-18 | 2022-10-18
200883C-000-MR-1654-4000 | [D] | 200883C | 0 | MR | 1654 | 4000 |  | 81 |  | Yuri Phase 0 - Material Requisition for LV Switchgear | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MELE | 2022-11-15 | 2022-11-15 | 2022-11-15
200883C-000-MR-1657-4000 | [D] | 200883C | 0 | MR | 1657 | 4000 |  | 81 |  | Yuri Phase 0 - Power Distribution Boards | Code: E0610 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-29 | 2022-06-29 | 2022-06-29 | 2022-06-29
200883C-000-MR-1657-4000 | [D] | 200883C | 0 | MR | 1657 | 4000 |  | 81 |  | Yuri Phase 0 - Power Distribution Boards | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-07-06 | 2022-07-06 | 2022-07-15 | 2022-07-15
200883C-000-MR-1657-4000 | [D] | 200883C | 0 | MR | 1657 | 4000 |  | 81 |  | Yuri Phase 0 - Power Distribution Boards | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-10-07 | 2022-10-07 | 2022-07-15 | 2022-07-15
200883C-000-MR-1657-4000 | [D] | 200883C | 0 | MR | 1657 | 4000 |  | 81 |  | Yuri Phase 0 - Power Distribution Boards | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MELE | 2022-11-04 | 2022-11-04 | 2022-07-15 | 2022-07-15
200883C-000-MR-1657-4000 | [D] | 200883C | 0 | MR | 1657 | 4000 |  | 81 |  | Yuri Phase 0 - Power Distribution Boards | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MELE | 2022-12-02 | 2022-12-02 | 2022-07-15 | 2022-07-15
200883C-000-MR-1657-4000 | [D] | 200883C | 0 | MR | 1657 | 4000 |  | 81 |  | Yuri Phase 0 - Power Distribution Boards | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MELE | 2022-12-30 | 2022-12-30 | 2022-07-15 | 2022-07-15
200883C-000-MR-1671-4000 | [D] | 200883C | 0 | MR | 1671 | 4000 |  | 81 |  | Yuri Phase 0 - AC UPS System | Code: E0610 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-29 | 2022-06-29 | 2022-06-29 | 2022-06-29
200883C-000-MR-1671-4000 | [D] | 200883C | 0 | MR | 1671 | 4000 |  | 81 |  | Yuri Phase 0 - AC UPS System | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-07-06 | 2022-07-06 | 2022-07-14 | 2022-07-14
200883C-000-MR-1671-4000 | [D] | 200883C | 0 | MR | 1671 | 4000 |  | 81 |  | Yuri Phase 0 - AC UPS System | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-10-07 | 2022-10-07 | 2022-10-07
200883C-000-MR-1671-4000 | [D] | 200883C | 0 | MR | 1671 | 4000 |  | 81 |  | Yuri Phase 0 - AC UPS System | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MELE | 2022-11-04 | 2022-11-04 | 2022-11-04
200883C-000-MR-1671-4000 | [D] | 200883C | 0 | MR | 1671 | 4000 |  | 81 |  | Yuri Phase 0 - AC UPS System | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MELE | 2022-12-02 | 2022-12-02 | 2022-12-02
200883C-000-MR-1671-4000 | [D] | 200883C | 0 | MR | 1671 | 4000 |  | 81 |  | Yuri Phase 0 - AC UPS System | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MELE | 2022-12-30 | 2022-12-30 | 2022-12-30
200883C-000-MR-1672-4000 | [D] | 200883C | 0 | MR | 1672 | 4000 |  | 81 |  | Yuri Phase 0 - DC UPS System | Code: E0610 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-29 | 2022-06-29 | 2022-06-29 | 2022-06-29
200883C-000-MR-1672-4000 | [D] | 200883C | 0 | MR | 1672 | 4000 |  | 81 |  | Yuri Phase 0 - DC UPS System | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-07-06 | 2022-07-06 | 2022-07-14 | 2022-07-14
200883C-000-MR-1672-4000 | [D] | 200883C | 0 | MR | 1672 | 4000 |  | 81 |  | Yuri Phase 0 - DC UPS System | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-10-07 | 2022-10-07 | 2022-10-07
200883C-000-MR-1672-4000 | [D] | 200883C | 0 | MR | 1672 | 4000 |  | 81 |  | Yuri Phase 0 - DC UPS System | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MELE | 2022-11-04 | 2022-11-04 | 2022-11-04
200883C-000-MR-1672-4000 | [D] | 200883C | 0 | MR | 1672 | 4000 |  | 81 |  | Yuri Phase 0 - DC UPS System | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MELE | 2022-12-02 | 2022-12-02 | 2022-12-02
200883C-000-MR-1672-4000 | [D] | 200883C | 0 | MR | 1672 | 4000 |  | 81 |  | Yuri Phase 0 - DC UPS System | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MELE | 2022-12-30 | 2022-12-30 | 2022-12-30
200883C-000-MTO-1577-4000 | [D] | 200883C | 0 | MTO | 1577 | 4000 |  | 63 |  | Yuri Phase 0 - MTO For Instrument Cable Ladder and Accessories and Instrument Bulk Materials | Code: E0306 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-000-MTO-1577-4000 | [D] | 200883C | 0 | MTO | 1577 | 4000 |  | 63 |  | Yuri Phase 0 - MTO For Instrument Cable Ladder and Accessories and Instrument Bulk Materials | Code: E0306 | INS | 000H2 |  |  |  |  | IFP1 | 70 |  |  | MINS | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-000-MTO-1577-4000 | [D] | 200883C | 0 | MTO | 1577 | 4000 |  | 63 |  | Yuri Phase 0 - MTO For Instrument Cable Ladder and Accessories and Instrument Bulk Materials | Code: E0306 | INS | 000H2 |  |  |  |  | IFP2 | 100 |  |  | MINS | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-000-MTO-1619-4000 | [D] | 200883C | 0 | MTO | 1619 | 4000 |  | 41 |  | Yuri Phase 0 - Earthing Material Take-Off | Code: E0306 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-000-MTO-1619-4000 | [D] | 200883C | 0 | MTO | 1619 | 4000 |  | 41 |  | Yuri Phase 0 - Earthing Material Take-Off | Code: E0306 | ELE | 000H2 |  |  |  |  | IFP1 | 70 |  |  | MELE | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-000-MTO-1619-4000 | [D] | 200883C | 0 | MTO | 1619 | 4000 |  | 41 |  | Yuri Phase 0 - Earthing Material Take-Off | Code: E0306 | ELE | 000H2 |  |  |  |  | IFP2 | 100 |  |  | MELE | 2022-10-04 | 2022-10-04 | 2022-10-04
200883C-000-MTO-1619-4001 | [D] | 200883C | 0 | MTO | 1619 | 4001 |  | 41 |  | Yuri Phase 0 - HV and LV Power And Control Cables Material Take-Off | Code: E0306 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-000-MTO-1619-4001 | [D] | 200883C | 0 | MTO | 1619 | 4001 |  | 41 |  | Yuri Phase 0 - HV and LV Power And Control Cables Material Take-Off | Code: E0306 | ELE | 000H2 |  |  |  |  | IFP1 | 70 |  |  | MELE | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-000-MTO-1619-4001 | [D] | 200883C | 0 | MTO | 1619 | 4001 |  | 41 |  | Yuri Phase 0 - HV and LV Power And Control Cables Material Take-Off | Code: E0306 | ELE | 000H2 |  |  |  |  | IFP2 | 100 |  |  | MELE | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-000-MTO-1619-4002 | [D] | 200883C | 0 | MTO | 1619 | 4002 |  | 41 |  | Yuri Phase 0 - Electrical Cable Ladder and Access Material Take-Off | Code: E0306 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-12-08 | 2022-12-08 | 2022-12-08
200883C-000-MTO-1619-4002 | [D] | 200883C | 0 | MTO | 1619 | 4002 |  | 41 |  | Yuri Phase 0 - Electrical Cable Ladder and Access Material Take-Off | Code: E0306 | ELE | 000H2 |  |  |  |  | IFP1 | 70 |  |  | MELE | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-000-MTO-1619-4002 | [D] | 200883C | 0 | MTO | 1619 | 4002 |  | 41 |  | Yuri Phase 0 - Electrical Cable Ladder and Access Material Take-Off | Code: E0306 | ELE | 000H2 |  |  |  |  | IFP2 | 100 |  |  | MELE | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-000-MTO-1619-4003 | [D] | 200883C | 0 | MTO | 1619 | 4003 |  | 41 |  | Yuri Phase 0 - Earthing Material Take-Off - Power | Code: E0306 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-12-08 | 2022-12-08 | 2022-12-08
200883C-000-MTO-1619-4003 | [D] | 200883C | 0 | MTO | 1619 | 4003 |  | 41 |  | Yuri Phase 0 - Earthing Material Take-Off - Power | Code: E0306 | ELE | 000H2 |  |  |  |  | IFP1 | 70 |  |  | MELE | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-000-MTO-1619-4003 | [D] | 200883C | 0 | MTO | 1619 | 4003 |  | 41 |  | Yuri Phase 0 - Earthing Material Take-Off - Power | Code: E0306 | ELE | 000H2 |  |  |  |  | IFP2 | 100 |  |  | MELE | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-000-MTO-1619-4004 | [D] | 200883C | 0 | MTO | 1619 | 4004 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Material Take-Off - Lighting | Code: E0306 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-12-08 | 2022-12-08 | 2022-12-08
200883C-000-MTO-1619-4004 | [D] | 200883C | 0 | MTO | 1619 | 4004 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Material Take-Off - Lighting | Code: E0306 | ELE | 000H2 |  |  |  |  | IFP1 | 70 |  |  | MELE | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-000-MTO-1619-4004 | [D] | 200883C | 0 | MTO | 1619 | 4004 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Material Take-Off - Lighting | Code: E0306 | ELE | 000H2 |  |  |  |  | IFP2 | 100 |  |  | MELE | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-000-NM-1500-5000 | [D] | 200883C | 0 | NM | 1500 | 5000 |  | 40 |  | Yuri Phase 0 - Inverter Station Das Panel I - O Signals List (Battery and PV) | Code: E0303 | INS | 000PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-04-26 | 2022-04-26 | 2022-04-26 | 2022-04-26
200883C-000-NM-1500-5000 | [D] | 200883C | 0 | NM | 1500 | 5000 |  | 40 |  | Yuri Phase 0 - Inverter Station Das Panel I - O Signals List (Battery and PV) | Code: E0303 | INS | 000PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-05-26 | 2022-05-26 | 2022-08-29
200883C-000-NM-1500-5000 | [D] | 200883C | 0 | NM | 1500 | 5000 |  | 40 |  | Yuri Phase 0 - Inverter Station Das Panel I - O Signals List (Battery and PV) | Code: E0303 | INS | 000PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-06-25 | 2022-06-25 | 2022-09-23
200883C-000-NM-1500-5001 | [D] | 200883C | 0 | NM | 1500 | 5001 |  | 80 |  | Yuri Phase 0 - Modbus Mapping Address NCU (Network Control Unit) | Code: E0303 | INS | 000PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-07-19 | 2022-07-19 | 2022-07-19
200883C-000-NM-1500-5001 | [D] | 200883C | 0 | NM | 1500 | 5001 |  | 80 |  | Yuri Phase 0 - Modbus Mapping Address NCU (Network Control Unit) | Code: E0303 | INS | 000PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-08-18 | 2022-08-18 | 2022-08-18
200883C-000-NM-1500-5001 | [D] | 200883C | 0 | NM | 1500 | 5001 |  | 80 |  | Yuri Phase 0 - Modbus Mapping Address NCU (Network Control Unit) | Code: E0303 | INS | 000PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-09-17 | 2022-09-17 | 2022-09-17
200883C-000-NM-1500-5002 | [D] | 200883C | 0 | NM | 1500 | 5002 |  | 80 |  | Yuri Phase 0 - Master Signals List | Code: E0303 | INS | 000PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-06-20 | 2022-06-20 | 2022-06-20 | 2022-06-20
200883C-000-NM-1500-5002 | [D] | 200883C | 0 | NM | 1500 | 5002 |  | 80 |  | Yuri Phase 0 - Master Signals List | Code: E0303 | INS | 000PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-07-20 | 2022-07-20 | 2022-08-22
200883C-000-NM-1500-5002 | [D] | 200883C | 0 | NM | 1500 | 5002 |  | 80 |  | Yuri Phase 0 - Master Signals List | Code: E0303 | INS | 000PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-08-19 | 2022-08-19 | 2022-09-16
200883C-000-NM-1511-4000 | [D] | 200883C | 0 | NM | 1511 | 4000 |  | 32 |  | Yuri Phase 0 - ICS Hardwired I - O List | Code: E0311 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-000-NM-1511-4000 | [D] | 200883C | 0 | NM | 1511 | 4000 |  | 32 |  | Yuri Phase 0 - ICS Hardwired I - O List | Code: E0311 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-09-19 | 2022-09-19 | 2022-09-19
200883C-000-NM-1511-4000 | [D] | 200883C | 0 | NM | 1511 | 4000 |  | 32 |  | Yuri Phase 0 - ICS Hardwired I - O List | Code: E0311 | INS | 000H2 |  |  |  |  | IFU | 100 |  |  | MINS | 2022-10-17 | 2022-10-17 | 2022-10-17
200883C-000-NM-1511-4001 | [D] | 200883C | 0 | NM | 1511 | 4001 |  | 32 |  | Yuri Phase 0 - Serial Data I - O List | Code: E0311 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2023-03-24 | 2023-03-24 | 2023-03-24
200883C-000-NM-1511-4001 | [D] | 200883C | 0 | NM | 1511 | 4001 |  | 32 |  | Yuri Phase 0 - Serial Data I - O List | Code: E0311 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2023-03-31 | 2023-03-31 | 2023-03-31
200883C-000-NM-1511-4001 | [D] | 200883C | 0 | NM | 1511 | 4001 |  | 32 |  | Yuri Phase 0 - Serial Data I - O List | Code: E0311 | INS | 000H2 |  |  |  |  | IFU | 100 |  |  | MINS | 2023-04-28 | 2023-04-28 | 2023-04-28
200883C-000-NM-1511-4002 | [D] | 200883C | 0 | NM | 1511 | 4002 |  | 32 |  | Yuri Phase 0 - FandG Hardwired I - O List | Code: E0311 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-000-NM-1511-4002 | [D] | 200883C | 0 | NM | 1511 | 4002 |  | 32 |  | Yuri Phase 0 - FandG Hardwired I - O List | Code: E0311 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-09-19 | 2022-09-19 | 2022-09-19
200883C-000-NM-1511-4002 | [D] | 200883C | 0 | NM | 1511 | 4002 |  | 32 |  | Yuri Phase 0 - FandG Hardwired I - O List | Code: E0311 | INS | 000H2 |  |  |  |  | IFU | 100 |  |  | MINS | 2022-10-17 | 2022-10-17 | 2022-10-17
200883C-000-NM-1551-4000 | [D] | 200883C | 0 | NM | 1551 | 4000 |  | 63 |  | Yuri Phase 0 - Instrument and FandG Index | Code: E0311 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-25 | 2022-07-25 | 2022-07-25 | 2022-07-25
200883C-000-NM-1551-4000 | [D] | 200883C | 0 | NM | 1551 | 4000 |  | 63 |  | Yuri Phase 0 - Instrument and FandG Index | Code: E0311 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-000-NM-1551-4000 | [D] | 200883C | 0 | NM | 1551 | 4000 |  | 63 |  | Yuri Phase 0 - Instrument and FandG Index | Code: E0311 | INS | 000H2 |  |  |  |  | IFU | 100 |  |  | MINS | 2022-08-26 | 2022-08-26 | 2022-08-26
200883C-000-NM-1571-4000 | [D] | 200883C | 0 | NM | 1571 | 4000 |  | 48 |  | Yuri Phase 0 - Instrument Cable Schedule | Code: E0311 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-12-15 | 2022-12-15 | 2022-12-15
200883C-000-NM-1571-4000 | [D] | 200883C | 0 | NM | 1571 | 4000 |  | 48 |  | Yuri Phase 0 - Instrument Cable Schedule | Code: E0311 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-12-29 | 2022-12-29 | 2022-12-29
200883C-000-NM-1571-4000 | [D] | 200883C | 0 | NM | 1571 | 4000 |  | 48 |  | Yuri Phase 0 - Instrument Cable Schedule | Code: E0311 | INS | 000H2 |  |  |  |  | IFU | 100 |  |  | MINS | 2023-03-10 | 2023-03-10 | 2023-03-10
200883C-000-NM-1571-4001 | [D] | 200883C | 0 | NM | 1571 | 4001 |  | 48 |  | Yuri Phase 0 - Telecom & F&G Cable Schedule | Code: E0311 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2023-02-10 | 2023-02-10 | 2023-02-10
200883C-000-NM-1571-4001 | [D] | 200883C | 0 | NM | 1571 | 4001 |  | 48 |  | Yuri Phase 0 - Telecom & F&G Cable Schedule | Code: E0311 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2023-02-24 | 2023-02-24 | 2023-02-24
200883C-000-NM-1571-4001 | [D] | 200883C | 0 | NM | 1571 | 4001 |  | 48 |  | Yuri Phase 0 - Telecom & F&G Cable Schedule | Code: E0311 | INS | 000H2 |  |  |  |  | IFU | 100 |  |  | MINS | 2023-03-24 | 2023-03-24 | 2023-03-24
200883C-000-NM-1600-4000 | [D] | 200883C | 0 | NM | 1600 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Equipment List | Code: E0311 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-10-02 | 2022-10-02 | 2022-06-27 | 2022-06-27
200883C-000-NM-1600-4000 | [D] | 200883C | 0 | NM | 1600 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Equipment List | Code: E0311 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-10-07 | 2022-10-07 | 2022-06-27 | 2022-06-27
200883C-000-NM-1600-4000 | [D] | 200883C | 0 | NM | 1600 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Equipment List | Code: E0311 | ELE | 000H2 |  |  |  |  | IFU | 100 |  |  | MELE | 2022-11-04 | 2022-11-04 | 2022-11-04
200883C-000-NM-1623-4000 | [D] | 200883C | 0 | NM | 1623 | 4000 |  | 81 |  | Yuri Phase 0 - HV and LV Power and Control Cable Schedule | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-10-01 | 2022-10-01 | 2022-08-21 | 2022-08-21
200883C-000-NM-1623-4000 | [D] | 200883C | 0 | NM | 1623 | 4000 |  | 81 |  | Yuri Phase 0 - HV and LV Power and Control Cable Schedule | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-10-15 | 2022-10-15 | 2022-08-26 | 2022-08-26
200883C-000-NM-1623-4000 | [D] | 200883C | 0 | NM | 1623 | 4000 |  | 81 |  | Yuri Phase 0 - HV and LV Power and Control Cable Schedule | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-11-27 | 2022-11-27 | 2022-11-27
200883C-000-NM-1630-4000 | [D] | 200883C | 0 | NM | 1630 | 4000 |  | 81 |  | Yuri Phase 0 - Distribution Board Schedule | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-09-08 | 2022-09-08 | 2022-09-08
200883C-000-NM-1630-4000 | [D] | 200883C | 0 | NM | 1630 | 4000 |  | 81 |  | Yuri Phase 0 - Distribution Board Schedule | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-09-15 | 2022-09-15 | 2022-09-15
200883C-000-NM-1630-4000 | [D] | 200883C | 0 | NM | 1630 | 4000 |  | 81 |  | Yuri Phase 0 - Distribution Board Schedule | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-10-13 | 2022-10-13 | 2022-10-13
200883C-000-NM-1654-4000 | [D] | 200883C | 0 | NM | 1654 | 4000 |  | 81 |  | Yuri Phase 0 - LV Switchgear Schedule | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-08 | 2022-06-08 | 2022-06-15 | 2022-06-15
200883C-000-NM-1654-4000 | [D] | 200883C | 0 | NM | 1654 | 4000 |  | 81 |  | Yuri Phase 0 - LV Switchgear Schedule | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-06-27 | 2022-06-27
200883C-000-NM-1654-4000 | [D] | 200883C | 0 | NM | 1654 | 4000 |  | 81 |  | Yuri Phase 0 - LV Switchgear Schedule | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-07-13 | 2022-07-13 | 2022-07-13
200883C-000-NM-1900-1000 | [D] | 200883C | 0 | NM | 1900 | 1000 |  | 30 |  | Yuri Phase 0 - List of Hazardous materials during operation | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-06-28 | 2022-06-28 | 2022-10-31
200883C-000-NM-1900-1000 | [D] | 200883C | 0 | NM | 1900 | 1000 |  | 30 |  | Yuri Phase 0 - List of Hazardous materials during operation | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-07-18 | 2022-07-18 | 2022-11-18
200883C-000-NM-1900-1000 | [D] | 200883C | 0 | NM | 1900 | 1000 |  | 30 |  | Yuri Phase 0 - List of Hazardous materials during operation | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-10-31 | 2022-10-31 | 2022-12-16
200883C-000-NM-1900-1001 | [D] | 200883C | 0 | NM | 1900 | 1001 |  | 30 |  | Yuri Phase 0 - Safety Critical Element Register | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-08-23 | 2022-08-23 | 2022-08-29
200883C-000-NM-1900-1001 | [D] | 200883C | 0 | NM | 1900 | 1001 |  | 30 |  | Yuri Phase 0 - Safety Critical Element Register | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-09-12 | 2022-09-12 | 2022-09-16
200883C-000-NM-1900-1001 | [D] | 200883C | 0 | NM | 1900 | 1001 |  | 30 |  | Yuri Phase 0 - Safety Critical Element Register | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-10-11 | 2022-10-11 | 2022-10-14
200883C-000-NM-1932-4000 | [D] | 200883C | 0 | NM | 1932 | 4000 |  | 29 |  | Yuri Phase 0 - Firewater Line List | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-07-08 | 2022-07-08 | 2022-06-30 | 2022-06-30
200883C-000-NM-1932-4000 | [D] | 200883C | 0 | NM | 1932 | 4000 |  | 29 |  | Yuri Phase 0 - Firewater Line List | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-07-14 | 2022-07-14 | 2022-06-30 | 2022-06-30
200883C-000-NM-1932-4000 | [D] | 200883C | 0 | NM | 1932 | 4000 |  | 29 |  | Yuri Phase 0 - Firewater Line List | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2022-10-04 | 2022-10-04 | 2022-10-04
200883C-000-NM-1932-4000 | [D] | 200883C | 0 | NM | 1932 | 4000 |  | 29 |  | Yuri Phase 0 - Firewater Line List | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-02-06 | 2023-02-06 | 2023-02-06
200883C-000-NM-1950-4000 | [D] | 200883C | 0 | NM | 1950 | 4000 |  | 29 |  | Yuri Phase 0 - Fire & Gas Cause & Effect Chart | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-07-25 | 2022-07-25 | 2022-07-25 | 2022-07-25
200883C-000-NM-1950-4000 | [D] | 200883C | 0 | NM | 1950 | 4000 |  | 29 |  | Yuri Phase 0 - Fire & Gas Cause & Effect Chart | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-000-NM-1950-4000 | [D] | 200883C | 0 | NM | 1950 | 4000 |  | 29 |  | Yuri Phase 0 - Fire & Gas Cause & Effect Chart | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2022-10-19 | 2022-10-19 | 2022-10-19
200883C-000-NM-1950-4000 | [D] | 200883C | 0 | NM | 1950 | 4000 |  | 29 |  | Yuri Phase 0 - Fire & Gas Cause & Effect Chart | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-02-09 | 2023-02-09 | 2023-02-09
200883C-000-RT-0008-1000 | [D] | 200883C | 0 | RT | 8 | 1000 |  | 200 |  | Yuri Phase 0 - RAM Study | Code: E0303 | MEC | 000H2 |  |  |  |  | STA | 10 |  |  | AMEC | 2022-04-02 | 2022-04-02 | 2022-04-02 | 2022-04-02
200883C-000-RT-0008-1000 | [D] | 200883C | 0 | RT | 8 | 1000 |  | 200 |  | Yuri Phase 0 - RAM Study | Code: E0303 | MEC | 000H2 |  |  |  |  | IFR | 70 |  |  | AMEC | 2022-07-30 | 2022-07-30 | 2023-04-20
200883C-000-RT-0008-1000 | [D] | 200883C | 0 | RT | 8 | 1000 |  | 200 |  | Yuri Phase 0 - RAM Study | Code: E0303 | MEC | 000H2 |  |  |  |  | IFC | 100 |  |  | AMEC | 2022-10-31 | 2022-10-31 | 2023-05-19
200883C-000-RT-1400-5001 | [D] | 200883C | 0 | RT | 1400 | 5001 |  | 30 |  | Yuri Phase 0 - Atmospheric Corrosion Assessment | Code: E0303 | CIV | 000PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-05-31 | 2022-05-31 | 2022-05-31 | 2022-05-31
200883C-000-RT-1400-5001 | [D] | 200883C | 0 | RT | 1400 | 5001 |  | 30 |  | Yuri Phase 0 - Atmospheric Corrosion Assessment | Code: E0303 | CIV | 000PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-07-06 | 2022-07-06
200883C-000-RT-1400-5001 | [D] | 200883C | 0 | RT | 1400 | 5001 |  | 30 |  | Yuri Phase 0 - Atmospheric Corrosion Assessment | Code: E0303 | CIV | 000PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-30
200883C-000-RT-1500-4000 | [D] | 200883C | 0 | RT | 1500 | 4000 |  | 16 |  | Yuri Phase 0 - Hazardous Area Dossier Instruments | Code: E0311 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2023-01-07 | 2023-01-07 | 2023-01-07
200883C-000-RT-1500-4000 | [D] | 200883C | 0 | RT | 1500 | 4000 |  | 16 |  | Yuri Phase 0 - Hazardous Area Dossier Instruments | Code: E0311 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2023-01-15 | 2023-01-15 | 2023-01-15
200883C-000-RT-1500-4000 | [D] | 200883C | 0 | RT | 1500 | 4000 |  | 16 |  | Yuri Phase 0 - Hazardous Area Dossier Instruments | Code: E0311 | INS | 000H2 |  |  |  |  | IFU | 100 |  |  | MINS | 2023-02-12 | 2023-02-12 | 2023-02-12
200883C-000-RT-1600-1000 | [D] | 200883C | 0 | RT | 1600 | 1000 |  | 120 |  | Yuri Phase 0 - Energy and H2 Production Model | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | AELE | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-000-RT-1600-1000 | [D] | 200883C | 0 | RT | 1600 | 1000 |  | 120 |  | Yuri Phase 0 - Energy and H2 Production Model | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | AELE | 2022-06-20 | 2022-06-20 | 2022-09-08
200883C-000-RT-1600-1000 | [D] | 200883C | 0 | RT | 1600 | 1000 |  | 120 |  | Yuri Phase 0 - Energy and H2 Production Model | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | AELE | 2022-08-31 | 2022-08-31 | 2022-10-07
200883C-000-RT-1600-1001 | [D] | 200883C | 0 | RT | 1600 | 1001 |  | 40 |  | Yuri Phase 0 - SOREL Terms of Reference | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | AELE | 2022-06-30 | 2022-06-30 | 2022-06-25 | 2022-06-25
200883C-000-RT-1600-1001 | [D] | 200883C | 0 | RT | 1600 | 1001 |  | 40 |  | Yuri Phase 0 - SOREL Terms of Reference | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | AELE | 2022-08-31 | 2022-08-31 | 2022-06-25 | 2022-06-25
200883C-000-RT-1600-1001 | [D] | 200883C | 0 | RT | 1600 | 1001 |  | 40 |  | Yuri Phase 0 - SOREL Terms of Reference | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | AELE | 2023-03-01 | 2023-03-01 | 2022-07-06 | 2022-07-06
200883C-000-RT-1600-5000 | [D] | 200883C | 0 | RT | 1600 | 5000 |  | 120 |  | Yuri Phase 0 - Arc Fault Studies | Code: E0303 | ELE | 000PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-08-14 | 2022-08-14 | 2022-08-14
200883C-000-RT-1600-5000 | [D] | 200883C | 0 | RT | 1600 | 5000 |  | 120 |  | Yuri Phase 0 - Arc Fault Studies | Code: E0303 | ELE | 000PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-000-RT-1600-5000 | [D] | 200883C | 0 | RT | 1600 | 5000 |  | 120 |  | Yuri Phase 0 - Arc Fault Studies | Code: E0303 | ELE | 000PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-10-13 | 2022-10-13 | 2022-10-13
200883C-000-RT-1600-5001 | [D] | 200883C | 0 | RT | 1600 | 5001 |  | 100 |  | Yuri Phase 0 - Relay Coordination and Selectivity Studies | Code: E0303 | ELE | 000PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-11-15 | 2022-11-15 | 2022-11-15
200883C-000-RT-1600-5001 | [D] | 200883C | 0 | RT | 1600 | 5001 |  | 100 |  | Yuri Phase 0 - Relay Coordination and Selectivity Studies | Code: E0303 | ELE | 000PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-12-15 | 2022-12-15 | 2022-12-15
200883C-000-RT-1600-5001 | [D] | 200883C | 0 | RT | 1600 | 5001 |  | 100 |  | Yuri Phase 0 - Relay Coordination and Selectivity Studies | Code: E0303 | ELE | 000PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2023-01-14 | 2023-01-14 | 2023-01-14
200883C-000-RT-1900-1000 | [D] | 200883C | 0 | RT | 1900 | 1000 |  | 42 |  | Yuri Phase 0 - Hazardous Area Classification Report | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-06-28 | 2022-06-28 | 2022-08-22
200883C-000-RT-1900-1000 | [D] | 200883C | 0 | RT | 1900 | 1000 |  | 42 |  | Yuri Phase 0 - Hazardous Area Classification Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-07-18 | 2022-07-18 | 2022-08-29
200883C-000-RT-1900-1000 | [D] | 200883C | 0 | RT | 1900 | 1000 |  | 42 |  | Yuri Phase 0 - Hazardous Area Classification Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-08-15 | 2022-08-15 | 2022-09-26
200883C-000-RT-1900-1001 | [D] | 200883C | 0 | RT | 1900 | 1001 |  | 60 |  | Yuri Phase 0 - LOPA Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-06-28 | 2022-06-28 | 2022-09-12
200883C-000-RT-1900-1001 | [D] | 200883C | 0 | RT | 1900 | 1001 |  | 60 |  | Yuri Phase 0 - LOPA Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-07-18 | 2022-07-18 | 2022-09-13
200883C-000-RT-1900-1001 | [D] | 200883C | 0 | RT | 1900 | 1001 |  | 60 |  | Yuri Phase 0 - LOPA Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-08-15 | 2022-08-15 | 2022-10-05
200883C-000-RT-1900-1002 | [D] | 200883C | 0 | RT | 1900 | 1002 |  | 60 |  | Yuri Phase 0 - HAZOP Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-08-17 | 2022-08-17 | 2022-08-17
200883C-000-RT-1900-1002 | [D] | 200883C | 0 | RT | 1900 | 1002 |  | 60 |  | Yuri Phase 0 - HAZOP Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-08-30 | 2022-08-30 | 2022-08-30
200883C-000-RT-1900-1002 | [D] | 200883C | 0 | RT | 1900 | 1002 |  | 60 |  | Yuri Phase 0 - HAZOP Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-09-20 | 2022-09-20 | 2022-09-20
200883C-000-RT-1900-1003 | [D] | 200883C | 0 | RT | 1900 | 1003 |  | 40 |  | Yuri Phase 0 - HSE Risk Register | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-08-16 | 2022-08-16 | 2022-08-16
200883C-000-RT-1900-1003 | [D] | 200883C | 0 | RT | 1900 | 1003 |  | 40 |  | Yuri Phase 0 - HSE Risk Register | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-09-05 | 2022-09-05 | 2022-09-05
200883C-000-RT-1900-1003 | [D] | 200883C | 0 | RT | 1900 | 1003 |  | 40 |  | Yuri Phase 0 - HSE Risk Register | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-10-04 | 2022-10-04 | 2022-10-04
200883C-000-RT-1900-1004 | [D] | 200883C | 0 | RT | 1900 | 1004 |  | 40 |  | Yuri Phase 0 - HAZID Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-000-RT-1900-1004 | [D] | 200883C | 0 | RT | 1900 | 1004 |  | 40 |  | Yuri Phase 0 - HAZID Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-08-24 | 2022-08-24 | 2022-08-24
200883C-000-RT-1900-1004 | [D] | 200883C | 0 | RT | 1900 | 1004 |  | 40 |  | Yuri Phase 0 - HAZID Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-10-12 | 2022-10-12 | 2022-09-09
200883C-000-RT-1900-1005 | [D] | 200883C | 0 | RT | 1900 | 1005 |  | 20 |  | Yuri Phase 0 - SIL Verification Report | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-09-29 | 2022-09-29 | 2022-09-29
200883C-000-RT-1900-1005 | [D] | 200883C | 0 | RT | 1900 | 1005 |  | 20 |  | Yuri Phase 0 - SIL Verification Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-10-19 | 2022-10-19 | 2022-10-19
200883C-000-RT-1900-1005 | [D] | 200883C | 0 | RT | 1900 | 1005 |  | 20 |  | Yuri Phase 0 - SIL Verification Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-11-16 | 2022-11-16 | 2022-11-16
200883C-000-RT-1900-1006 | [D] | 200883C | 0 | RT | 1900 | 1006 |  | 30 |  | Yuri Phase 0 - Human Factors Review Report | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-000-RT-1900-1006 | [D] | 200883C | 0 | RT | 1900 | 1006 |  | 30 |  | Yuri Phase 0 - Human Factors Review Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-000-RT-1900-1006 | [D] | 200883C | 0 | RT | 1900 | 1006 |  | 30 |  | Yuri Phase 0 - Human Factors Review Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-11-30 | 2022-11-30 | 2022-11-30
200883C-000-RT-1900-1007 | [D] | 200883C | 0 | RT | 1900 | 1007 |  | 30 |  | Yuri Phase 0 - SFARP Assessment Report | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-10-12 | 2022-10-12 | 2022-10-12
200883C-000-RT-1900-1007 | [D] | 200883C | 0 | RT | 1900 | 1007 |  | 30 |  | Yuri Phase 0 - SFARP Assessment Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-11-01 | 2022-11-01 | 2022-11-01
200883C-000-RT-1900-1007 | [D] | 200883C | 0 | RT | 1900 | 1007 |  | 30 |  | Yuri Phase 0 - SFARP Assessment Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-12-30 | 2022-12-30 | 2022-12-30
200883C-000-RT-1900-1008 | [D] | 200883C | 0 | RT | 1900 | 1008 |  | 30 |  | Yuri Phase 0 - Quantitative Risk Assessment Report | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-000-RT-1900-1008 | [D] | 200883C | 0 | RT | 1900 | 1008 |  | 30 |  | Yuri Phase 0 - Quantitative Risk Assessment Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-07-30 | 2022-07-30 | 2022-11-23
200883C-000-RT-1900-1008 | [D] | 200883C | 0 | RT | 1900 | 1008 |  | 30 |  | Yuri Phase 0 - Quantitative Risk Assessment Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-09-30 | 2022-09-30 | 2022-12-21
200883C-000-RT-1900-1009 | [D] | 200883C | 0 | RT | 1900 | 1009 |  | 40 |  | Yuri Phase 0 - Terms of Reference - HAZID Study | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-000-RT-1900-1009 | [D] | 200883C | 0 | RT | 1900 | 1009 |  | 40 |  | Yuri Phase 0 - Terms of Reference - HAZID Study | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-07-22 | 2022-07-22 | 2022-07-05 | 2022-07-05
200883C-000-RT-1900-1009 | [D] | 200883C | 0 | RT | 1900 | 1009 |  | 40 |  | Yuri Phase 0 - Terms of Reference - HAZID Study | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-08-31 | 2022-08-31 | 2022-07-18
200883C-000-RT-1900-1010 | [D] | 200883C | 0 | RT | 1900 | 1010 |  | 40 |  | Yuri Phase 0 - Terms of Reference - HAZOP Study | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-000-RT-1900-1010 | [D] | 200883C | 0 | RT | 1900 | 1010 |  | 40 |  | Yuri Phase 0 - Terms of Reference - HAZOP Study | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-07-22 | 2022-07-22 | 2022-08-13 | 2022-08-13
200883C-000-RT-1900-1010 | [D] | 200883C | 0 | RT | 1900 | 1010 |  | 40 |  | Yuri Phase 0 - Terms of Reference - HAZOP Study | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-08-31 | 2022-08-31 | 2022-08-16 | 2022-08-16
200883C-000-RT-1900-1011 | [D] | 200883C | 0 | RT | 1900 | 1011 |  | 40 |  | Yuri Phase 0 - Terms of Reference - LOPA Study | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-09-03 | 2022-09-03 | 2022-08-13 | 2022-08-13
200883C-000-RT-1900-1011 | [D] | 200883C | 0 | RT | 1900 | 1011 |  | 40 |  | Yuri Phase 0 - Terms of Reference - LOPA Study | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-09-10 | 2022-09-10 | 2022-08-15 | 2022-08-15
200883C-000-RT-1900-1011 | [D] | 200883C | 0 | RT | 1900 | 1011 |  | 40 |  | Yuri Phase 0 - Terms of Reference - LOPA Study | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-10-31 | 2022-10-31 | 2022-09-02
200883C-000-RT-1900-4000 | [D] | 200883C | 0 | RT | 1900 | 4000 |  | 44 |  | Yuri Phase 0 - Fire Water System Hydraulic Report | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-000-RT-1900-4000 | [D] | 200883C | 0 | RT | 1900 | 4000 |  | 44 |  | Yuri Phase 0 - Fire Water System Hydraulic Report | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-000-RT-1900-4000 | [D] | 200883C | 0 | RT | 1900 | 4000 |  | 44 |  | Yuri Phase 0 - Fire Water System Hydraulic Report | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-000-RT-1900-4000 | [D] | 200883C | 0 | RT | 1900 | 4000 |  | 44 |  | Yuri Phase 0 - Fire Water System Hydraulic Report | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-000-RT-1900-4001 | [D] | 200883C | 0 | RT | 1900 | 4001 |  | 44 |  | Yuri Phase 0 - Fire and Gas Mapping Study Report | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-12-08 | 2022-12-08 | 2022-12-08
200883C-000-RT-1900-4001 | [D] | 200883C | 0 | RT | 1900 | 4001 |  | 44 |  | Yuri Phase 0 - Fire and Gas Mapping Study Report | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-000-RT-1900-4001 | [D] | 200883C | 0 | RT | 1900 | 4001 |  | 44 |  | Yuri Phase 0 - Fire and Gas Mapping Study Report | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-000-RT-1900-4001 | [D] | 200883C | 0 | RT | 1900 | 4001 |  | 44 |  | Yuri Phase 0 - Fire and Gas Mapping Study Report | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-000-RT-1900-5000 | [D] | 200883C | 0 | RT | 1900 | 5000 |  | 1 |  | Yuri Phase 0 - Onshore Facilities Construction Formal Safety Assessment Report(DELETED 3-Aug-22) | Code: E0303 | SAF | 000PV |  |  |  |  | STA | 10 |  |  | MFSAF | 2022-08-31 | 2022-08-31 | 2022-07-29 | 2022-07-29
200883C-000-RT-1900-5000 | [D] | 200883C | 0 | RT | 1900 | 5000 |  | 1 |  | Yuri Phase 0 - Onshore Facilities Construction Formal Safety Assessment Report(DELETED 3-Aug-22) | Code: E0303 | SAF | 000PV |  |  |  |  | IFR | 70 |  |  | MFSAF | 2022-09-30 | 2022-09-30 | 2022-07-29 | 2022-07-29
200883C-000-RT-1900-5000 | [D] | 200883C | 0 | RT | 1900 | 5000 |  | 1 |  | Yuri Phase 0 - Onshore Facilities Construction Formal Safety Assessment Report(DELETED 3-Aug-22) | Code: E0303 | SAF | 000PV |  |  |  |  | IFC | 100 |  |  | MFSAF | 2022-10-30 | 2022-10-30 | 2022-07-29 | 2022-07-29
200883C-000-SOW-1600-4000 | [D] | 200883C | 0 | SOW | 1600 | 4000 |  | 41 |  | Yuri Phase 0 - Scope of Work for Site Electrical Installation | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-08 | 2022-06-08 | 2022-06-08 | 2022-06-08
200883C-000-SOW-1600-4000 | [D] | 200883C | 0 | SOW | 1600 | 4000 |  | 41 |  | Yuri Phase 0 - Scope of Work for Site Electrical Installation | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-08-12 | 2022-08-12
200883C-000-SOW-1600-4000 | [D] | 200883C | 0 | SOW | 1600 | 4000 |  | 41 |  | Yuri Phase 0 - Scope of Work for Site Electrical Installation | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-13 | 2022-07-13 | 2022-08-31
200883C-000-SP-1641-4000 | [D] | 200883C | 0 | SP | 1641 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - Transformers | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-06 | 2022-06-06 | 2022-06-03 | 2022-06-03
200883C-000-SP-1641-4000 | [D] | 200883C | 0 | SP | 1641 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - Transformers | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-10 | 2022-06-10 | 2022-06-03 | 2022-06-03
200883C-000-SP-1641-4000 | [D] | 200883C | 0 | SP | 1641 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - Transformers | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-08 | 2022-07-08 | 2022-08-01 | 2022-08-01
200883C-000-SP-1641-4001 | [D] | 200883C | 0 | SP | 1641 | 4001 |  | 21 |  | Yuri Phase 0 - Data Sheet - Neutral Earthing Resistor | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-06 | 2022-06-06 | 2022-06-07 | 2022-06-07
200883C-000-SP-1641-4001 | [D] | 200883C | 0 | SP | 1641 | 4001 |  | 21 |  | Yuri Phase 0 - Data Sheet - Neutral Earthing Resistor | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-10 | 2022-06-10 | 2022-06-07 | 2022-06-07
200883C-000-SP-1641-4001 | [D] | 200883C | 0 | SP | 1641 | 4001 |  | 21 |  | Yuri Phase 0 - Data Sheet - Neutral Earthing Resistor | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-08 | 2022-07-08 | 2022-07-29 | 2022-07-29
200883C-000-SP-1652-4000 | [D] | 200883C | 0 | SP | 1652 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - HV Switchgear | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-06 | 2022-06-06 | 2022-06-01 | 2022-06-01
200883C-000-SP-1652-4000 | [D] | 200883C | 0 | SP | 1652 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - HV Switchgear | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-10 | 2022-06-10 | 2022-06-01 | 2022-06-01
200883C-000-SP-1652-4000 | [D] | 200883C | 0 | SP | 1652 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - HV Switchgear | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-08 | 2022-07-08 | 2022-07-29 | 2022-07-29
200883C-000-SP-1654-4000 | [D] | 200883C | 0 | SP | 1654 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - LV Switchgear | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-06 | 2022-06-06 | 2022-06-03 | 2022-06-03
200883C-000-SP-1654-4000 | [D] | 200883C | 0 | SP | 1654 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - LV Switchgear | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-10 | 2022-06-10 | 2022-06-03 | 2022-06-03
200883C-000-SP-1654-4000 | [D] | 200883C | 0 | SP | 1654 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - LV Switchgear | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-08 | 2022-07-08 | 2022-07-29 | 2022-07-29
200883C-000-SP-1657-4000 | [D] | 200883C | 0 | SP | 1657 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - Power Distribution Board | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-09 | 2022-06-09 | 2022-06-09 | 2022-06-09
200883C-000-SP-1657-4000 | [D] | 200883C | 0 | SP | 1657 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - Power Distribution Board | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-07-13 | 2022-07-13
200883C-000-SP-1657-4000 | [D] | 200883C | 0 | SP | 1657 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - Power Distribution Board | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-13 | 2022-07-13 | 2022-07-13 | 2022-07-13
200883C-000-SP-1671-4000 | [D] | 200883C | 0 | SP | 1671 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - AC UPS System | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-09 | 2022-06-09 | 2022-06-15 | 2022-06-15
200883C-000-SP-1671-4000 | [D] | 200883C | 0 | SP | 1671 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - AC UPS System | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-06-30 | 2022-06-30
200883C-000-SP-1671-4000 | [D] | 200883C | 0 | SP | 1671 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - AC UPS System | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-13 | 2022-07-13 | 2022-08-22 | 2022-08-22
200883C-000-SP-1672-4000 | [D] | 200883C | 0 | SP | 1672 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - DC UPS System | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-09 | 2022-06-09 | 2022-06-15 | 2022-06-15
200883C-000-SP-1672-4000 | [D] | 200883C | 0 | SP | 1672 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - DC UPS System | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-06-30 | 2022-06-30
200883C-000-SP-1672-4000 | [D] | 200883C | 0 | SP | 1672 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - DC UPS System | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-13 | 2022-07-13 | 2022-07-29 | 2022-07-29
200883C-000-SP-1691-4000 | [D] | 200883C | 0 | SP | 1691 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - LV Motors | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-06 | 2022-06-06 | 2022-05-17 | 2022-05-17
200883C-000-SP-1691-4000 | [D] | 200883C | 0 | SP | 1691 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - LV Motors | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-10 | 2022-06-10 | 2022-05-17 | 2022-05-17
200883C-000-SP-1691-4000 | [D] | 200883C | 0 | SP | 1691 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - LV Motors | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-08 | 2022-07-08 | 2022-07-29 | 2022-07-29
200883C-000-SP-1693-4000 | [D] | 200883C | 0 | SP | 1693 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - Variable Speed Drives | Code: E0301 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-06 | 2022-06-06 | 2022-06-10 | 2022-06-10
200883C-000-SP-1693-4000 | [D] | 200883C | 0 | SP | 1693 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - Variable Speed Drives | Code: E0301 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-10 | 2022-06-10 | 2022-06-10 | 2022-06-10
200883C-000-SP-1693-4000 | [D] | 200883C | 0 | SP | 1693 | 4000 |  | 21 |  | Yuri Phase 0 - Data Sheet - Variable Speed Drives | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-08 | 2022-07-08 | 2022-07-29 | 2022-07-29
200883C-000-SP-1940-4000 | [D] | 200883C | 0 | SP | 1940 | 4000 |  | 36 |  | Yuri Phase 0 - Data Sheets For Safety Equipment | Code: E0401 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | MSAF | 2022-08-25 | 2022-08-25 | 2022-08-25 | 2022-08-25
200883C-000-SP-1940-4000 | [D] | 200883C | 0 | SP | 1940 | 4000 |  | 36 |  | Yuri Phase 0 - Data Sheets For Safety Equipment | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-09-02 | 2022-09-02 | 2022-09-02
200883C-000-SP-1940-4000 | [D] | 200883C | 0 | SP | 1940 | 4000 |  | 36 |  | Yuri Phase 0 - Data Sheets For Safety Equipment | Code: E0401 | SAF | 000H2 |  |  |  |  | IFD | 70 |  |  | MSAF | 2022-09-30 | 2022-09-30 | 2022-09-30
200883C-000-SP-1940-4000 | [D] | 200883C | 0 | SP | 1940 | 4000 |  | 36 |  | Yuri Phase 0 - Data Sheets For Safety Equipment | Code: E0401 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | MSAF | 2022-10-28 | 2022-10-28 | 2022-10-28
200883C-000-STC-1490-2000 | [D] | 200883C | 0 | STC | 1490 | 2000 |  | 25 |  | Yuri Phase 0 - Civil Works Standard Drawings | Code: E0303 | CIV | 000H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-06-15 | 2022-06-15 | 2022-06-24 | 2022-06-24
200883C-000-STC-1490-2000 | [D] | 200883C | 0 | STC | 1490 | 2000 |  | 25 |  | Yuri Phase 0 - Civil Works Standard Drawings | Code: E0303 | CIV | 000H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-06-24 | 2022-06-24 | 2022-06-30 | 2022-06-30
200883C-000-STC-1490-2000 | [D] | 200883C | 0 | STC | 1490 | 2000 |  | 25 |  | Yuri Phase 0 - Civil Works Standard Drawings | Code: E0303 | CIV | 000H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-07-22 | 2022-07-22 | 2022-08-29
200883C-000-STC-1790-2000 | [D] | 200883C | 0 | STC | 1790 | 2000 |  | 25 |  | Yuri Phase 0 - Concrete Works Standard Drawings | Code: E0303 | CIV | 000H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-06-15 | 2022-06-15 | 2022-06-24 | 2022-06-24
200883C-000-STC-1790-2000 | [D] | 200883C | 0 | STC | 1790 | 2000 |  | 25 |  | Yuri Phase 0 - Concrete Works Standard Drawings | Code: E0303 | CIV | 000H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-06-24 | 2022-06-24 | 2022-06-30 | 2022-06-30
200883C-000-STC-1790-2000 | [D] | 200883C | 0 | STC | 1790 | 2000 |  | 25 |  | Yuri Phase 0 - Concrete Works Standard Drawings | Code: E0303 | CIV | 000H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-07-22 | 2022-07-22 | 2022-08-22 | 2022-08-22
200883C-000-STC-1790-2001 | [D] | 200883C | 0 | STC | 1790 | 2001 |  | 25 |  | Yuri Phase 0 - Typical Earthing Details - Rebar - Structures | Code: E0303 | CIV | 000H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-06-15 | 2022-06-15 | 2022-06-24 | 2022-06-24
200883C-000-STC-1790-2001 | [D] | 200883C | 0 | STC | 1790 | 2001 |  | 25 |  | Yuri Phase 0 - Typical Earthing Details - Rebar - Structures | Code: E0303 | CIV | 000H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-06-24 | 2022-06-24 | 2022-06-30 | 2022-06-30
200883C-000-STC-1790-2001 | [D] | 200883C | 0 | STC | 1790 | 2001 |  | 25 |  | Yuri Phase 0 - Typical Earthing Details - Rebar - Structures | Code: E0303 | CIV | 000H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-07-22 | 2022-07-22 | 2022-07-29 | 2022-07-29
200883C-000-STD-1681-4000 | [D] | 200883C | 0 | STD | 1681 | 4000 |  | 21 |  | Yuri Phase 0 - Earthing System Standard Details | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-06 | 2022-06-06 | 2022-06-03 | 2022-06-03
200883C-000-STD-1681-4000 | [D] | 200883C | 0 | STD | 1681 | 4000 |  | 21 |  | Yuri Phase 0 - Earthing System Standard Details | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-10 | 2022-06-10 | 2022-06-03 | 2022-06-03
200883C-000-STD-1681-4000 | [D] | 200883C | 0 | STD | 1681 | 4000 |  | 21 |  | Yuri Phase 0 - Earthing System Standard Details | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-07-15 | 2022-07-15 | 2022-08-05 | 2022-08-05
200883C-000-STD-1682-4000 | [D] | 200883C | 0 | STD | 1682 | 4000 |  | 21 |  | Yuri Phase 0 - Power System Standard Details | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-06 | 2022-06-06 | 2022-06-03 | 2022-06-03
200883C-000-STD-1682-4000 | [D] | 200883C | 0 | STD | 1682 | 4000 |  | 21 |  | Yuri Phase 0 - Power System Standard Details | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-10 | 2022-06-10 | 2022-06-03 | 2022-06-03
200883C-000-STD-1682-4000 | [D] | 200883C | 0 | STD | 1682 | 4000 |  | 21 |  | Yuri Phase 0 - Power System Standard Details | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-07-15 | 2022-07-15 | 2022-08-03 | 2022-08-03
200883C-000-STD-1683-4000 | [D] | 200883C | 0 | STD | 1683 | 4000 |  | 21 |  | Yuri Phase 0 - Lighting System Standard Details | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-06 | 2022-06-06 | 2022-06-03 | 2022-06-03
200883C-000-STD-1683-4000 | [D] | 200883C | 0 | STD | 1683 | 4000 |  | 21 |  | Yuri Phase 0 - Lighting System Standard Details | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-10 | 2022-06-10 | 2022-06-03 | 2022-06-03
200883C-000-STD-1683-4000 | [D] | 200883C | 0 | STD | 1683 | 4000 |  | 21 |  | Yuri Phase 0 - Lighting System Standard Details | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-07-15 | 2022-07-15 | 2022-08-03 | 2022-08-03
200883C-000-TAS-000 | [T] | 200883C | 0 | TAS | 0 |  |  | 210 |  | Engineering System Support | Code: T0100 | ENS | 000H2 |  |  |  |  | STA | 5 |  |  | AENS | 2022-04-30 | 2022-04-30 | 2022-04-30 | 2022-04-30
200883C-000-TAS-000 | [T] | 200883C | 0 | TAS | 0 |  |  | 210 |  | Engineering System Support | Code: T0100 | ENS | 000H2 |  |  |  |  | M1 | 10 |  |  | AENS | 2022-05-31 | 2022-05-31 | 2022-06-25 | 2022-06-25
200883C-000-TAS-000 | [T] | 200883C | 0 | TAS | 0 |  |  | 210 |  | Engineering System Support | Code: T0100 | ENS | 000H2 |  |  |  |  | M2 | 20 |  |  | AENS | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-000-TAS-000 | [T] | 200883C | 0 | TAS | 0 |  |  | 210 |  | Engineering System Support | Code: T0100 | ENS | 000H2 |  |  |  |  | M3 | 30 |  |  | AENS | 2022-07-31 | 2022-07-31 | 2022-08-15 | 2022-08-15
200883C-000-TAS-000 | [T] | 200883C | 0 | TAS | 0 |  |  | 210 |  | Engineering System Support | Code: T0100 | ENS | 000H2 |  |  |  |  | M4 | 40 |  |  | AENS | 2022-08-31 | 2022-08-31 | 2022-08-31
200883C-000-TAS-000 | [T] | 200883C | 0 | TAS | 0 |  |  | 210 |  | Engineering System Support | Code: T0100 | ENS | 000H2 |  |  |  |  | M5 | 50 |  |  | AENS | 2022-09-30 | 2022-09-30 | 2022-09-30
200883C-000-TAS-000 | [T] | 200883C | 0 | TAS | 0 |  |  | 210 |  | Engineering System Support | Code: T0100 | ENS | 000H2 |  |  |  |  | M6 | 60 |  |  | AENS | 2022-10-31 | 2022-10-31 | 2022-10-31
200883C-000-TAS-000 | [T] | 200883C | 0 | TAS | 0 |  |  | 210 |  | Engineering System Support | Code: T0100 | ENS | 000H2 |  |  |  |  | M7 | 70 |  |  | AENS | 2022-11-30 | 2022-11-30 | 2022-11-30
200883C-000-TAS-000 | [T] | 200883C | 0 | TAS | 0 |  |  | 210 |  | Engineering System Support | Code: T0100 | ENS | 000H2 |  |  |  |  | M8 | 80 |  |  | AENS | 2022-12-31 | 2022-12-31 | 2022-12-31
200883C-000-TAS-000 | [T] | 200883C | 0 | TAS | 0 |  |  | 210 |  | Engineering System Support | Code: T0100 | ENS | 000H2 |  |  |  |  | M9 | 90 |  |  | AENS | 2023-01-31 | 2023-01-31 | 2023-01-31
200883C-000-TAS-000 | [T] | 200883C | 0 | TAS | 0 |  |  | 210 |  | Engineering System Support | Code: T0100 | ENS | 000H2 |  |  |  |  | FIN | 100 |  |  | AENS | 2023-02-28 | 2023-02-28 | 2023-02-28
200883C-000-TAS-000-0001 | [T] | 200883C | 0 | TAS | 0 | 1 |  | 660 |  | Process Australia Task | Code: T0100 | PRO | 000H2 |  |  |  |  | STA | 5 |  |  | APRO | 2022-04-30 | 2022-04-30 | 2022-04-30 | 2022-04-30
200883C-000-TAS-000-0001 | [T] | 200883C | 0 | TAS | 0 | 1 |  | 660 |  | Process Australia Task | Code: T0100 | PRO | 000H2 |  |  |  |  | M1 | 10 |  |  | APRO | 2022-05-31 | 2022-05-31 | 2022-06-25 | 2022-06-25
200883C-000-TAS-000-0001 | [T] | 200883C | 0 | TAS | 0 | 1 |  | 660 |  | Process Australia Task | Code: T0100 | PRO | 000H2 |  |  |  |  | M2 | 20 |  |  | APRO | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-000-TAS-000-0001 | [T] | 200883C | 0 | TAS | 0 | 1 |  | 660 |  | Process Australia Task | Code: T0100 | PRO | 000H2 |  |  |  |  | M3 | 30 |  |  | APRO | 2022-07-31 | 2022-07-31 | 2022-08-31
200883C-000-TAS-000-0001 | [T] | 200883C | 0 | TAS | 0 | 1 |  | 660 |  | Process Australia Task | Code: T0100 | PRO | 000H2 |  |  |  |  | M4 | 40 |  |  | APRO | 2022-08-31 | 2022-08-31 | 2022-09-30
200883C-000-TAS-000-0001 | [T] | 200883C | 0 | TAS | 0 | 1 |  | 660 |  | Process Australia Task | Code: T0100 | PRO | 000H2 |  |  |  |  | M5 | 50 |  |  | APRO | 2022-09-30 | 2022-09-30 | 2022-10-31
200883C-000-TAS-000-0001 | [T] | 200883C | 0 | TAS | 0 | 1 |  | 660 |  | Process Australia Task | Code: T0100 | PRO | 000H2 |  |  |  |  | M6 | 60 |  |  | APRO | 2022-10-31 | 2022-10-31 | 2022-11-30
200883C-000-TAS-000-0001 | [T] | 200883C | 0 | TAS | 0 | 1 |  | 660 |  | Process Australia Task | Code: T0100 | PRO | 000H2 |  |  |  |  | M7 | 70 |  |  | APRO | 2022-11-30 | 2022-11-30 | 2022-12-30
200883C-000-TAS-000-0001 | [T] | 200883C | 0 | TAS | 0 | 1 |  | 660 |  | Process Australia Task | Code: T0100 | PRO | 000H2 |  |  |  |  | M8 | 80 |  |  | APRO | 2022-12-31 | 2022-12-31 | 2023-01-31
200883C-000-TAS-000-0001 | [T] | 200883C | 0 | TAS | 0 | 1 |  | 660 |  | Process Australia Task | Code: T0100 | PRO | 000H2 |  |  |  |  | M9 | 90 |  |  | APRO | 2023-01-31 | 2023-01-31 | 2023-02-28
200883C-000-TAS-000-0001 | [T] | 200883C | 0 | TAS | 0 | 1 |  | 660 |  | Process Australia Task | Code: T0100 | PRO | 000H2 |  |  |  |  | FIN | 100 |  |  | APRO | 2023-02-28 | 2023-02-28 | 2023-03-28
200883C-000-TAS-0000-1001 | [T] | 200883C | 0 | TAS | 0 | 1001 |  | 991 |  | Yuri Phase 0-Stress Analysis | Code: T0100 | PIP | 000H2 |  |  |  |  | STA | 5 |  |  | MPIP | 2022-05-15 | 2022-05-15 | 2022-05-15 | 2022-05-15
200883C-000-TAS-0000-1001 | [T] | 200883C | 0 | TAS | 0 | 1001 |  | 991 |  | Yuri Phase 0-Stress Analysis | Code: T0100 | PIP | 000H2 |  |  |  |  | M1 | 10 |  |  | MPIP | 2022-06-26 | 2022-06-26 | 2022-06-26 | 2022-06-26
200883C-000-TAS-0000-1001 | [T] | 200883C | 0 | TAS | 0 | 1001 |  | 991 |  | Yuri Phase 0-Stress Analysis | Code: T0100 | PIP | 000H2 |  |  |  |  | M2 | 20 |  |  | MPIP | 2022-07-24 | 2022-07-24 | 2022-07-25 | 2022-07-25
200883C-000-TAS-0000-1001 | [T] | 200883C | 0 | TAS | 0 | 1001 |  | 991 |  | Yuri Phase 0-Stress Analysis | Code: T0100 | PIP | 000H2 |  |  |  |  | M3 | 30 |  |  | MPIP | 2022-08-21 | 2022-08-21 | 2022-08-21 | 2022-08-21
200883C-000-TAS-0000-1001 | [T] | 200883C | 0 | TAS | 0 | 1001 |  | 991 |  | Yuri Phase 0-Stress Analysis | Code: T0100 | PIP | 000H2 |  |  |  |  | M4 | 40 |  |  | MPIP | 2022-10-14 | 2022-10-14 | 2022-10-14
200883C-000-TAS-0000-1001 | [T] | 200883C | 0 | TAS | 0 | 1001 |  | 991 |  | Yuri Phase 0-Stress Analysis | Code: T0100 | PIP | 000H2 |  |  |  |  | M5 | 50 |  |  | MPIP | 2022-11-11 | 2022-11-11 | 2022-11-11
200883C-000-TAS-0000-1001 | [T] | 200883C | 0 | TAS | 0 | 1001 |  | 991 |  | Yuri Phase 0-Stress Analysis | Code: T0100 | PIP | 000H2 |  |  |  |  | M6 | 60 |  |  | MPIP | 2022-12-09 | 2022-12-09 | 2022-12-09
200883C-000-TAS-0000-1001 | [T] | 200883C | 0 | TAS | 0 | 1001 |  | 991 |  | Yuri Phase 0-Stress Analysis | Code: T0100 | PIP | 000H2 |  |  |  |  | M7 | 70 |  |  | MPIP | 2023-01-06 | 2023-01-06 | 2023-01-06
200883C-000-TAS-0000-1001 | [T] | 200883C | 0 | TAS | 0 | 1001 |  | 991 |  | Yuri Phase 0-Stress Analysis | Code: T0100 | PIP | 000H2 |  |  |  |  | M8 | 80 |  |  | MPIP | 2023-02-03 | 2023-02-03 | 2023-02-03
200883C-000-TAS-0000-1001 | [T] | 200883C | 0 | TAS | 0 | 1001 |  | 991 |  | Yuri Phase 0-Stress Analysis | Code: T0100 | PIP | 000H2 |  |  |  |  | M9 | 90 |  |  | MPIP | 2023-03-03 | 2023-03-03 | 2023-03-03
200883C-000-TAS-0000-1001 | [T] | 200883C | 0 | TAS | 0 | 1001 |  | 991 |  | Yuri Phase 0-Stress Analysis | Code: T0100 | PIP | 000H2 |  |  |  |  | FIN | 100 |  |  | MPIP | 2023-03-31 | 2023-03-31 | 2023-03-31
200883C-000-TAS-0000-1002 | [T] | 200883C | 0 | TAS | 0 | 1002 |  | 540 |  | Yuri Phase 0-SPMAT creation and updation | Code: T0100 | PIP | 000H2 |  |  |  |  | STA | 5 |  |  | MPIP | 2022-05-15 | 2022-05-15 | 2022-05-15 | 2022-05-15
200883C-000-TAS-0000-1002 | [T] | 200883C | 0 | TAS | 0 | 1002 |  | 540 |  | Yuri Phase 0-SPMAT creation and updation | Code: T0100 | PIP | 000H2 |  |  |  |  | M1 | 10 |  |  | MPIP | 2022-06-26 | 2022-06-26 | 2022-06-26 | 2022-06-26
200883C-000-TAS-0000-1002 | [T] | 200883C | 0 | TAS | 0 | 1002 |  | 540 |  | Yuri Phase 0-SPMAT creation and updation | Code: T0100 | PIP | 000H2 |  |  |  |  | M2 | 20 |  |  | MPIP | 2022-07-24 | 2022-07-24 | 2022-07-25 | 2022-07-25
200883C-000-TAS-0000-1002 | [T] | 200883C | 0 | TAS | 0 | 1002 |  | 540 |  | Yuri Phase 0-SPMAT creation and updation | Code: T0100 | PIP | 000H2 |  |  |  |  | M3 | 30 |  |  | MPIP | 2022-08-21 | 2022-08-21 | 2022-08-21 | 2022-08-21
200883C-000-TAS-0000-1002 | [T] | 200883C | 0 | TAS | 0 | 1002 |  | 540 |  | Yuri Phase 0-SPMAT creation and updation | Code: T0100 | PIP | 000H2 |  |  |  |  | M4 | 40 |  |  | MPIP | 2022-10-14 | 2022-10-14 | 2022-10-14
200883C-000-TAS-0000-1002 | [T] | 200883C | 0 | TAS | 0 | 1002 |  | 540 |  | Yuri Phase 0-SPMAT creation and updation | Code: T0100 | PIP | 000H2 |  |  |  |  | M5 | 50 |  |  | MPIP | 2022-11-11 | 2022-11-11 | 2022-11-11
200883C-000-TAS-0000-1002 | [T] | 200883C | 0 | TAS | 0 | 1002 |  | 540 |  | Yuri Phase 0-SPMAT creation and updation | Code: T0100 | PIP | 000H2 |  |  |  |  | M6 | 60 |  |  | MPIP | 2022-12-09 | 2022-12-09 | 2022-12-09
200883C-000-TAS-0000-1002 | [T] | 200883C | 0 | TAS | 0 | 1002 |  | 540 |  | Yuri Phase 0-SPMAT creation and updation | Code: T0100 | PIP | 000H2 |  |  |  |  | M7 | 70 |  |  | MPIP | 2023-01-06 | 2023-01-06 | 2023-01-06
200883C-000-TAS-0000-1002 | [T] | 200883C | 0 | TAS | 0 | 1002 |  | 540 |  | Yuri Phase 0-SPMAT creation and updation | Code: T0100 | PIP | 000H2 |  |  |  |  | M8 | 80 |  |  | MPIP | 2023-02-03 | 2023-02-03 | 2023-02-03
200883C-000-TAS-0000-1002 | [T] | 200883C | 0 | TAS | 0 | 1002 |  | 540 |  | Yuri Phase 0-SPMAT creation and updation | Code: T0100 | PIP | 000H2 |  |  |  |  | M9 | 90 |  |  | MPIP | 2023-03-03 | 2023-03-03 | 2023-03-03
200883C-000-TAS-0000-1002 | [T] | 200883C | 0 | TAS | 0 | 1002 |  | 540 |  | Yuri Phase 0-SPMAT creation and updation | Code: T0100 | PIP | 000H2 |  |  |  |  | FIN | 100 |  |  | MPIP | 2023-03-31 | 2023-03-31 | 2023-03-31
200883C-000-TAS-0000-1003 | [T] | 200883C | 0 | TAS | 0 | 1003 |  | 270 |  | Yuri Phase 0-Vendor document review/IDC | Code: T0100 | PIP | 000H2 |  |  |  |  | STA | 5 |  |  | MPIP | 2022-05-15 | 2022-05-15 | 2022-05-15 | 2022-05-15
200883C-000-TAS-0000-1003 | [T] | 200883C | 0 | TAS | 0 | 1003 |  | 270 |  | Yuri Phase 0-Vendor document review/IDC | Code: T0100 | PIP | 000H2 |  |  |  |  | M1 | 10 |  |  | MPIP | 2022-06-26 | 2022-06-26 | 2022-06-26 | 2022-06-26
200883C-000-TAS-0000-1003 | [T] | 200883C | 0 | TAS | 0 | 1003 |  | 270 |  | Yuri Phase 0-Vendor document review/IDC | Code: T0100 | PIP | 000H2 |  |  |  |  | M2 | 20 |  |  | MPIP | 2022-07-24 | 2022-07-24 | 2022-07-25 | 2022-07-25
200883C-000-TAS-0000-1003 | [T] | 200883C | 0 | TAS | 0 | 1003 |  | 270 |  | Yuri Phase 0-Vendor document review/IDC | Code: T0100 | PIP | 000H2 |  |  |  |  | M3 | 30 |  |  | MPIP | 2022-08-21 | 2022-08-21 | 2022-08-21 | 2022-08-21
200883C-000-TAS-0000-1003 | [T] | 200883C | 0 | TAS | 0 | 1003 |  | 270 |  | Yuri Phase 0-Vendor document review/IDC | Code: T0100 | PIP | 000H2 |  |  |  |  | M4 | 40 |  |  | MPIP | 2022-10-14 | 2022-10-14 | 2022-10-14
200883C-000-TAS-0000-1003 | [T] | 200883C | 0 | TAS | 0 | 1003 |  | 270 |  | Yuri Phase 0-Vendor document review/IDC | Code: T0100 | PIP | 000H2 |  |  |  |  | M5 | 50 |  |  | MPIP | 2022-11-11 | 2022-11-11 | 2022-11-11
200883C-000-TAS-0000-1003 | [T] | 200883C | 0 | TAS | 0 | 1003 |  | 270 |  | Yuri Phase 0-Vendor document review/IDC | Code: T0100 | PIP | 000H2 |  |  |  |  | M6 | 60 |  |  | MPIP | 2022-12-09 | 2022-12-09 | 2022-12-09
200883C-000-TAS-0000-1003 | [T] | 200883C | 0 | TAS | 0 | 1003 |  | 270 |  | Yuri Phase 0-Vendor document review/IDC | Code: T0100 | PIP | 000H2 |  |  |  |  | M7 | 70 |  |  | MPIP | 2023-01-06 | 2023-01-06 | 2023-01-06
200883C-000-TAS-0000-1003 | [T] | 200883C | 0 | TAS | 0 | 1003 |  | 270 |  | Yuri Phase 0-Vendor document review/IDC | Code: T0100 | PIP | 000H2 |  |  |  |  | M8 | 80 |  |  | MPIP | 2023-02-03 | 2023-02-03 | 2023-02-03
200883C-000-TAS-0000-1003 | [T] | 200883C | 0 | TAS | 0 | 1003 |  | 270 |  | Yuri Phase 0-Vendor document review/IDC | Code: T0100 | PIP | 000H2 |  |  |  |  | M9 | 90 |  |  | MPIP | 2023-03-03 | 2023-03-03 | 2023-03-03
200883C-000-TAS-0000-1003 | [T] | 200883C | 0 | TAS | 0 | 1003 |  | 270 |  | Yuri Phase 0-Vendor document review/IDC | Code: T0100 | PIP | 000H2 |  |  |  |  | FIN | 100 |  |  | MPIP | 2023-03-31 | 2023-03-31 | 2023-03-31
200883C-000-TAS-0000-1004 | [T] | 200883C | 0 | TAS | 0 | 1004 |  | 968 |  | Yuri Phase 0-LB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | STA | 5 |  |  | MPIP | 2022-05-15 | 2022-05-15 | 2022-05-15 | 2022-05-15
200883C-000-TAS-0000-1004 | [T] | 200883C | 0 | TAS | 0 | 1004 |  | 968 |  | Yuri Phase 0-LB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M1 | 10 |  |  | MPIP | 2022-06-26 | 2022-06-26 | 2022-06-26 | 2022-06-26
200883C-000-TAS-0000-1004 | [T] | 200883C | 0 | TAS | 0 | 1004 |  | 968 |  | Yuri Phase 0-LB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M2 | 20 |  |  | MPIP | 2022-07-24 | 2022-07-24 | 2022-07-23 | 2022-07-23
200883C-000-TAS-0000-1004 | [T] | 200883C | 0 | TAS | 0 | 1004 |  | 968 |  | Yuri Phase 0-LB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M3 | 30 |  |  | MPIP | 2022-08-21 | 2022-08-21 | 2022-07-29 | 2022-07-29
200883C-000-TAS-0000-1004 | [T] | 200883C | 0 | TAS | 0 | 1004 |  | 968 |  | Yuri Phase 0-LB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M4 | 40 |  |  | MPIP | 2022-10-14 | 2022-10-14 | 2022-08-26 | 2022-08-26
200883C-000-TAS-0000-1004 | [T] | 200883C | 0 | TAS | 0 | 1004 |  | 968 |  | Yuri Phase 0-LB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M5 | 50 |  |  | MPIP | 2022-11-11 | 2022-11-11 | 2022-11-11
200883C-000-TAS-0000-1004 | [T] | 200883C | 0 | TAS | 0 | 1004 |  | 968 |  | Yuri Phase 0-LB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M6 | 60 |  |  | MPIP | 2022-12-09 | 2022-12-09 | 2022-12-09
200883C-000-TAS-0000-1004 | [T] | 200883C | 0 | TAS | 0 | 1004 |  | 968 |  | Yuri Phase 0-LB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M7 | 70 |  |  | MPIP | 2023-01-06 | 2023-01-06 | 2023-01-06
200883C-000-TAS-0000-1004 | [T] | 200883C | 0 | TAS | 0 | 1004 |  | 968 |  | Yuri Phase 0-LB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M8 | 80 |  |  | MPIP | 2023-02-03 | 2023-02-03 | 2023-02-03
200883C-000-TAS-0000-1004 | [T] | 200883C | 0 | TAS | 0 | 1004 |  | 968 |  | Yuri Phase 0-LB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M9 | 90 |  |  | MPIP | 2023-03-03 | 2023-03-03 | 2023-03-03
200883C-000-TAS-0000-1004 | [T] | 200883C | 0 | TAS | 0 | 1004 |  | 968 |  | Yuri Phase 0-LB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | FIN | 100 |  |  | MPIP | 2023-03-31 | 2023-03-31 | 2023-03-31
200883C-000-TAS-0000-1005 | [T] | 200883C | 0 | TAS | 0 | 1005 |  | 957 |  | Yuri Phase 0-SB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | STA | 5 |  |  | MPIP | 2022-05-15 | 2022-05-15 | 2022-05-15 | 2022-05-15
200883C-000-TAS-0000-1005 | [T] | 200883C | 0 | TAS | 0 | 1005 |  | 957 |  | Yuri Phase 0-SB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M1 | 10 |  |  | MPIP | 2022-06-26 | 2022-06-26 | 2022-06-26 | 2022-06-26
200883C-000-TAS-0000-1005 | [T] | 200883C | 0 | TAS | 0 | 1005 |  | 957 |  | Yuri Phase 0-SB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M2 | 20 |  |  | MPIP | 2022-07-24 | 2022-07-24 | 2022-08-12 | 2022-08-12
200883C-000-TAS-0000-1005 | [T] | 200883C | 0 | TAS | 0 | 1005 |  | 957 |  | Yuri Phase 0-SB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M3 | 30 |  |  | MPIP | 2022-08-21 | 2022-08-21 | 2022-08-21
200883C-000-TAS-0000-1005 | [T] | 200883C | 0 | TAS | 0 | 1005 |  | 957 |  | Yuri Phase 0-SB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M4 | 40 |  |  | MPIP | 2022-10-14 | 2022-10-14 | 2022-10-14
200883C-000-TAS-0000-1005 | [T] | 200883C | 0 | TAS | 0 | 1005 |  | 957 |  | Yuri Phase 0-SB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M5 | 50 |  |  | MPIP | 2022-11-11 | 2022-11-11 | 2022-11-11
200883C-000-TAS-0000-1005 | [T] | 200883C | 0 | TAS | 0 | 1005 |  | 957 |  | Yuri Phase 0-SB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M6 | 60 |  |  | MPIP | 2022-12-09 | 2022-12-09 | 2022-12-09
200883C-000-TAS-0000-1005 | [T] | 200883C | 0 | TAS | 0 | 1005 |  | 957 |  | Yuri Phase 0-SB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M7 | 70 |  |  | MPIP | 2023-01-06 | 2023-01-06 | 2023-01-06
200883C-000-TAS-0000-1005 | [T] | 200883C | 0 | TAS | 0 | 1005 |  | 957 |  | Yuri Phase 0-SB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M8 | 80 |  |  | MPIP | 2023-02-03 | 2023-02-03 | 2023-02-03
200883C-000-TAS-0000-1005 | [T] | 200883C | 0 | TAS | 0 | 1005 |  | 957 |  | Yuri Phase 0-SB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M9 | 90 |  |  | MPIP | 2023-03-03 | 2023-03-03 | 2023-03-03
200883C-000-TAS-0000-1005 | [T] | 200883C | 0 | TAS | 0 | 1005 |  | 957 |  | Yuri Phase 0-SB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | FIN | 100 |  |  | MPIP | 2023-03-31 | 2023-03-31 | 2023-03-31
200883C-000-TAS-0000-1006 | [T] | 200883C | 0 | TAS | 0 | 1006 |  | 450 |  | Yuri Phase 0-Equipment Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | STA | 5 |  |  | MPIP | 2022-05-15 | 2022-05-15 | 2022-05-15 | 2022-05-15
200883C-000-TAS-0000-1006 | [T] | 200883C | 0 | TAS | 0 | 1006 |  | 450 |  | Yuri Phase 0-Equipment Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M1 | 10 |  |  | MPIP | 2022-06-26 | 2022-06-26 | 2022-06-26 | 2022-06-26
200883C-000-TAS-0000-1006 | [T] | 200883C | 0 | TAS | 0 | 1006 |  | 450 |  | Yuri Phase 0-Equipment Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M2 | 20 |  |  | MPIP | 2022-07-24 | 2022-07-24 | 2022-07-23 | 2022-07-23
200883C-000-TAS-0000-1006 | [T] | 200883C | 0 | TAS | 0 | 1006 |  | 450 |  | Yuri Phase 0-Equipment Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M3 | 30 |  |  | MPIP | 2022-08-21 | 2022-08-21 | 2022-07-29 | 2022-07-29
200883C-000-TAS-0000-1006 | [T] | 200883C | 0 | TAS | 0 | 1006 |  | 450 |  | Yuri Phase 0-Equipment Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M4 | 40 |  |  | MPIP | 2022-10-14 | 2022-10-14 | 2022-10-14
200883C-000-TAS-0000-1006 | [T] | 200883C | 0 | TAS | 0 | 1006 |  | 450 |  | Yuri Phase 0-Equipment Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M5 | 50 |  |  | MPIP | 2022-11-11 | 2022-11-11 | 2022-11-11
200883C-000-TAS-0000-1006 | [T] | 200883C | 0 | TAS | 0 | 1006 |  | 450 |  | Yuri Phase 0-Equipment Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M6 | 60 |  |  | MPIP | 2022-12-09 | 2022-12-09 | 2022-12-09
200883C-000-TAS-0000-1006 | [T] | 200883C | 0 | TAS | 0 | 1006 |  | 450 |  | Yuri Phase 0-Equipment Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M7 | 70 |  |  | MPIP | 2023-01-06 | 2023-01-06 | 2023-01-06
200883C-000-TAS-0000-1006 | [T] | 200883C | 0 | TAS | 0 | 1006 |  | 450 |  | Yuri Phase 0-Equipment Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M8 | 80 |  |  | MPIP | 2023-02-03 | 2023-02-03 | 2023-02-03
200883C-000-TAS-0000-1006 | [T] | 200883C | 0 | TAS | 0 | 1006 |  | 450 |  | Yuri Phase 0-Equipment Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M9 | 90 |  |  | MPIP | 2023-03-03 | 2023-03-03 | 2023-03-03
200883C-000-TAS-0000-1006 | [T] | 200883C | 0 | TAS | 0 | 1006 |  | 450 |  | Yuri Phase 0-Equipment Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | FIN | 100 |  |  | MPIP | 2023-03-31 | 2023-03-31 | 2023-03-31
200883C-000-TAS-0000-1007 | [T] | 200883C | 0 | TAS | 0 | 1007 |  | 180 |  | Yuri Phase 0-3D Model Review | Code: T0200 | PIP | 000H2 |  |  |  |  | STA | 5 |  |  | MPIP | 2022-08-08 | 2022-08-08 | 2022-07-25 | 2022-07-25
200883C-000-TAS-0000-1007 | [T] | 200883C | 0 | TAS | 0 | 1007 |  | 180 |  | Yuri Phase 0-3D Model Review | Code: T0200 | PIP | 000H2 |  |  |  |  | M1 | 30 |  |  | MPIP | 2022-08-22 | 2022-08-22 | 2022-07-28 | 2022-07-28
200883C-000-TAS-0000-1007 | [T] | 200883C | 0 | TAS | 0 | 1007 |  | 180 |  | Yuri Phase 0-3D Model Review | Code: T0200 | PIP | 000H2 |  |  |  |  | M2 | 60 |  |  | MPIP | 2022-11-30 | 2022-11-30 | 2022-11-30
200883C-000-TAS-0000-1007 | [T] | 200883C | 0 | TAS | 0 | 1007 |  | 180 |  | Yuri Phase 0-3D Model Review | Code: T0200 | PIP | 000H2 |  |  |  |  | M3 | 100 |  |  | MPIP | 2023-02-09 | 2023-02-09 | 2023-02-09
200883C-000-TAS-0000-1008 | [T] | 200883C | 0 | TAS | 0 | 1008 |  | 183 |  | 3D Modelling | Code: T0100 | ELE | 000H2 |  |  |  |  | STA | 5 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-06-15 | 2022-06-15
200883C-000-TAS-0000-1008 | [T] | 200883C | 0 | TAS | 0 | 1008 |  | 183 |  | 3D Modelling | Code: T0100 | ELE | 000H2 |  |  |  |  | M1 | 10 |  |  | MELE | 2022-07-13 | 2022-07-13 | 2022-07-13 | 2022-07-13
200883C-000-TAS-0000-1008 | [T] | 200883C | 0 | TAS | 0 | 1008 |  | 183 |  | 3D Modelling | Code: T0100 | ELE | 000H2 |  |  |  |  | M2 | 20 |  |  | MELE | 2022-08-10 | 2022-08-10 | 2022-08-10 | 2022-08-10
200883C-000-TAS-0000-1008 | [T] | 200883C | 0 | TAS | 0 | 1008 |  | 183 |  | 3D Modelling | Code: T0100 | ELE | 000H2 |  |  |  |  | M3 | 30 |  |  | MELE | 2022-09-07 | 2022-09-07 | 2022-09-07
200883C-000-TAS-0000-1008 | [T] | 200883C | 0 | TAS | 0 | 1008 |  | 183 |  | 3D Modelling | Code: T0100 | ELE | 000H2 |  |  |  |  | M4 | 40 |  |  | MELE | 2022-10-05 | 2022-10-05 | 2022-10-05
200883C-000-TAS-0000-1008 | [T] | 200883C | 0 | TAS | 0 | 1008 |  | 183 |  | 3D Modelling | Code: T0100 | ELE | 000H2 |  |  |  |  | M5 | 50 |  |  | MELE | 2022-11-02 | 2022-11-02 | 2022-11-02
200883C-000-TAS-0000-1008 | [T] | 200883C | 0 | TAS | 0 | 1008 |  | 183 |  | 3D Modelling | Code: T0100 | ELE | 000H2 |  |  |  |  | M6 | 60 |  |  | MELE | 2022-11-30 | 2022-11-30 | 2022-11-30
200883C-000-TAS-0000-1008 | [T] | 200883C | 0 | TAS | 0 | 1008 |  | 183 |  | 3D Modelling | Code: T0100 | ELE | 000H2 |  |  |  |  | M7 | 70 |  |  | MELE | 2022-12-28 | 2022-12-28 | 2022-12-28
200883C-000-TAS-0000-1008 | [T] | 200883C | 0 | TAS | 0 | 1008 |  | 183 |  | 3D Modelling | Code: T0100 | ELE | 000H2 |  |  |  |  | M8 | 80 |  |  | MELE | 2023-01-25 | 2023-01-25 | 2023-01-25
200883C-000-TAS-0000-1008 | [T] | 200883C | 0 | TAS | 0 | 1008 |  | 183 |  | 3D Modelling | Code: T0100 | ELE | 000H2 |  |  |  |  | M9 | 90 |  |  | MELE | 2023-02-22 | 2023-02-22 | 2023-02-22
200883C-000-TAS-0000-1008 | [T] | 200883C | 0 | TAS | 0 | 1008 |  | 183 |  | 3D Modelling | Code: T0100 | ELE | 000H2 |  |  |  |  | FIN | 100 |  |  | MELE | 2023-03-22 | 2023-03-22 | 2023-03-22
200883C-000-TAS-0000-1009 | [T] | 200883C | 0 | TAS | 0 | 1009 |  | 142 |  | Mechanical Package Review | Code: T0100 | ELE | 000H2 |  |  |  |  | STA | 5 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-06-15 | 2022-06-15
200883C-000-TAS-0000-1009 | [T] | 200883C | 0 | TAS | 0 | 1009 |  | 142 |  | Mechanical Package Review | Code: T0100 | ELE | 000H2 |  |  |  |  | M1 | 10 |  |  | MELE | 2022-07-13 | 2022-07-13 | 2022-07-13 | 2022-07-13
200883C-000-TAS-0000-1009 | [T] | 200883C | 0 | TAS | 0 | 1009 |  | 142 |  | Mechanical Package Review | Code: T0100 | ELE | 000H2 |  |  |  |  | M2 | 20 |  |  | MELE | 2022-08-10 | 2022-08-10 | 2022-08-10 | 2022-08-10
200883C-000-TAS-0000-1009 | [T] | 200883C | 0 | TAS | 0 | 1009 |  | 142 |  | Mechanical Package Review | Code: T0100 | ELE | 000H2 |  |  |  |  | M3 | 30 |  |  | MELE | 2022-09-07 | 2022-09-07 | 2022-09-07
200883C-000-TAS-0000-1009 | [T] | 200883C | 0 | TAS | 0 | 1009 |  | 142 |  | Mechanical Package Review | Code: T0100 | ELE | 000H2 |  |  |  |  | M4 | 40 |  |  | MELE | 2022-10-05 | 2022-10-05 | 2022-10-05
200883C-000-TAS-0000-1009 | [T] | 200883C | 0 | TAS | 0 | 1009 |  | 142 |  | Mechanical Package Review | Code: T0100 | ELE | 000H2 |  |  |  |  | M5 | 50 |  |  | MELE | 2022-11-02 | 2022-11-02 | 2022-11-02
200883C-000-TAS-0000-1009 | [T] | 200883C | 0 | TAS | 0 | 1009 |  | 142 |  | Mechanical Package Review | Code: T0100 | ELE | 000H2 |  |  |  |  | M6 | 60 |  |  | MELE | 2022-11-30 | 2022-11-30 | 2022-11-30
200883C-000-TAS-0000-1009 | [T] | 200883C | 0 | TAS | 0 | 1009 |  | 142 |  | Mechanical Package Review | Code: T0100 | ELE | 000H2 |  |  |  |  | M7 | 70 |  |  | MELE | 2022-12-28 | 2022-12-28 | 2022-12-28
200883C-000-TAS-0000-1009 | [T] | 200883C | 0 | TAS | 0 | 1009 |  | 142 |  | Mechanical Package Review | Code: T0100 | ELE | 000H2 |  |  |  |  | M8 | 80 |  |  | MELE | 2023-01-25 | 2023-01-25 | 2023-01-25
200883C-000-TAS-0000-1009 | [T] | 200883C | 0 | TAS | 0 | 1009 |  | 142 |  | Mechanical Package Review | Code: T0100 | ELE | 000H2 |  |  |  |  | M9 | 90 |  |  | MELE | 2023-02-22 | 2023-02-22 | 2023-02-22
200883C-000-TAS-0000-1009 | [T] | 200883C | 0 | TAS | 0 | 1009 |  | 142 |  | Mechanical Package Review | Code: T0100 | ELE | 000H2 |  |  |  |  | FIN | 100 |  |  | MELE | 2023-03-22 | 2023-03-22 | 2023-03-22
200883C-000-TAS-0000-1010 | [T] | 200883C | 0 | TAS | 0 | 1010 |  | 164 |  | 3D Modelling | Code: T0100 | INS | 000H2 |  |  |  |  | STA | 5 |  |  | MINS | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-000-TAS-0000-1010 | [T] | 200883C | 0 | TAS | 0 | 1010 |  | 164 |  | 3D Modelling | Code: T0100 | INS | 000H2 |  |  |  |  | M1 | 10 |  |  | MINS | 2022-06-27 | 2022-06-27 | 2022-06-26 | 2022-06-26
200883C-000-TAS-0000-1010 | [T] | 200883C | 0 | TAS | 0 | 1010 |  | 164 |  | 3D Modelling | Code: T0100 | INS | 000H2 |  |  |  |  | M2 | 20 |  |  | MINS | 2022-07-25 | 2022-07-25 | 2022-07-25 | 2022-07-25
200883C-000-TAS-0000-1010 | [T] | 200883C | 0 | TAS | 0 | 1010 |  | 164 |  | 3D Modelling | Code: T0100 | INS | 000H2 |  |  |  |  | M3 | 30 |  |  | MINS | 2022-08-22 | 2022-08-22 | 2022-08-22 | 2022-08-22
200883C-000-TAS-0000-1010 | [T] | 200883C | 0 | TAS | 0 | 1010 |  | 164 |  | 3D Modelling | Code: T0100 | INS | 000H2 |  |  |  |  | M4 | 40 |  |  | MINS | 2022-09-19 | 2022-09-19 | 2022-09-19
200883C-000-TAS-0000-1010 | [T] | 200883C | 0 | TAS | 0 | 1010 |  | 164 |  | 3D Modelling | Code: T0100 | INS | 000H2 |  |  |  |  | M5 | 50 |  |  | MINS | 2022-10-17 | 2022-10-17 | 2022-10-17
200883C-000-TAS-0000-1010 | [T] | 200883C | 0 | TAS | 0 | 1010 |  | 164 |  | 3D Modelling | Code: T0100 | INS | 000H2 |  |  |  |  | M6 | 60 |  |  | MINS | 2022-11-14 | 2022-11-14 | 2022-11-14
200883C-000-TAS-0000-1010 | [T] | 200883C | 0 | TAS | 0 | 1010 |  | 164 |  | 3D Modelling | Code: T0100 | INS | 000H2 |  |  |  |  | M7 | 70 |  |  | MINS | 2022-12-12 | 2022-12-12 | 2022-12-12
200883C-000-TAS-0000-1010 | [T] | 200883C | 0 | TAS | 0 | 1010 |  | 164 |  | 3D Modelling | Code: T0100 | INS | 000H2 |  |  |  |  | M8 | 80 |  |  | MINS | 2023-01-09 | 2023-01-09 | 2023-01-09
200883C-000-TAS-0000-1010 | [T] | 200883C | 0 | TAS | 0 | 1010 |  | 164 |  | 3D Modelling | Code: T0100 | INS | 000H2 |  |  |  |  | M9 | 90 |  |  | MINS | 2023-02-06 | 2023-02-06 | 2023-02-06
200883C-000-TAS-0000-1010 | [T] | 200883C | 0 | TAS | 0 | 1010 |  | 164 |  | 3D Modelling | Code: T0100 | INS | 000H2 |  |  |  |  | FIN | 100 |  |  | MINS | 2023-03-06 | 2023-03-06 | 2023-03-06
200883C-000-TAS-0000-1011 | [T] | 200883C | 0 | TAS | 0 | 1011 |  | 164 |  | Mechanical Package Review | Code: T0100 | INS | 000H2 |  |  |  |  | STA | 5 |  |  | MINS | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-000-TAS-0000-1011 | [T] | 200883C | 0 | TAS | 0 | 1011 |  | 164 |  | Mechanical Package Review | Code: T0100 | INS | 000H2 |  |  |  |  | M1 | 10 |  |  | MINS | 2022-06-27 | 2022-06-27 | 2022-06-26 | 2022-06-26
200883C-000-TAS-0000-1011 | [T] | 200883C | 0 | TAS | 0 | 1011 |  | 164 |  | Mechanical Package Review | Code: T0100 | INS | 000H2 |  |  |  |  | M2 | 20 |  |  | MINS | 2022-07-25 | 2022-07-25 | 2022-07-25 | 2022-07-25
200883C-000-TAS-0000-1011 | [T] | 200883C | 0 | TAS | 0 | 1011 |  | 164 |  | Mechanical Package Review | Code: T0100 | INS | 000H2 |  |  |  |  | M3 | 30 |  |  | MINS | 2022-08-22 | 2022-08-22 | 2022-08-22 | 2022-08-22
200883C-000-TAS-0000-1011 | [T] | 200883C | 0 | TAS | 0 | 1011 |  | 164 |  | Mechanical Package Review | Code: T0100 | INS | 000H2 |  |  |  |  | M4 | 40 |  |  | MINS | 2022-09-19 | 2022-09-19 | 2022-09-19
200883C-000-TAS-0000-1011 | [T] | 200883C | 0 | TAS | 0 | 1011 |  | 164 |  | Mechanical Package Review | Code: T0100 | INS | 000H2 |  |  |  |  | M5 | 50 |  |  | MINS | 2022-10-17 | 2022-10-17 | 2022-10-17
200883C-000-TAS-0000-1011 | [T] | 200883C | 0 | TAS | 0 | 1011 |  | 164 |  | Mechanical Package Review | Code: T0100 | INS | 000H2 |  |  |  |  | M6 | 60 |  |  | MINS | 2022-11-14 | 2022-11-14 | 2022-11-14
200883C-000-TAS-0000-1011 | [T] | 200883C | 0 | TAS | 0 | 1011 |  | 164 |  | Mechanical Package Review | Code: T0100 | INS | 000H2 |  |  |  |  | M7 | 70 |  |  | MINS | 2022-12-12 | 2022-12-12 | 2022-12-12
200883C-000-TAS-0000-1011 | [T] | 200883C | 0 | TAS | 0 | 1011 |  | 164 |  | Mechanical Package Review | Code: T0100 | INS | 000H2 |  |  |  |  | M8 | 80 |  |  | MINS | 2023-01-09 | 2023-01-09 | 2023-01-09
200883C-000-TAS-0000-1011 | [T] | 200883C | 0 | TAS | 0 | 1011 |  | 164 |  | Mechanical Package Review | Code: T0100 | INS | 000H2 |  |  |  |  | M9 | 90 |  |  | MINS | 2023-02-06 | 2023-02-06 | 2023-02-06
200883C-000-TAS-0000-1011 | [T] | 200883C | 0 | TAS | 0 | 1011 |  | 164 |  | Mechanical Package Review | Code: T0100 | INS | 000H2 |  |  |  |  | FIN | 100 |  |  | MINS | 2023-03-06 | 2023-03-06 | 2023-03-06
200883C-000-TBT-1511-1000 | [D] | 200883C | 0 | TBT | 1511 | 1000 |  | 88 |  | Yuri Phase 0 - Technical Bid Tabulation For Integrated Control System | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | AINS | 2022-09-08 | 2022-09-08 | 2022-09-08
200883C-000-TBT-1511-1000 | [D] | 200883C | 0 | TBT | 1511 | 1000 |  | 88 |  | Yuri Phase 0 - Technical Bid Tabulation For Integrated Control System | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | AINS | 2022-10-08 | 2022-10-08 | 2022-10-08
200883C-000-TBT-1511-1000 | [D] | 200883C | 0 | TBT | 1511 | 1000 |  | 88 |  | Yuri Phase 0 - Technical Bid Tabulation For Integrated Control System | Code: E0303 | INS | 000H2 |  |  |  |  | IFC | 100 |  |  | AINS | 2022-10-31 | 2022-10-31 | 2022-10-31
200883C-000-TBT-1531-4000 | [D] | 200883C | 0 | TBT | 1531 | 4000 |  | 32 |  | Yuri Phase 0 - Technical Bid Tabulation for CCTV | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-12-24 | 2022-12-24 | 2022-12-24
200883C-000-TBT-1531-4000 | [D] | 200883C | 0 | TBT | 1531 | 4000 |  | 32 |  | Yuri Phase 0 - Technical Bid Tabulation for CCTV | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2023-01-21 | 2023-01-21 | 2023-01-21
200883C-000-TBT-1533-4000 | [D] | 200883C | 0 | TBT | 1533 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Pressure Gauges | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-12 | 2022-08-12 | 2022-08-08 | 2022-08-08
200883C-000-TBT-1533-4000 | [D] | 200883C | 0 | TBT | 1533 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Pressure Gauges | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-09 | 2022-09-09 | 2022-09-09
200883C-000-TBT-1541-4000 | [D] | 200883C | 0 | TBT | 1541 | 4000 |  | 38 |  | Yuri Phase 0 - Technical Bid Tabulation For Control Valves | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-09-05 | 2022-09-05 | 2022-09-05
200883C-000-TBT-1541-4000 | [D] | 200883C | 0 | TBT | 1541 | 4000 |  | 38 |  | Yuri Phase 0 - Technical Bid Tabulation For Control Valves | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-10-03 | 2022-10-03 | 2022-10-03
200883C-000-TBT-1543-4000 | [D] | 200883C | 0 | TBT | 1543 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For On - Off Valves | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-12 | 2022-08-12 | 2022-08-12
200883C-000-TBT-1543-4000 | [D] | 200883C | 0 | TBT | 1543 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For On - Off Valves | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-09 | 2022-09-09 | 2022-09-09
200883C-000-TBT-1545-4000 | [D] | 200883C | 0 | TBT | 1545 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Safety Relief Valves | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-000-TBT-1545-4000 | [D] | 200883C | 0 | TBT | 1545 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Safety Relief Valves | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-10-10 | 2022-10-10 | 2022-10-10
200883C-000-TBT-1546-4000 | [D] | 200883C | 0 | TBT | 1546 | 4000 |  | 32 |  | Yuri Phase 0 - Technical Bid Tabulation For Flow Element | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-000-TBT-1546-4000 | [D] | 200883C | 0 | TBT | 1546 | 4000 |  | 32 |  | Yuri Phase 0 - Technical Bid Tabulation For Flow Element | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-26 | 2022-09-26 | 2022-09-26
200883C-000-TBT-1547-4000 | [D] | 200883C | 0 | TBT | 1547 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Magnetic Flow Meter | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-000-TBT-1547-4000 | [D] | 200883C | 0 | TBT | 1547 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Magnetic Flow Meter | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-26 | 2022-09-26 | 2022-09-26
200883C-000-TBT-1552-4000 | [D] | 200883C | 0 | TBT | 1552 | 4000 |  | 26 |  | Yuri Phase 0 - Technical Bid Tabulation For Magnetic Level Gauge | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-12 | 2022-08-12 | 2022-08-12
200883C-000-TBT-1552-4000 | [D] | 200883C | 0 | TBT | 1552 | 4000 |  | 26 |  | Yuri Phase 0 - Technical Bid Tabulation For Magnetic Level Gauge | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-09 | 2022-09-09 | 2022-09-09
200883C-000-TBT-1552-4001 | [D] | 200883C | 0 | TBT | 1552 | 4001 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Radar Level transmitter | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-28 | 2022-07-28 | 2022-07-28
200883C-000-TBT-1552-4001 | [D] | 200883C | 0 | TBT | 1552 | 4001 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Radar Level transmitter | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-08-25 | 2022-08-25 | 2022-08-25
200883C-000-TBT-1553-4000 | [D] | 200883C | 0 | TBT | 1553 | 4000 |  | 57 |  | Yuri Phase 0 - Technical Bid Tabulation For Electronic Transmitters (Pressure , Flow, level , temperature) | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-12 | 2022-08-12 | 2022-08-12
200883C-000-TBT-1553-4000 | [D] | 200883C | 0 | TBT | 1553 | 4000 |  | 57 |  | Yuri Phase 0 - Technical Bid Tabulation For Electronic Transmitters (Pressure , Flow, level , temperature) | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-09 | 2022-09-09 | 2022-09-09
200883C-000-TBT-1554-4000 | [D] | 200883C | 0 | TBT | 1554 | 4000 |  | 38 |  | Yuri Phase 0 - Technical Bid Tabulation For Temperature Elements and Gauges | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-13 | 2022-08-13 | 2022-08-13
200883C-000-TBT-1554-4000 | [D] | 200883C | 0 | TBT | 1554 | 4000 |  | 38 |  | Yuri Phase 0 - Technical Bid Tabulation For Temperature Elements and Gauges | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-10 | 2022-09-10 | 2022-09-10
200883C-000-TBT-1566-4000 | [D] | 200883C | 0 | TBT | 1566 | 4000 |  | 45 |  | Yuri Phase 0 - Technical Bid Tabulation For FandG Detectors | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-09-22 | 2022-09-22 | 2022-09-22
200883C-000-TBT-1566-4000 | [D] | 200883C | 0 | TBT | 1566 | 4000 |  | 45 |  | Yuri Phase 0 - Technical Bid Tabulation For FandG Detectors | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-10-20 | 2022-10-20 | 2022-10-20
200883C-000-TBT-1572-4000 | [D] | 200883C | 0 | TBT | 1572 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Cable Tray And Accessories | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2023-01-28 | 2023-01-28 | 2022-07-18 | 2022-07-18
200883C-000-TBT-1572-4000 | [D] | 200883C | 0 | TBT | 1572 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Cable Tray And Accessories | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2023-02-25 | 2023-02-25 | 2022-07-18 | 2022-07-18
200883C-000-TBT-1572-4001 | [D] | 200883C | 0 | TBT | 1572 | 4001 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Tube and Fittings | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2023-01-07 | 2023-01-07 | 2023-01-07
200883C-000-TBT-1572-4001 | [D] | 200883C | 0 | TBT | 1572 | 4001 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Tube and Fittings | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2023-02-04 | 2023-02-04 | 2023-02-04
200883C-000-TBT-1574-4000 | [D] | 200883C | 0 | TBT | 1574 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Instrument Cables | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-10-21 | 2022-10-21 | 2022-10-21
200883C-000-TBT-1574-4000 | [D] | 200883C | 0 | TBT | 1574 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Instrument Cables | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-11-18 | 2022-11-18 | 2022-11-18
200883C-000-TBT-1575-4000 | [D] | 200883C | 0 | TBT | 1575 | 4000 |  | 23 |  | Yuri Phase 0 - Technical Bid Tabulation For Junction Boxes and cable glands | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2023-01-07 | 2023-01-07 | 2023-01-07
200883C-000-TBT-1575-4000 | [D] | 200883C | 0 | TBT | 1575 | 4000 |  | 23 |  | Yuri Phase 0 - Technical Bid Tabulation For Junction Boxes and cable glands | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2023-02-04 | 2023-02-04 | 2023-02-04
200883C-000-TBT-1584-4000 | [D] | 200883C | 0 | TBT | 1584 | 4000 |  | 89 |  | Yuri Phase 0 - Technical Bid Tabulation For Hydrogen Quality and Metering System | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-18 | 2022-07-18 | 2022-07-18
200883C-000-TBT-1584-4000 | [D] | 200883C | 0 | TBT | 1584 | 4000 |  | 89 |  | Yuri Phase 0 - Technical Bid Tabulation For Hydrogen Quality and Metering System | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-08-15 | 2022-08-15 | 2022-08-15
200883C-000-TBT-1610-4000 | [D] | 200883C | 0 | TBT | 1610 | 4000 |  | 21 |  | Yuri Phase 0 - Electrical Bulk Materials - Earthing | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-09-29 | 2022-09-29 | 2022-09-29
200883C-000-TBT-1610-4000 | [D] | 200883C | 0 | TBT | 1610 | 4000 |  | 21 |  | Yuri Phase 0 - Electrical Bulk Materials - Earthing | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-10-27 | 2022-10-27 | 2022-10-27
200883C-000-TBT-1620-4000 | [D] | 200883C | 0 | TBT | 1620 | 4000 |  | 21 |  | Yuri Phase 0 - Electrical Bulk Materials - Power | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-09-29 | 2022-09-29 | 2022-09-29
200883C-000-TBT-1620-4000 | [D] | 200883C | 0 | TBT | 1620 | 4000 |  | 21 |  | Yuri Phase 0 - Electrical Bulk Materials - Power | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-10-27 | 2022-10-27 | 2022-10-27
200883C-000-TBT-1621-4000 | [D] | 200883C | 0 | TBT | 1621 | 4000 |  | 21 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Green field | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-11-04 | 2022-11-04 | 2022-11-04
200883C-000-TBT-1621-4000 | [D] | 200883C | 0 | TBT | 1621 | 4000 |  | 21 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Green field | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-12-02 | 2022-12-02 | 2022-12-02
200883C-000-TBT-1623-4000 | [D] | 200883C | 0 | TBT | 1623 | 4000 |  | 21 |  | Yuri Phase 0 - Cable Trays And Ladders - Green field | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2023-01-14 | 2023-01-14 | 2023-01-14
200883C-000-TBT-1623-4000 | [D] | 200883C | 0 | TBT | 1623 | 4000 |  | 21 |  | Yuri Phase 0 - Cable Trays And Ladders - Green field | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2023-02-11 | 2023-02-11 | 2023-02-11
200883C-000-TBT-1630-4000 | [D] | 200883C | 0 | TBT | 1630 | 4000 |  | 21 |  | Yuri Phase 0 - Electrical Bulk Materials - Lighting | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-09-29 | 2022-09-29 | 2022-09-29
200883C-000-TBT-1630-4000 | [D] | 200883C | 0 | TBT | 1630 | 4000 |  | 21 |  | Yuri Phase 0 - Electrical Bulk Materials - Lighting | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-10-27 | 2022-10-27 | 2022-10-27
200883C-000-TBT-1641-4000 | [D] | 200883C | 0 | TBT | 1641 | 4000 |  | 41 |  | Yuri Phase 0 - Transformers | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-12 | 2022-07-12 | 2022-08-15 | 2022-08-15
200883C-000-TBT-1641-4000 | [D] | 200883C | 0 | TBT | 1641 | 4000 |  | 41 |  | Yuri Phase 0 - Transformers | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-08-09 | 2022-08-09 | 2022-09-09
200883C-000-TBT-1641-4001 | [D] | 200883C | 0 | TBT | 1641 | 4001 |  | 41 |  | Yuri Phase 0 - Neutral Earthing Resistor | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-16 | 2022-07-16 | 2022-08-02 | 2022-08-02
200883C-000-TBT-1641-4001 | [D] | 200883C | 0 | TBT | 1641 | 4001 |  | 41 |  | Yuri Phase 0 - Neutral Earthing Resistor | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-08-13 | 2022-08-13 | 2022-08-02 | 2022-08-02
200883C-000-TBT-1652-4000 | [D] | 200883C | 0 | TBT | 1652 | 4000 |  | 41 |  | Yuri Phase 0 - HV Switchgear | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-06 | 2022-07-06 | 2022-07-01 | 2022-07-01
200883C-000-TBT-1652-4000 | [D] | 200883C | 0 | TBT | 1652 | 4000 |  | 41 |  | Yuri Phase 0 - HV Switchgear | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-08-03 | 2022-08-03 | 2022-08-03
200883C-000-TBT-1652-4001 | [D] | 200883C | 0 | TBT | 1652 | 4001 |  | 41 |  | Yuri Phase 0 - Switchgear (MV & LV) Modification | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-08-04 | 2022-08-04 | 2022-08-18 | 2022-08-18
200883C-000-TBT-1652-4001 | [D] | 200883C | 0 | TBT | 1652 | 4001 |  | 41 |  | Yuri Phase 0 - Switchgear (MV & LV) Modification | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-09-01 | 2022-09-01 | 2022-08-18 | 2022-08-18
200883C-000-TBT-1654-4000 | [D] | 200883C | 0 | TBT | 1654 | 4000 |  | 41 |  | Yuri Phase 0 - LV Switchgear | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-12 | 2022-07-12 | 2022-08-15 | 2022-08-15
200883C-000-TBT-1654-4000 | [D] | 200883C | 0 | TBT | 1654 | 4000 |  | 41 |  | Yuri Phase 0 - LV Switchgear | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-08-09 | 2022-08-09 | 2022-09-09
200883C-000-TBT-1657-4000 | [D] | 200883C | 0 | TBT | 1657 | 4000 |  | 41 |  | Yuri Phase 0 - Power Distribution Boards | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-21 | 2022-07-21 | 2022-07-18 | 2022-07-18
200883C-000-TBT-1657-4000 | [D] | 200883C | 0 | TBT | 1657 | 4000 |  | 41 |  | Yuri Phase 0 - Power Distribution Boards | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-08-18 | 2022-08-18 | 2022-07-18 | 2022-07-18
200883C-000-TBT-1671-4000 | [D] | 200883C | 0 | TBT | 1671 | 4000 |  | 41 |  | Yuri Phase 0 - AC UPS System | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-21 | 2022-07-21 | 2022-07-21
200883C-000-TBT-1671-4000 | [D] | 200883C | 0 | TBT | 1671 | 4000 |  | 41 |  | Yuri Phase 0 - AC UPS System | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-08-18 | 2022-08-18 | 2022-08-18
200883C-000-TBT-1672-4000 | [D] | 200883C | 0 | TBT | 1672 | 4000 |  | 41 |  | Yuri Phase 0 - DC UPS System | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-21 | 2022-07-21 | 2022-07-21
200883C-000-TBT-1672-4000 | [D] | 200883C | 0 | TBT | 1672 | 4000 |  | 41 |  | Yuri Phase 0 - DC UPS System | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-08-18 | 2022-08-18 | 2022-08-18
200883C-300-DW-1423-5000 | [D] | 200883C | 300 | DW | 1423 | 5000 |  | 1 |  | Yuri Phase 0 - Laydown Area General Arrangements (DELETED 3-Aug-22) | Code: E0303 | CIV | 300PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-05-31 | 2022-05-31 | 2022-05-31 | 2022-05-31
200883C-300-DW-1423-5000 | [D] | 200883C | 300 | DW | 1423 | 5000 |  | 1 |  | Yuri Phase 0 - Laydown Area General Arrangements (DELETED 3-Aug-22) | Code: E0303 | CIV | 300PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-07-29 | 2022-07-29
200883C-300-DW-1423-5000 | [D] | 200883C | 300 | DW | 1423 | 5000 |  | 1 |  | Yuri Phase 0 - Laydown Area General Arrangements (DELETED 3-Aug-22) | Code: E0303 | CIV | 300PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-29 | 2022-07-29
200883C-300-DW-8200-5000 | [D] | 200883C | 300 | DW | 8200 | 5000 |  | 1 |  | Yuri Phase 0 - Site Plan GA (Including Facilities) Laydown Area | Code: E0303 | CIV | 300PV |  |  |  |  | STA | 10 |  |  | MFCIV |  | 2022-09-02 | 2022-08-13 | 2022-08-13
200883C-300-DW-8200-5000 | [D] | 200883C | 300 | DW | 8200 | 5000 |  | 1 |  | Yuri Phase 0 - Site Plan GA (Including Facilities) Laydown Area | Code: E0303 | CIV | 300PV |  |  |  |  | IFR | 70 |  |  | MFCIV |  | 2022-09-16 | 2022-08-15 | 2022-08-15
200883C-300-DW-8200-5000 | [D] | 200883C | 300 | DW | 8200 | 5000 |  | 1 |  | Yuri Phase 0 - Site Plan GA (Including Facilities) Laydown Area | Code: E0303 | CIV | 300PV |  |  |  |  | IFC | 100 |  |  | MFCIV |  | 2022-10-07 | 2022-10-07
200883C-400-DW-0410-5000 | [D] | 200883C | 400 | DW | 410 | 5000 |  | 200 |  | Yuri Phase 0 - Site Plan - GA (Including Facilities) Overall Site Layout - Array - 6 sheets | Code: E0303 | MEC | 400PV |  |  |  |  | STA | 10 |  |  | MFMEC | 2022-05-11 | 2022-05-11 | 2022-06-10 | 2022-06-10
200883C-400-DW-0410-5000 | [D] | 200883C | 400 | DW | 410 | 5000 |  | 200 |  | Yuri Phase 0 - Site Plan - GA (Including Facilities) Overall Site Layout - Array - 6 sheets | Code: E0303 | MEC | 400PV |  |  |  |  | IFR | 70 |  |  | MFMEC | 2022-06-10 | 2022-06-10 | 2022-06-30 | 2022-06-30
200883C-400-DW-0410-5000 | [D] | 200883C | 400 | DW | 410 | 5000 |  | 200 |  | Yuri Phase 0 - Site Plan - GA (Including Facilities) Overall Site Layout - Array - 6 sheets | Code: E0303 | MEC | 400PV |  |  |  |  | IFC | 100 |  |  | MFMEC | 2022-07-10 | 2022-07-10 | 2022-08-31
200883C-400-DW-1423-5000 | [D] | 200883C | 400 | DW | 1423 | 5000 |  | 20 |  | Yuri Phase 0 - Drainage - culvert layout plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-15 | 2022-06-15 | 2022-06-15 | 2022-06-15
200883C-400-DW-1423-5000 | [D] | 200883C | 400 | DW | 1423 | 5000 |  | 20 |  | Yuri Phase 0 - Drainage - culvert layout plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-15 | 2022-07-15 | 2022-07-15
200883C-400-DW-1423-5000 | [D] | 200883C | 400 | DW | 1423 | 5000 |  | 20 |  | Yuri Phase 0 - Drainage - culvert layout plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-14 | 2022-08-14 | 2022-08-14
200883C-400-DW-1423-5001 | [D] | 200883C | 400 | DW | 1423 | 5001 |  | 1 |  | Yuri Phase 0 - Drainage Schedule - Table - Drainage Profile - PV (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-07-18 | 2022-07-18 | 2022-07-29 | 2022-07-29
200883C-400-DW-1423-5001 | [D] | 200883C | 400 | DW | 1423 | 5001 |  | 1 |  | Yuri Phase 0 - Drainage Schedule - Table - Drainage Profile - PV (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-08-17 | 2022-08-17 | 2022-07-29 | 2022-07-29
200883C-400-DW-1423-5001 | [D] | 200883C | 400 | DW | 1423 | 5001 |  | 1 |  | Yuri Phase 0 - Drainage Schedule - Table - Drainage Profile - PV (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-09-16 | 2022-09-16 | 2022-07-29 | 2022-07-29
200883C-400-DW-1423-5002 | [D] | 200883C | 400 | DW | 1423 | 5002 |  | 1 |  | Yuri Phase 0 - Drainage Details - PV (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-07-04 | 2022-07-04 | 2022-07-29 | 2022-07-29
200883C-400-DW-1423-5002 | [D] | 200883C | 400 | DW | 1423 | 5002 |  | 1 |  | Yuri Phase 0 - Drainage Details - PV (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-08-03 | 2022-08-03 | 2022-07-29 | 2022-07-29
200883C-400-DW-1423-5002 | [D] | 200883C | 400 | DW | 1423 | 5002 |  | 1 |  | Yuri Phase 0 - Drainage Details - PV (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-09-02 | 2022-09-02 | 2022-07-29 | 2022-07-29
200883C-400-DW-1423-5003 | [D] | 200883C | 400 | DW | 1423 | 5003 |  | 40 |  | Yuri Phase 0 - Bulk Earthworks Cut and Fill Plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-15 | 2022-06-15 | 2022-06-15 | 2022-06-15
200883C-400-DW-1423-5003 | [D] | 200883C | 400 | DW | 1423 | 5003 |  | 40 |  | Yuri Phase 0 - Bulk Earthworks Cut and Fill Plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-15 | 2022-07-15 | 2022-07-15
200883C-400-DW-1423-5003 | [D] | 200883C | 400 | DW | 1423 | 5003 |  | 40 |  | Yuri Phase 0 - Bulk Earthworks Cut and Fill Plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-14 | 2022-08-14 | 2022-08-14
200883C-400-DW-1423-5004 | [D] | 200883C | 400 | DW | 1423 | 5004 |  | 48 |  | Yuri Phase 0 - Bulk earthworks grading plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-15 | 2022-06-15 | 2022-06-15 | 2022-06-15
200883C-400-DW-1423-5004 | [D] | 200883C | 400 | DW | 1423 | 5004 |  | 48 |  | Yuri Phase 0 - Bulk earthworks grading plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-15 | 2022-07-15 | 2022-07-15
200883C-400-DW-1423-5004 | [D] | 200883C | 400 | DW | 1423 | 5004 |  | 48 |  | Yuri Phase 0 - Bulk earthworks grading plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-14 | 2022-08-14 | 2022-08-14
200883C-400-DW-1423-5005 | [D] | 200883C | 400 | DW | 1423 | 5005 |  | 48 |  | Yuri Phase 0 - Typical bulk earthwork cross sections - PV | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-05-31 | 2022-05-31 | 2022-05-31 | 2022-05-31
200883C-400-DW-1423-5005 | [D] | 200883C | 400 | DW | 1423 | 5005 |  | 48 |  | Yuri Phase 0 - Typical bulk earthwork cross sections - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1423-5005 | [D] | 200883C | 400 | DW | 1423 | 5005 |  | 48 |  | Yuri Phase 0 - Typical bulk earthwork cross sections - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-30
200883C-400-DW-1423-5006 | [D] | 200883C | 400 | DW | 1423 | 5006 |  | 20 |  | Yuri Phase 0 - Cut and Fill Bulk Earthworks Overview - PV plant | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-15 | 2022-06-15 | 2022-06-15 | 2022-06-15
200883C-400-DW-1423-5006 | [D] | 200883C | 400 | DW | 1423 | 5006 |  | 20 |  | Yuri Phase 0 - Cut and Fill Bulk Earthworks Overview - PV plant | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-15 | 2022-07-15 | 2022-07-15
200883C-400-DW-1423-5006 | [D] | 200883C | 400 | DW | 1423 | 5006 |  | 20 |  | Yuri Phase 0 - Cut and Fill Bulk Earthworks Overview - PV plant | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-14 | 2022-08-14 | 2022-08-14
200883C-400-DW-1423-5007 | [D] | 200883C | 400 | DW | 1423 | 5007 |  | 40 |  | Yuri Phase 0 - Cut And Fill Bulk Earthworks - Array Xx - PV plant | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-15 | 2022-06-15 | 2022-06-15 | 2022-06-15
200883C-400-DW-1423-5007 | [D] | 200883C | 400 | DW | 1423 | 5007 |  | 40 |  | Yuri Phase 0 - Cut And Fill Bulk Earthworks - Array Xx - PV plant | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-15 | 2022-07-15 | 2022-07-15
200883C-400-DW-1423-5007 | [D] | 200883C | 400 | DW | 1423 | 5007 |  | 40 |  | Yuri Phase 0 - Cut And Fill Bulk Earthworks - Array Xx - PV plant | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-14 | 2022-08-14 | 2022-08-14
200883C-400-DW-1424-5000 | [D] | 200883C | 400 | DW | 1424 | 5000 |  | 40 |  | Yuri Phase 0 - Fencing Plan Sheet | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-15 | 2022-06-15 | 2022-06-15 | 2022-06-15
200883C-400-DW-1424-5000 | [D] | 200883C | 400 | DW | 1424 | 5000 |  | 40 |  | Yuri Phase 0 - Fencing Plan Sheet | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-15 | 2022-07-15 | 2022-07-15
200883C-400-DW-1424-5000 | [D] | 200883C | 400 | DW | 1424 | 5000 |  | 40 |  | Yuri Phase 0 - Fencing Plan Sheet | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-14 | 2022-08-14 | 2022-08-14
200883C-400-DW-1424-5001 | [D] | 200883C | 400 | DW | 1424 | 5001 |  | 16 |  | Yuri Phase 0 - Fence and Gates Manufacturing Details - 2 Sheets | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-11-15 | 2022-11-15 | 2022-06-30 | 2022-06-30
200883C-400-DW-1424-5001 | [D] | 200883C | 400 | DW | 1424 | 5001 |  | 16 |  | Yuri Phase 0 - Fence and Gates Manufacturing Details - 2 Sheets | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-12-15 | 2022-12-15 | 2022-06-30 | 2022-06-30
200883C-400-DW-1424-5001 | [D] | 200883C | 400 | DW | 1424 | 5001 |  | 16 |  | Yuri Phase 0 - Fence and Gates Manufacturing Details - 2 Sheets | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2023-01-14 | 2023-01-14 | 2023-01-14
200883C-400-DW-1424-5002 | [D] | 200883C | 400 | DW | 1424 | 5002 |  | 16 |  | Yuri Phase 0 - Gate Details Sheet - PV | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-08-16 | 2022-08-16 | 2022-08-16
200883C-400-DW-1424-5002 | [D] | 200883C | 400 | DW | 1424 | 5002 |  | 16 |  | Yuri Phase 0 - Gate Details Sheet - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-09-15 | 2022-09-15 | 2022-09-15
200883C-400-DW-1424-5002 | [D] | 200883C | 400 | DW | 1424 | 5002 |  | 16 |  | Yuri Phase 0 - Gate Details Sheet - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-10-15 | 2022-10-15 | 2022-10-15
200883C-400-DW-1425-5001 | [D] | 200883C | 400 | DW | 1425 | 5001 |  | 40 |  | Yuri Phase 0 - Road Culvert layout - PV | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-07-11 | 2022-07-11 | 2022-07-11
200883C-400-DW-1425-5001 | [D] | 200883C | 400 | DW | 1425 | 5001 |  | 40 |  | Yuri Phase 0 - Road Culvert layout - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-08-10 | 2022-08-10 | 2022-08-10
200883C-400-DW-1425-5001 | [D] | 200883C | 400 | DW | 1425 | 5001 |  | 40 |  | Yuri Phase 0 - Road Culvert layout - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-09-09 | 2022-09-09 | 2022-09-09
200883C-400-DW-1425-5002 | [D] | 200883C | 400 | DW | 1425 | 5002 |  | 32 |  | Yuri Phase 0 - Roadside drainage structure design plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-05-31 | 2022-05-31 | 2022-05-31 | 2022-05-31
200883C-400-DW-1425-5002 | [D] | 200883C | 400 | DW | 1425 | 5002 |  | 32 |  | Yuri Phase 0 - Roadside drainage structure design plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1425-5002 | [D] | 200883C | 400 | DW | 1425 | 5002 |  | 32 |  | Yuri Phase 0 - Roadside drainage structure design plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-30
200883C-400-DW-1425-5003 | [D] | 200883C | 400 | DW | 1425 | 5003 |  | 40 |  | Yuri Phase 0 - Roadside drainage structure detail - PV | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-26 | 2022-06-26 | 2022-06-26
200883C-400-DW-1425-5003 | [D] | 200883C | 400 | DW | 1425 | 5003 |  | 40 |  | Yuri Phase 0 - Roadside drainage structure detail - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-26 | 2022-07-26 | 2022-07-26
200883C-400-DW-1425-5003 | [D] | 200883C | 400 | DW | 1425 | 5003 |  | 40 |  | Yuri Phase 0 - Roadside drainage structure detail - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-25 | 2022-08-25 | 2022-08-25
200883C-400-DW-1425-5004 | [D] | 200883C | 400 | DW | 1425 | 5004 |  | 1 |  | Yuri Phase 0 - Turning Movements (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1425-5004 | [D] | 200883C | 400 | DW | 1425 | 5004 |  | 1 |  | Yuri Phase 0 - Turning Movements (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1425-5004 | [D] | 200883C | 400 | DW | 1425 | 5004 |  | 1 |  | Yuri Phase 0 - Turning Movements (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-29 | 2022-08-29 | 2022-07-29 | 2022-07-29
200883C-400-DW-1425-5005 | [D] | 200883C | 400 | DW | 1425 | 5005 |  | 40 |  | Yuri Phase 0 - Road Longitudinal Section | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-07-25 | 2022-07-25 | 2022-07-25
200883C-400-DW-1425-5005 | [D] | 200883C | 400 | DW | 1425 | 5005 |  | 40 |  | Yuri Phase 0 - Road Longitudinal Section | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-08-24 | 2022-08-24 | 2022-08-24
200883C-400-DW-1425-5005 | [D] | 200883C | 400 | DW | 1425 | 5005 |  | 40 |  | Yuri Phase 0 - Road Longitudinal Section | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-09-23 | 2022-09-23 | 2022-09-23
200883C-400-DW-1425-5006 | [D] | 200883C | 400 | DW | 1425 | 5006 |  | 40 |  | Yuri Phase 0 - Road Cross Sections | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1425-5006 | [D] | 200883C | 400 | DW | 1425 | 5006 |  | 40 |  | Yuri Phase 0 - Road Cross Sections | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-30
200883C-400-DW-1425-5006 | [D] | 200883C | 400 | DW | 1425 | 5006 |  | 40 |  | Yuri Phase 0 - Road Cross Sections | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-400-DW-1454-5000 | [D] | 200883C | 400 | DW | 1454 | 5000 |  | 1 |  | Yuri Phase 0 - Trench Route and Set Out Points - PV Array Xx (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1454-5000 | [D] | 200883C | 400 | DW | 1454 | 5000 |  | 1 |  | Yuri Phase 0 - Trench Route and Set Out Points - PV Array Xx (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1454-5000 | [D] | 200883C | 400 | DW | 1454 | 5000 |  | 1 |  | Yuri Phase 0 - Trench Route and Set Out Points - PV Array Xx (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-29 | 2022-08-29 | 2022-07-29 | 2022-07-29
200883C-400-DW-1454-5001 | [D] | 200883C | 400 | DW | 1454 | 5001 |  | 40 |  | Yuri Phase 0 - Trench Sections | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-13 | 2022-06-13 | 2022-06-13 | 2022-06-13
200883C-400-DW-1454-5001 | [D] | 200883C | 400 | DW | 1454 | 5001 |  | 40 |  | Yuri Phase 0 - Trench Sections | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-13 | 2022-07-13 | 2022-07-13
200883C-400-DW-1454-5001 | [D] | 200883C | 400 | DW | 1454 | 5001 |  | 40 |  | Yuri Phase 0 - Trench Sections | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-12 | 2022-08-12 | 2022-08-12
200883C-400-DW-1454-5002 | [D] | 200883C | 400 | DW | 1454 | 5002 |  | 40 |  | Yuri Phase 0 - DC Trench Route PV Array Xx | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-15 | 2022-06-15 | 2022-06-30 | 2022-06-30
200883C-400-DW-1454-5002 | [D] | 200883C | 400 | DW | 1454 | 5002 |  | 40 |  | Yuri Phase 0 - DC Trench Route PV Array Xx | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-15 | 2022-07-15 | 2022-06-30 | 2022-06-30
200883C-400-DW-1454-5002 | [D] | 200883C | 400 | DW | 1454 | 5002 |  | 40 |  | Yuri Phase 0 - DC Trench Route PV Array Xx | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-14 | 2022-08-14 | 2022-08-14
200883C-400-DW-1454-5003 | [D] | 200883C | 400 | DW | 1454 | 5003 |  | 40 |  | Yuri Phase 0 - DC Trench Route PV Array Xx - Section | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1454-5003 | [D] | 200883C | 400 | DW | 1454 | 5003 |  | 40 |  | Yuri Phase 0 - DC Trench Route PV Array Xx - Section | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-30
200883C-400-DW-1454-5003 | [D] | 200883C | 400 | DW | 1454 | 5003 |  | 40 |  | Yuri Phase 0 - DC Trench Route PV Array Xx - Section | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-400-DW-1454-5004 | [D] | 200883C | 400 | DW | 1454 | 5004 |  | 1 |  | Yuri Phase 0 - PCS and Trench Arrangements (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-05-31 | 2022-05-31 | 2022-05-31 | 2022-05-31
200883C-400-DW-1454-5004 | [D] | 200883C | 400 | DW | 1454 | 5004 |  | 1 |  | Yuri Phase 0 - PCS and Trench Arrangements (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1454-5004 | [D] | 200883C | 400 | DW | 1454 | 5004 |  | 1 |  | Yuri Phase 0 - PCS and Trench Arrangements (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1454-5005 | [D] | 200883C | 400 | DW | 1454 | 5005 |  | 1 |  | Yuri Phase 0 - CBX - Racking and Trench Arrangements (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-08-03 | 2022-08-03 | 2022-07-29 | 2022-07-29
200883C-400-DW-1454-5005 | [D] | 200883C | 400 | DW | 1454 | 5005 |  | 1 |  | Yuri Phase 0 - CBX - Racking and Trench Arrangements (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-09-02 | 2022-09-02 | 2022-07-29 | 2022-07-29
200883C-400-DW-1454-5005 | [D] | 200883C | 400 | DW | 1454 | 5005 |  | 1 |  | Yuri Phase 0 - CBX - Racking and Trench Arrangements (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-10-02 | 2022-10-02 | 2022-07-29 | 2022-07-29
200883C-400-DW-1512-5000 | [D] | 200883C | 400 | DW | 1512 | 5000 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Fibre Reticulation | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS |  | 2022-09-02 | 2022-08-13 | 2022-08-13
200883C-400-DW-1512-5000 | [D] | 200883C | 400 | DW | 1512 | 5000 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Fibre Reticulation | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS |  | 2022-09-16 | 2022-08-15 | 2022-08-15
200883C-400-DW-1512-5000 | [D] | 200883C | 400 | DW | 1512 | 5000 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Fibre Reticulation | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS |  | 2022-10-07 | 2022-10-07
200883C-400-DW-1512-5001 | [D] | 200883C | 400 | DW | 1512 | 5001 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - PCS-01 | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS |  | 2022-09-02 | 2022-08-13 | 2022-08-13
200883C-400-DW-1512-5001 | [D] | 200883C | 400 | DW | 1512 | 5001 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - PCS-01 | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS |  | 2022-09-23 | 2022-08-15 | 2022-08-15
200883C-400-DW-1512-5001 | [D] | 200883C | 400 | DW | 1512 | 5001 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - PCS-01 | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS |  | 2022-10-07 | 2022-10-07
200883C-400-DW-1512-5002 | [D] | 200883C | 400 | DW | 1512 | 5002 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - PCS-02 | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS |  | 2022-09-02 | 2022-08-13 | 2022-08-13
200883C-400-DW-1512-5002 | [D] | 200883C | 400 | DW | 1512 | 5002 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - PCS-02 | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS |  | 2022-09-23 | 2022-08-15 | 2022-08-15
200883C-400-DW-1512-5002 | [D] | 200883C | 400 | DW | 1512 | 5002 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - PCS-02 | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS |  | 2022-10-07 | 2022-10-07
200883C-400-DW-1512-5003 | [D] | 200883C | 400 | DW | 1512 | 5003 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - PCS-03 | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS |  | 2022-09-02 | 2022-08-13 | 2022-08-13
200883C-400-DW-1512-5003 | [D] | 200883C | 400 | DW | 1512 | 5003 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - PCS-03 | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS |  | 2022-09-23 | 2022-08-15 | 2022-08-15
200883C-400-DW-1512-5003 | [D] | 200883C | 400 | DW | 1512 | 5003 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - PCS-03 | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS |  | 2022-10-07 | 2022-10-07
200883C-400-DW-1512-5004 | [D] | 200883C | 400 | DW | 1512 | 5004 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - PCS-04 | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS |  | 2022-09-02 | 2022-08-13 | 2022-08-13
200883C-400-DW-1512-5004 | [D] | 200883C | 400 | DW | 1512 | 5004 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - PCS-04 | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS |  | 2022-09-23 | 2022-08-15 | 2022-08-15
200883C-400-DW-1512-5004 | [D] | 200883C | 400 | DW | 1512 | 5004 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - PCS-04 | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS |  | 2022-10-07 | 2022-10-07
200883C-400-DW-1512-5005 | [D] | 200883C | 400 | DW | 1512 | 5005 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - PCS-05 | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS |  | 2022-09-02 | 2022-08-13 | 2022-08-13
200883C-400-DW-1512-5005 | [D] | 200883C | 400 | DW | 1512 | 5005 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - PCS-05 | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS |  | 2022-09-23 | 2022-08-15 | 2022-08-15
200883C-400-DW-1512-5005 | [D] | 200883C | 400 | DW | 1512 | 5005 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - PCS-05 | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS |  | 2022-10-07 | 2022-10-07
200883C-400-DW-1512-5006 | [D] | 200883C | 400 | DW | 1512 | 5006 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - BESS-01 | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS |  | 2022-09-02 | 2022-08-13 | 2022-08-13
200883C-400-DW-1512-5006 | [D] | 200883C | 400 | DW | 1512 | 5006 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - BESS-01 | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS |  | 2022-09-23 | 2022-08-15 | 2022-08-15
200883C-400-DW-1512-5006 | [D] | 200883C | 400 | DW | 1512 | 5006 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - BESS-01 | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS |  | 2022-10-07 | 2022-10-07
200883C-400-DW-1512-5007 | [D] | 200883C | 400 | DW | 1512 | 5007 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - BESS-02 | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS |  | 2022-09-02 | 2022-08-13 | 2022-08-13
200883C-400-DW-1512-5007 | [D] | 200883C | 400 | DW | 1512 | 5007 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - BESS-02 | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS |  | 2022-09-23 | 2022-08-15 | 2022-08-15
200883C-400-DW-1512-5007 | [D] | 200883C | 400 | DW | 1512 | 5007 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - BESS-02 | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS |  | 2022-10-07 | 2022-10-07
200883C-400-DW-1512-5008 | [D] | 200883C | 400 | DW | 1512 | 5008 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - BESS-03 | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS |  | 2022-09-02 | 2022-08-13 | 2022-08-13
200883C-400-DW-1512-5008 | [D] | 200883C | 400 | DW | 1512 | 5008 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - BESS-03 | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS |  | 2022-09-23 | 2022-08-15 | 2022-08-15
200883C-400-DW-1512-5008 | [D] | 200883C | 400 | DW | 1512 | 5008 |  | 1 |  | Yuri Phase 0 - Microgrid Solar and BESS Network Topology - BESS-03 | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS |  | 2022-10-07 | 2022-10-07
200883C-400-DW-1522-5000 | [D] | 200883C | 400 | DW | 1522 | 5000 |  | 1 |  | Yuri Phase 0 - PCS-0x (DELETED 3-Aug-22) | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-06-12 | 2022-06-12 | 2022-06-12 | 2022-06-12
200883C-400-DW-1522-5000 | [D] | 200883C | 400 | DW | 1522 | 5000 |  | 1 |  | Yuri Phase 0 - PCS-0x (DELETED 3-Aug-22) | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-07-12 | 2022-07-12 | 2022-07-29 | 2022-07-29
200883C-400-DW-1522-5000 | [D] | 200883C | 400 | DW | 1522 | 5000 |  | 1 |  | Yuri Phase 0 - PCS-0x (DELETED 3-Aug-22) | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-08-11 | 2022-08-11 | 2022-07-29 | 2022-07-29
200883C-400-DW-1522-5001 | [D] | 200883C | 400 | DW | 1522 | 5001 |  | 40 |  | Yuri Phase 0 - PCS-Xx Comms Connections | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-06-19 | 2022-06-19 | 2022-06-19 | 2022-06-19
200883C-400-DW-1522-5001 | [D] | 200883C | 400 | DW | 1522 | 5001 |  | 40 |  | Yuri Phase 0 - PCS-Xx Comms Connections | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-07-19 | 2022-07-19 | 2022-08-19
200883C-400-DW-1522-5001 | [D] | 200883C | 400 | DW | 1522 | 5001 |  | 40 |  | Yuri Phase 0 - PCS-Xx Comms Connections | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-08-18 | 2022-08-18 | 2022-08-31
200883C-400-DW-1522-5002 | [D] | 200883C | 400 | DW | 1522 | 5002 |  | 1 |  | Yuri Phase 0 - PCS-Xx Earthing Layout (DELETED 3-Aug-22) | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-07-03 | 2022-07-03 | 2022-07-29 | 2022-07-29
200883C-400-DW-1522-5002 | [D] | 200883C | 400 | DW | 1522 | 5002 |  | 1 |  | Yuri Phase 0 - PCS-Xx Earthing Layout (DELETED 3-Aug-22) | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-08-02 | 2022-08-02 | 2022-07-29 | 2022-07-29
200883C-400-DW-1522-5002 | [D] | 200883C | 400 | DW | 1522 | 5002 |  | 1 |  | Yuri Phase 0 - PCS-Xx Earthing Layout (DELETED 3-Aug-22) | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-09-01 | 2022-09-01 | 2022-07-29 | 2022-07-29
200883C-400-DW-1572-5000 | [D] | 200883C | 400 | DW | 1572 | 5000 |  | 40 |  | Yuri Phase 0 - PCS-Xx Cable Connections | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-06-19 | 2022-06-19 | 2022-06-19 | 2022-06-19
200883C-400-DW-1572-5000 | [D] | 200883C | 400 | DW | 1572 | 5000 |  | 40 |  | Yuri Phase 0 - PCS-Xx Cable Connections | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-07-19 | 2022-07-19 | 2022-07-19
200883C-400-DW-1572-5000 | [D] | 200883C | 400 | DW | 1572 | 5000 |  | 40 |  | Yuri Phase 0 - PCS-Xx Cable Connections | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-08-18 | 2022-08-18 | 2022-08-18
200883C-400-DW-1612-5000 | [D] | 200883C | 400 | DW | 1612 | 5000 |  | 1 |  | Yuri Phase 0 - Earthing Layout Drawings - PV area (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2023-01-10 | 2023-01-10 | 2022-07-29 | 2022-07-29
200883C-400-DW-1612-5000 | [D] | 200883C | 400 | DW | 1612 | 5000 |  | 1 |  | Yuri Phase 0 - Earthing Layout Drawings - PV area (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2023-02-09 | 2023-02-09 | 2022-07-29 | 2022-07-29
200883C-400-DW-1612-5000 | [D] | 200883C | 400 | DW | 1612 | 5000 |  | 1 |  | Yuri Phase 0 - Earthing Layout Drawings - PV area (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2023-03-11 | 2023-03-11 | 2022-07-29 | 2022-07-29
200883C-400-DW-1612-5001 | [D] | 200883C | 400 | DW | 1612 | 5001 |  | 16 |  | Yuri Phase 0 - LV Protective Earthing Connections General Arrangments-02 | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-05-31 | 2022-05-31 | 2022-06-30 | 2022-06-30
200883C-400-DW-1612-5001 | [D] | 200883C | 400 | DW | 1612 | 5001 |  | 16 |  | Yuri Phase 0 - LV Protective Earthing Connections General Arrangments-02 | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1612-5001 | [D] | 200883C | 400 | DW | 1612 | 5001 |  | 16 |  | Yuri Phase 0 - LV Protective Earthing Connections General Arrangments-02 | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-08-30
200883C-400-DW-1612-5002 | [D] | 200883C | 400 | DW | 1612 | 5002 |  | 16 |  | Yuri Phase 0 - LV Protective Earthing Between Structures - PV | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-05-31 | 2022-05-31 | 2022-06-30 | 2022-06-30
200883C-400-DW-1612-5002 | [D] | 200883C | 400 | DW | 1612 | 5002 |  | 16 |  | Yuri Phase 0 - LV Protective Earthing Between Structures - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1612-5002 | [D] | 200883C | 400 | DW | 1612 | 5002 |  | 16 |  | Yuri Phase 0 - LV Protective Earthing Between Structures - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-08-30
200883C-400-DW-1612-5003 | [D] | 200883C | 400 | DW | 1612 | 5003 |  | 50 |  | Yuri Phase 0 - Array Xx LV Earthing - PV | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1612-5003 | [D] | 200883C | 400 | DW | 1612 | 5003 |  | 50 |  | Yuri Phase 0 - Array Xx LV Earthing - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1612-5003 | [D] | 200883C | 400 | DW | 1612 | 5003 |  | 50 |  | Yuri Phase 0 - Array Xx LV Earthing - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-400-DW-1622-5000 | [D] | 200883C | 400 | DW | 1622 | 5000 |  | 1 |  | Yuri Phase 0 - Underground Services Cable Trench Layout Drawing - PV area (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-12 | 2022-06-12 | 2022-06-12 | 2022-06-12
200883C-400-DW-1622-5000 | [D] | 200883C | 400 | DW | 1622 | 5000 |  | 1 |  | Yuri Phase 0 - Underground Services Cable Trench Layout Drawing - PV area (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-12 | 2022-07-12 | 2022-07-29 | 2022-07-29
200883C-400-DW-1622-5000 | [D] | 200883C | 400 | DW | 1622 | 5000 |  | 1 |  | Yuri Phase 0 - Underground Services Cable Trench Layout Drawing - PV area (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-11 | 2022-08-11 | 2022-07-29 | 2022-07-29
200883C-400-DW-1622-5001 | [D] | 200883C | 400 | DW | 1622 | 5001 |  | 32 |  | Yuri Phase 0 - Major Electrical Equipment Labelling - PV | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1622-5001 | [D] | 200883C | 400 | DW | 1622 | 5001 |  | 32 |  | Yuri Phase 0 - Major Electrical Equipment Labelling - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1622-5001 | [D] | 200883C | 400 | DW | 1622 | 5001 |  | 32 |  | Yuri Phase 0 - Major Electrical Equipment Labelling - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-400-DW-1622-5002 | [D] | 200883C | 400 | DW | 1622 | 5002 |  | 40 |  | Yuri Phase 0 - Site Array Layout And Labelling - PV | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1622-5002 | [D] | 200883C | 400 | DW | 1622 | 5002 |  | 40 |  | Yuri Phase 0 - Site Array Layout And Labelling - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-08-31
200883C-400-DW-1622-5002 | [D] | 200883C | 400 | DW | 1622 | 5002 |  | 40 |  | Yuri Phase 0 - Site Array Layout And Labelling - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-09-29
200883C-400-DW-1624-5000 | [D] | 200883C | 400 | DW | 1624 | 5000 |  | 40 |  | Yuri Phase 0 - Electrical General Arrangement Cable Extender Arrangements - 3 Sheets | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-05-31 | 2022-05-31 | 2022-06-30 | 2022-06-30
200883C-400-DW-1624-5000 | [D] | 200883C | 400 | DW | 1624 | 5000 |  | 40 |  | Yuri Phase 0 - Electrical General Arrangement Cable Extender Arrangements - 3 Sheets | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1624-5000 | [D] | 200883C | 400 | DW | 1624 | 5000 |  | 40 |  | Yuri Phase 0 - Electrical General Arrangement Cable Extender Arrangements - 3 Sheets | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-08-30
200883C-400-DW-1624-5001 | [D] | 200883C | 400 | DW | 1624 | 5001 |  | 40 |  | Yuri Phase 0 - DC Sub-Array Feeder Cables - PV | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1624-5001 | [D] | 200883C | 400 | DW | 1624 | 5001 |  | 40 |  | Yuri Phase 0 - DC Sub-Array Feeder Cables - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1624-5001 | [D] | 200883C | 400 | DW | 1624 | 5001 |  | 40 |  | Yuri Phase 0 - DC Sub-Array Feeder Cables - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-400-DW-1624-5002 | [D] | 200883C | 400 | DW | 1624 | 5002 |  | 1 |  | Yuri Phase 0 - Cable Management - Cbx To Structures (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1624-5002 | [D] | 200883C | 400 | DW | 1624 | 5002 |  | 1 |  | Yuri Phase 0 - Cable Management - Cbx To Structures (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1624-5002 | [D] | 200883C | 400 | DW | 1624 | 5002 |  | 1 |  | Yuri Phase 0 - Cable Management - Cbx To Structures (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-07-29 | 2022-07-29
200883C-400-DW-1624-5003 | [D] | 200883C | 400 | DW | 1624 | 5003 |  | 1 |  | Yuri Phase 0 - Cable Management - Across Structures (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1624-5003 | [D] | 200883C | 400 | DW | 1624 | 5003 |  | 1 |  | Yuri Phase 0 - Cable Management - Across Structures (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1624-5003 | [D] | 200883C | 400 | DW | 1624 | 5003 |  | 1 |  | Yuri Phase 0 - Cable Management - Across Structures (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-07-29 | 2022-07-29
200883C-400-DW-1624-5004 | [D] | 200883C | 400 | DW | 1624 | 5004 |  | 1 |  | Yuri Phase 0 - Cable Management - Between Structures (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1624-5004 | [D] | 200883C | 400 | DW | 1624 | 5004 |  | 1 |  | Yuri Phase 0 - Cable Management - Between Structures (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1624-5004 | [D] | 200883C | 400 | DW | 1624 | 5004 |  | 1 |  | Yuri Phase 0 - Cable Management - Between Structures (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-07-29 | 2022-07-29
200883C-400-DW-1624-5005 | [D] | 200883C | 400 | DW | 1624 | 5005 |  | 1 |  | Yuri Phase 0 - Cable Management - Combiner Box Inst Ga (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1624-5005 | [D] | 200883C | 400 | DW | 1624 | 5005 |  | 1 |  | Yuri Phase 0 - Cable Management - Combiner Box Inst Ga (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1624-5005 | [D] | 200883C | 400 | DW | 1624 | 5005 |  | 1 |  | Yuri Phase 0 - Cable Management - Combiner Box Inst Ga (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-07-29 | 2022-07-29
200883C-400-DW-1625-5000 | [D] | 200883C | 400 | DW | 1625 | 5000 |  | 1 |  | Yuri Phase 0 - PV Array Xx Pv String Layout - PV (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1625-5000 | [D] | 200883C | 400 | DW | 1625 | 5000 |  | 1 |  | Yuri Phase 0 - PV Array Xx Pv String Layout - PV (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1625-5000 | [D] | 200883C | 400 | DW | 1625 | 5000 |  | 1 |  | Yuri Phase 0 - PV Array Xx Pv String Layout - PV (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-07-29 | 2022-07-29
200883C-400-DW-1625-5001 | [D] | 200883C | 400 | DW | 1625 | 5001 |  | 1 |  | Yuri Phase 0 - BESS Layout Drawings (Internal) (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-11-30 | 2022-11-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1625-5001 | [D] | 200883C | 400 | DW | 1625 | 5001 |  | 1 |  | Yuri Phase 0 - BESS Layout Drawings (Internal) (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-12-30 | 2022-12-30 | 2022-07-29 | 2022-07-29
200883C-400-DW-1625-5001 | [D] | 200883C | 400 | DW | 1625 | 5001 |  | 1 |  | Yuri Phase 0 - BESS Layout Drawings (Internal) (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2023-01-29 | 2023-01-29 | 2022-07-29 | 2022-07-29
200883C-400-DW-1625-5002 | [D] | 200883C | 400 | DW | 1625 | 5002 |  | 1 |  | Yuri Phase 0 - DAS General Arrangement | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE |  | 2022-09-02 | 2022-09-02
200883C-400-DW-1625-5002 | [D] | 200883C | 400 | DW | 1625 | 5002 |  | 1 |  | Yuri Phase 0 - DAS General Arrangement | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE |  | 2022-09-23 | 2022-09-23
200883C-400-DW-1625-5002 | [D] | 200883C | 400 | DW | 1625 | 5002 |  | 1 |  | Yuri Phase 0 - DAS General Arrangement | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE |  | 2022-10-07 | 2022-10-07
200883C-400-DW-1625-5003 | [D] | 200883C | 400 | DW | 1625 | 5003 |  | 1 |  | Yuri Phase 0 - DAS Internal Layout | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFELE |  | 2022-09-02 | 2022-09-02
200883C-400-DW-1625-5003 | [D] | 200883C | 400 | DW | 1625 | 5003 |  | 1 |  | Yuri Phase 0 - DAS Internal Layout | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE |  | 2022-09-23 | 2022-09-23
200883C-400-DW-1625-5003 | [D] | 200883C | 400 | DW | 1625 | 5003 |  | 1 |  | Yuri Phase 0 - DAS Internal Layout | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE |  | 2022-10-07 | 2022-10-07
200883C-400-DW-1652-5000 | [D] | 200883C | 400 | DW | 1652 | 5000 |  | 24 |  | Yuri Phase 0 - SLD Xx - Xx string COMBINER BOX - PV | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-05-18 | 2022-05-18 | 2022-06-17 | 2022-06-17
200883C-400-DW-1652-5000 | [D] | 200883C | 400 | DW | 1652 | 5000 |  | 24 |  | Yuri Phase 0 - SLD Xx - Xx string COMBINER BOX - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-17 | 2022-06-17 | 2022-06-30 | 2022-06-30
200883C-400-DW-1652-5000 | [D] | 200883C | 400 | DW | 1652 | 5000 |  | 24 |  | Yuri Phase 0 - SLD Xx - Xx string COMBINER BOX - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-17 | 2022-07-17 | 2022-07-17
200883C-400-DW-1652-5001 | [D] | 200883C | 400 | DW | 1652 | 5001 |  | 128 |  | Yuri Phase 0 - EMS SLD - Architecture | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-05-16 | 2022-05-16 | 2022-05-16 | 2022-05-16
200883C-400-DW-1652-5001 | [D] | 200883C | 400 | DW | 1652 | 5001 |  | 128 |  | Yuri Phase 0 - EMS SLD - Architecture | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-15 | 2022-06-15 | 2022-06-15
200883C-400-DW-1652-5001 | [D] | 200883C | 400 | DW | 1652 | 5001 |  | 128 |  | Yuri Phase 0 - EMS SLD - Architecture | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-15 | 2022-07-15 | 2022-07-15
200883C-400-DW-1662-5000 | [D] | 200883C | 400 | DW | 1662 | 5000 |  | 40 |  | Yuri Phase 0 - Inverter HV Switchgear Schematic Control Diagrams - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-05-18 | 2022-05-18 | 2022-05-18 | 2022-05-18
200883C-400-DW-1662-5000 | [D] | 200883C | 400 | DW | 1662 | 5000 |  | 40 |  | Yuri Phase 0 - Inverter HV Switchgear Schematic Control Diagrams - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-17 | 2022-06-17 | 2022-06-17
200883C-400-DW-1662-5000 | [D] | 200883C | 400 | DW | 1662 | 5000 |  | 40 |  | Yuri Phase 0 - Inverter HV Switchgear Schematic Control Diagrams - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-17 | 2022-07-17 | 2022-07-17
200883C-400-DW-1662-5001 | [D] | 200883C | 400 | DW | 1662 | 5001 |  | 80 |  | Yuri Phase 0 - EMS Schematics | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-06 | 2022-06-06 | 2022-06-06 | 2022-06-06
200883C-400-DW-1662-5001 | [D] | 200883C | 400 | DW | 1662 | 5001 |  | 80 |  | Yuri Phase 0 - EMS Schematics | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-06 | 2022-07-06 | 2022-07-06
200883C-400-DW-1662-5001 | [D] | 200883C | 400 | DW | 1662 | 5001 |  | 80 |  | Yuri Phase 0 - EMS Schematics | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-05 | 2022-08-05 | 2022-08-05
200883C-400-DW-1664-5000 | [D] | 200883C | 400 | DW | 1664 | 5000 |  | 24 |  | Yuri Phase 0 - CBX Xx STRING-INTERNAL | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-10-21 | 2022-10-21 | 2022-06-30 | 2022-06-30
200883C-400-DW-1664-5000 | [D] | 200883C | 400 | DW | 1664 | 5000 |  | 24 |  | Yuri Phase 0 - CBX Xx STRING-INTERNAL | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-11-20 | 2022-11-20 | 2022-06-30 | 2022-06-30
200883C-400-DW-1664-5000 | [D] | 200883C | 400 | DW | 1664 | 5000 |  | 24 |  | Yuri Phase 0 - CBX Xx STRING-INTERNAL | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-12-20 | 2022-12-20 | 2022-12-20
200883C-400-DW-1664-5001 | [D] | 200883C | 400 | DW | 1664 | 5001 |  | 40 |  | Yuri Phase 0 - Panel Wiring Drawings - EMS | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-07-27 | 2022-07-27 | 2022-07-27
200883C-400-DW-1664-5001 | [D] | 200883C | 400 | DW | 1664 | 5001 |  | 40 |  | Yuri Phase 0 - Panel Wiring Drawings - EMS | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-08-26 | 2022-08-26 | 2022-08-26
200883C-400-DW-1664-5001 | [D] | 200883C | 400 | DW | 1664 | 5001 |  | 40 |  | Yuri Phase 0 - Panel Wiring Drawings - EMS | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-09-25 | 2022-09-25 | 2022-09-25
200883C-400-DW-1665-5000 | [D] | 200883C | 400 | DW | 1665 | 5000 |  | 16 |  | Yuri Phase 0 - Electrical General Arrangement Module Interconnection Details - 2 Sheets | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-05-16 | 2022-05-16 | 2022-06-15 | 2022-06-15
200883C-400-DW-1665-5000 | [D] | 200883C | 400 | DW | 1665 | 5000 |  | 16 |  | Yuri Phase 0 - Electrical General Arrangement Module Interconnection Details - 2 Sheets | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-15 | 2022-06-15 | 2022-06-30 | 2022-06-30
200883C-400-DW-1665-5000 | [D] | 200883C | 400 | DW | 1665 | 5000 |  | 16 |  | Yuri Phase 0 - Electrical General Arrangement Module Interconnection Details - 2 Sheets | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-15 | 2022-07-15 | 2022-07-15
200883C-400-DW-1665-5001 | [D] | 200883C | 400 | DW | 1665 | 5001 |  | 16 |  | Yuri Phase 0 - Termination Drawings | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-05-10 | 2022-05-10 | 2022-05-10 | 2022-05-10
200883C-400-DW-1665-5001 | [D] | 200883C | 400 | DW | 1665 | 5001 |  | 16 |  | Yuri Phase 0 - Termination Drawings | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-09 | 2022-06-09 | 2022-06-09
200883C-400-DW-1665-5001 | [D] | 200883C | 400 | DW | 1665 | 5001 |  | 16 |  | Yuri Phase 0 - Termination Drawings | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-09 | 2022-07-09 | 2022-07-09
200883C-400-DW-1722-5000 | [D] | 200883C | 400 | DW | 1722 | 5000 |  | 40 |  | Yuri Phase 0 - Platform Levels and Details Specifications - Foundations and Footings - PV Inverters | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-08 | 2022-06-08 | 2022-06-08 | 2022-06-08
200883C-400-DW-1722-5000 | [D] | 200883C | 400 | DW | 1722 | 5000 |  | 40 |  | Yuri Phase 0 - Platform Levels and Details Specifications - Foundations and Footings - PV Inverters | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-08 | 2022-07-08 | 2022-07-08
200883C-400-DW-1722-5000 | [D] | 200883C | 400 | DW | 1722 | 5000 |  | 40 |  | Yuri Phase 0 - Platform Levels and Details Specifications - Foundations and Footings - PV Inverters | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-07 | 2022-08-07 | 2022-08-07
200883C-400-DW-1722-5001 | [D] | 200883C | 400 | DW | 1722 | 5001 |  | 16 |  | Yuri Phase 0 - Typical Table Arrangments - PV structures | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-05-31 | 2022-05-31 | 2022-06-30 | 2022-06-30
200883C-400-DW-1722-5001 | [D] | 200883C | 400 | DW | 1722 | 5001 |  | 16 |  | Yuri Phase 0 - Typical Table Arrangments - PV structures | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1722-5001 | [D] | 200883C | 400 | DW | 1722 | 5001 |  | 16 |  | Yuri Phase 0 - Typical Table Arrangments - PV structures | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-30
200883C-400-DW-1824-5000 | [D] | 200883C | 400 | DW | 1824 | 5000 |  | 40 |  | Yuri Phase 0 - Platform Levels - PV area | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-05-31 | 2022-05-31 | 2022-05-31 | 2022-05-31
200883C-400-DW-1824-5000 | [D] | 200883C | 400 | DW | 1824 | 5000 |  | 40 |  | Yuri Phase 0 - Platform Levels - PV area | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-400-DW-1824-5000 | [D] | 200883C | 400 | DW | 1824 | 5000 |  | 40 |  | Yuri Phase 0 - Platform Levels - PV area | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-30
200883C-400-JSD-1400-5000 | [D] | 200883C | 400 | JSD | 1400 | 5000 |  | 40 |  | Yuri Phase 0 - Basis Of Design For Civil Works - PV Plant | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-04-18 | 2022-04-18 | 2022-04-18 | 2022-04-18
200883C-400-JSD-1400-5000 | [D] | 200883C | 400 | JSD | 1400 | 5000 |  | 40 |  | Yuri Phase 0 - Basis Of Design For Civil Works - PV Plant | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-05-18 | 2022-05-18 | 2022-05-18
200883C-400-JSD-1400-5000 | [D] | 200883C | 400 | JSD | 1400 | 5000 |  | 40 |  | Yuri Phase 0 - Basis Of Design For Civil Works - PV Plant | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-06-17 | 2022-06-17 | 2022-06-17
200883C-400-JSS-1510-5000 | [D] | 200883C | 400 | JSS | 1510 | 5000 |  | 168 |  | Yuri Phase 0 - Functional Design Specifications | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-05-23 | 2022-05-23 | 2022-05-23 | 2022-05-23
200883C-400-JSS-1510-5000 | [D] | 200883C | 400 | JSS | 1510 | 5000 |  | 168 |  | Yuri Phase 0 - Functional Design Specifications | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-06-22 | 2022-06-22 | 2022-06-22
200883C-400-JSS-1510-5000 | [D] | 200883C | 400 | JSS | 1510 | 5000 |  | 168 |  | Yuri Phase 0 - Functional Design Specifications | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-07-22 | 2022-07-22 | 2022-07-22
200883C-400-JSS-1640-5000 | [D] | 200883C | 400 | JSS | 1640 | 5000 |  | 40 |  | Yuri Phase 0 - Specification for Transformers - Inverters | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-29 | 2022-06-29 | 2022-06-29
200883C-400-JSS-1640-5000 | [D] | 200883C | 400 | JSS | 1640 | 5000 |  | 40 |  | Yuri Phase 0 - Specification for Transformers - Inverters | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-400-JSS-1640-5000 | [D] | 200883C | 400 | JSS | 1640 | 5000 |  | 40 |  | Yuri Phase 0 - Specification for Transformers - Inverters | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-28 | 2022-08-28 | 2022-08-28
200883C-400-JSS-1656-5000 | [D] | 200883C | 400 | JSS | 1656 | 5000 |  | 40 |  | Yuri Phase 0 - Specification for Harmonic Filtering System | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-10-12 | 2022-10-12 | 2022-10-12
200883C-400-JSS-1656-5000 | [D] | 200883C | 400 | JSS | 1656 | 5000 |  | 40 |  | Yuri Phase 0 - Specification for Harmonic Filtering System | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-11-11 | 2022-11-11 | 2022-11-11
200883C-400-JSS-1656-5000 | [D] | 200883C | 400 | JSS | 1656 | 5000 |  | 40 |  | Yuri Phase 0 - Specification for Harmonic Filtering System | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-12-11 | 2022-12-11 | 2022-12-11
200883C-400-JSS-1673-5000 | [D] | 200883C | 400 | JSS | 1673 | 5000 |  | 40 |  | Yuri Phase 0 - Specification for BESS | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-400-JSS-1673-5000 | [D] | 200883C | 400 | JSS | 1673 | 5000 |  | 40 |  | Yuri Phase 0 - Specification for BESS | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-09-28 | 2022-09-28 | 2022-09-28
200883C-400-JSS-1673-5000 | [D] | 200883C | 400 | JSS | 1673 | 5000 |  | 40 |  | Yuri Phase 0 - Specification for BESS | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-10-28 | 2022-10-28 | 2022-10-28
200883C-400-JSS-1673-5001 | [D] | 200883C | 400 | JSS | 1673 | 5001 |  | 40 |  | Yuri Phase 0 - Battery Management System Description | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-19 | 2022-06-19 | 2022-06-19 | 2022-06-19
200883C-400-JSS-1673-5001 | [D] | 200883C | 400 | JSS | 1673 | 5001 |  | 40 |  | Yuri Phase 0 - Battery Management System Description | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-19 | 2022-07-19 | 2022-07-19
200883C-400-JSS-1673-5001 | [D] | 200883C | 400 | JSS | 1673 | 5001 |  | 40 |  | Yuri Phase 0 - Battery Management System Description | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-18 | 2022-08-18 | 2022-08-18
200883C-400-MR-1656-1000 | [D] | 200883C | 400 | MR | 1656 | 1000 |  | 80 |  | Yuri Phase 0 - Material Requisistion - Harmonic Filtering System | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | AELE | 2023-04-30 | 2023-04-30 | 2023-04-30
200883C-400-MR-1656-1000 | [D] | 200883C | 400 | MR | 1656 | 1000 |  | 80 |  | Yuri Phase 0 - Material Requisistion - Harmonic Filtering System | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | AELE | 2023-04-30 | 2023-04-30 | 2023-04-30
200883C-400-MR-1656-1000 | [D] | 200883C | 400 | MR | 1656 | 1000 |  | 80 |  | Yuri Phase 0 - Material Requisistion - Harmonic Filtering System | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | AELE | 2024-02-29 | 2024-02-29 | 2024-02-29
200883C-400-MR-1673-5000 | [D] | 200883C | 400 | MR | 1673 | 5000 |  | 1 |  | Yuri Phase 0 - Material Requisistion - BESS (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-08-08 | 2022-08-08 | 2022-07-29 | 2022-07-29
200883C-400-MR-1673-5000 | [D] | 200883C | 400 | MR | 1673 | 5000 |  | 1 |  | Yuri Phase 0 - Material Requisistion - BESS (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-09-07 | 2022-09-07 | 2022-07-29 | 2022-07-29
200883C-400-MR-1673-5000 | [D] | 200883C | 400 | MR | 1673 | 5000 |  | 1 |  | Yuri Phase 0 - Material Requisistion - BESS (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-10-07 | 2022-10-07 | 2022-07-29 | 2022-07-29
200883C-400-NM-1500-5000 | [D] | 200883C | 400 | NM | 1500 | 5000 |  | 80 |  | Yuri Phase 0 - MV Station Com Panel I - O Signals List | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-07-19 | 2022-07-19 | 2022-07-19
200883C-400-NM-1500-5000 | [D] | 200883C | 400 | NM | 1500 | 5000 |  | 80 |  | Yuri Phase 0 - MV Station Com Panel I - O Signals List | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-08-18 | 2022-08-18 | 2022-08-18
200883C-400-NM-1500-5000 | [D] | 200883C | 400 | NM | 1500 | 5000 |  | 80 |  | Yuri Phase 0 - MV Station Com Panel I - O Signals List | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-09-17 | 2022-09-17 | 2022-09-17
200883C-400-NM-1535-5000 | [D] | 200883C | 400 | NM | 1535 | 5000 |  | 80 |  | Yuri Phase 0 – EMS Alarm List | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-07-19 | 2022-07-19 | 2022-07-19
200883C-400-NM-1535-5000 | [D] | 200883C | 400 | NM | 1535 | 5000 |  | 80 |  | Yuri Phase 0 – EMS Alarm List | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-08-18 | 2022-08-18 | 2022-08-18
200883C-400-NM-1535-5000 | [D] | 200883C | 400 | NM | 1535 | 5000 |  | 80 |  | Yuri Phase 0 – EMS Alarm List | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-09-17 | 2022-09-17 | 2022-09-17
200883C-400-NM-1572-5000 | [D] | 200883C | 400 | NM | 1572 | 5000 |  | 80 |  | Yuri Phase 0 - Met Station Signal List | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-06-20 | 2022-06-20 | 2022-06-20 | 2022-06-20
200883C-400-NM-1572-5000 | [D] | 200883C | 400 | NM | 1572 | 5000 |  | 80 |  | Yuri Phase 0 - Met Station Signal List | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-07-20 | 2022-07-20 | 2022-07-20
200883C-400-NM-1572-5000 | [D] | 200883C | 400 | NM | 1572 | 5000 |  | 80 |  | Yuri Phase 0 - Met Station Signal List | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-08-19 | 2022-08-19 | 2022-08-19
200883C-400-NM-1600-5000 | [D] | 200883C | 400 | NM | 1600 | 5000 |  | 40 |  | Yuri Phase 0 - Hourly Generation Data | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-400-NM-1600-5000 | [D] | 200883C | 400 | NM | 1600 | 5000 |  | 40 |  | Yuri Phase 0 - Hourly Generation Data | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-07-30
200883C-400-NM-1600-5000 | [D] | 200883C | 400 | NM | 1600 | 5000 |  | 40 |  | Yuri Phase 0 - Hourly Generation Data | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-400-NM-1623-5000 | [D] | 200883C | 400 | NM | 1623 | 5000 |  | 80 |  | Yuri Phase 0 - DC Cable Schedules - PV | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-05-18 | 2022-05-18 | 2022-05-18 | 2022-05-18
200883C-400-NM-1623-5000 | [D] | 200883C | 400 | NM | 1623 | 5000 |  | 80 |  | Yuri Phase 0 - DC Cable Schedules - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-17 | 2022-06-17 | 2022-06-17
200883C-400-NM-1623-5000 | [D] | 200883C | 400 | NM | 1623 | 5000 |  | 80 |  | Yuri Phase 0 - DC Cable Schedules - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-17 | 2022-07-17 | 2022-07-17
200883C-400-NM-5000 | [D] | 200883C | 400 | NM |  | 5000 |  | 40 |  | Yuri Phase 0 - PV Array Xx - Set out Points | Code: E0303 | MEC | 400PV |  |  |  |  | STA | 10 |  |  | MFMEC | 2022-07-10 | 2022-07-10 | 2022-08-15
200883C-400-NM-5000 | [D] | 200883C | 400 | NM |  | 5000 |  | 40 |  | Yuri Phase 0 - PV Array Xx - Set out Points | Code: E0303 | MEC | 400PV |  |  |  |  | IFR | 70 |  |  | MFMEC | 2022-08-09 | 2022-08-09 | 2022-09-01
200883C-400-NM-5000 | [D] | 200883C | 400 | NM |  | 5000 |  | 40 |  | Yuri Phase 0 - PV Array Xx - Set out Points | Code: E0303 | MEC | 400PV |  |  |  |  | IFC | 100 |  |  | MFMEC | 2022-09-08 | 2022-09-08 | 2022-09-29
200883C-400-RT-1400-5000 | [D] | 200883C | 400 | RT | 1400 | 5000 |  | 80 |  | Yuri Phase 0 - Civil and Structural Report - PV Area | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-07-19 | 2022-07-19 | 2022-07-19
200883C-400-RT-1400-5000 | [D] | 200883C | 400 | RT | 1400 | 5000 |  | 80 |  | Yuri Phase 0 - Civil and Structural Report - PV Area | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-08-18 | 2022-08-18 | 2022-08-18
200883C-400-RT-1400-5000 | [D] | 200883C | 400 | RT | 1400 | 5000 |  | 80 |  | Yuri Phase 0 - Civil and Structural Report - PV Area | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-09-17 | 2022-09-17 | 2022-09-17
200883C-400-RT-1600-5000 | [D] | 200883C | 400 | RT | 1600 | 5000 |  | 320 |  | Yuri Phase 0 - Power System Studies (loadflow - short circuit - transient stability) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-07-15 | 2022-07-15 | 2022-07-15
200883C-400-RT-1600-5000 | [D] | 200883C | 400 | RT | 1600 | 5000 |  | 320 |  | Yuri Phase 0 - Power System Studies (loadflow - short circuit - transient stability) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-08-14 | 2022-08-14 | 2022-08-14
200883C-400-RT-1600-5000 | [D] | 200883C | 400 | RT | 1600 | 5000 |  | 320 |  | Yuri Phase 0 - Power System Studies (loadflow - short circuit - transient stability) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-400-RT-1600-5001 | [D] | 200883C | 400 | RT | 1600 | 5001 |  | 120 |  | Yuri Phase 0 - Harmonic Analysis | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-08-31 | 2022-08-31 | 2022-08-31
200883C-400-RT-1600-5001 | [D] | 200883C | 400 | RT | 1600 | 5001 |  | 120 |  | Yuri Phase 0 - Harmonic Analysis | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-09-30 | 2022-09-30 | 2022-09-30
200883C-400-RT-1600-5001 | [D] | 200883C | 400 | RT | 1600 | 5001 |  | 120 |  | Yuri Phase 0 - Harmonic Analysis | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-10-30 | 2022-10-30 | 2022-10-30
200883C-400-RT-1600-5002 | [D] | 200883C | 400 | RT | 1600 | 5002 |  | 40 |  | Yuri Phase 0 - Energy Yield Analysis | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-400-RT-1600-5002 | [D] | 200883C | 400 | RT | 1600 | 5002 |  | 40 |  | Yuri Phase 0 - Energy Yield Analysis | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-29 | 2022-06-29 | 2022-06-29
200883C-400-RT-1600-5002 | [D] | 200883C | 400 | RT | 1600 | 5002 |  | 40 |  | Yuri Phase 0 - Energy Yield Analysis | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-400-RT-1600-5003 | [D] | 200883C | 400 | RT | 1600 | 5003 |  | 40 |  | Yuri Phase 0 - Shading Analysis | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-400-RT-1600-5003 | [D] | 200883C | 400 | RT | 1600 | 5003 |  | 40 |  | Yuri Phase 0 - Shading Analysis | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-29 | 2022-06-29 | 2022-06-29
200883C-400-RT-1600-5003 | [D] | 200883C | 400 | RT | 1600 | 5003 |  | 40 |  | Yuri Phase 0 - Shading Analysis | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-400-RT-1600-5004 | [D] | 200883C | 400 | RT | 1600 | 5004 |  | 40 |  | Yuri Phase 0 - Earthing And Lightning Report - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-08-30 | 2022-08-30 | 2022-08-30
200883C-400-RT-1600-5004 | [D] | 200883C | 400 | RT | 1600 | 5004 |  | 40 |  | Yuri Phase 0 - Earthing And Lightning Report - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-09-29 | 2022-09-29 | 2022-09-29
200883C-400-RT-1600-5004 | [D] | 200883C | 400 | RT | 1600 | 5004 |  | 40 |  | Yuri Phase 0 - Earthing And Lightning Report - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-10-29 | 2022-10-29 | 2022-10-29
200883C-400-RT-1600-5005 | [D] | 200883C | 400 | RT | 1600 | 5005 |  | 40 |  | Yuri Phase 0 - Cable Design Report - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-15 | 2022-06-15 | 2022-06-15 | 2022-06-15
200883C-400-RT-1600-5005 | [D] | 200883C | 400 | RT | 1600 | 5005 |  | 40 |  | Yuri Phase 0 - Cable Design Report - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-15 | 2022-07-15 | 2022-07-15
200883C-400-RT-1600-5005 | [D] | 200883C | 400 | RT | 1600 | 5005 |  | 40 |  | Yuri Phase 0 - Cable Design Report - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-14 | 2022-08-14 | 2022-08-14
200883C-400-RT-1600-5006 | [D] | 200883C | 400 | RT | 1600 | 5006 |  | 40 |  | Yuri Phase 0 - Insulation Coordination Report - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-07-30
200883C-400-RT-1600-5006 | [D] | 200883C | 400 | RT | 1600 | 5006 |  | 40 |  | Yuri Phase 0 - Insulation Coordination Report - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-400-RT-1600-5006 | [D] | 200883C | 400 | RT | 1600 | 5006 |  | 40 |  | Yuri Phase 0 - Insulation Coordination Report - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-09-28 | 2022-09-28 | 2022-09-28
200883C-400-RT-1600-5007 | [D] | 200883C | 400 | RT | 1600 | 5007 |  | 80 |  | Yuri Phase 0 - Electrical Design Report - PV | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-21 | 2022-06-21 | 2022-06-21 | 2022-06-21
200883C-400-RT-1600-5007 | [D] | 200883C | 400 | RT | 1600 | 5007 |  | 80 |  | Yuri Phase 0 - Electrical Design Report - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-21 | 2022-07-21 | 2022-07-21
200883C-400-RT-1600-5007 | [D] | 200883C | 400 | RT | 1600 | 5007 |  | 80 |  | Yuri Phase 0 - Electrical Design Report - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-20 | 2022-08-20 | 2022-08-20
200883C-400-RT-5000 | [D] | 200883C | 400 | RT |  | 5000 |  | 80 |  | Yuri Phase 0 - Certified Plant Certificates - Reports | Code: E0303 | MEC | 400PV |  |  |  |  | STA | 10 |  |  | MFMEC | 2022-08-31 | 2022-08-31 | 2022-08-31
200883C-400-RT-5000 | [D] | 200883C | 400 | RT |  | 5000 |  | 80 |  | Yuri Phase 0 - Certified Plant Certificates - Reports | Code: E0303 | MEC | 400PV |  |  |  |  | IFR | 70 |  |  | MFMEC | 2022-09-30 | 2022-09-30 | 2022-09-30
200883C-400-RT-5000 | [D] | 200883C | 400 | RT |  | 5000 |  | 80 |  | Yuri Phase 0 - Certified Plant Certificates - Reports | Code: E0303 | MEC | 400PV |  |  |  |  | IFC | 100 |  |  | MFMEC | 2022-10-30 | 2022-10-30 | 2022-10-30
200883C-400-SOW-1700-5000 | [D] | 200883C | 400 | SOW | 1700 | 5000 |  | 1 |  | Yuri Phase 0 - Subcontract Scope of Work - Site Preparation - Civil Works and Buildings (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-08-31 | 2022-08-31 | 2022-07-29 | 2022-07-29
200883C-400-SOW-1700-5000 | [D] | 200883C | 400 | SOW | 1700 | 5000 |  | 1 |  | Yuri Phase 0 - Subcontract Scope of Work - Site Preparation - Civil Works and Buildings (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-09-30 | 2022-09-30 | 2022-07-29 | 2022-07-29
200883C-400-SOW-1700-5000 | [D] | 200883C | 400 | SOW | 1700 | 5000 |  | 1 |  | Yuri Phase 0 - Subcontract Scope of Work - Site Preparation - Civil Works and Buildings (DELETED 3-Aug-22) | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-10-30 | 2022-10-30 | 2022-07-29 | 2022-07-29
200883C-400-SP-1600-5000 | [D] | 200883C | 400 | SP | 1600 | 5000 |  | 1 |  | Yuri Phase 0 - Technical Data Sheet Of PV - Inverter (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-07-29 | 2022-07-29
200883C-400-SP-1600-5000 | [D] | 200883C | 400 | SP | 1600 | 5000 |  | 1 |  | Yuri Phase 0 - Technical Data Sheet Of PV - Inverter (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-07-29 | 2022-07-29
200883C-400-SP-1600-5000 | [D] | 200883C | 400 | SP | 1600 | 5000 |  | 1 |  | Yuri Phase 0 - Technical Data Sheet Of PV - Inverter (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-07-29 | 2022-07-29
200883C-400-SP-1600-5001 | [D] | 200883C | 400 | SP | 1600 | 5001 |  | 1 |  | Yuri Phase 0 - Technical Data Sheet Cloud Detection System (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-04-25 | 2022-04-25 | 2022-04-25 | 2022-04-25
200883C-400-SP-1600-5001 | [D] | 200883C | 400 | SP | 1600 | 5001 |  | 1 |  | Yuri Phase 0 - Technical Data Sheet Cloud Detection System (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-05-25 | 2022-05-25 | 2022-07-29 | 2022-07-29
200883C-400-SP-1600-5001 | [D] | 200883C | 400 | SP | 1600 | 5001 |  | 1 |  | Yuri Phase 0 - Technical Data Sheet Cloud Detection System (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-06-24 | 2022-06-24 | 2022-07-29 | 2022-07-29
200883C-400-SP-1656-1000 | [D] | 200883C | 400 | SP | 1656 | 1000 |  | 10 |  | Yuri Phase 0 - Technical Data Sheet Of Harmonic Filter (response Sht) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-10-12 | 2022-10-12 | 2022-10-12
200883C-400-SP-1656-1000 | [D] | 200883C | 400 | SP | 1656 | 1000 |  | 10 |  | Yuri Phase 0 - Technical Data Sheet Of Harmonic Filter (response Sht) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-11-11 | 2022-11-11 | 2022-11-11
200883C-400-SP-1656-1000 | [D] | 200883C | 400 | SP | 1656 | 1000 |  | 10 |  | Yuri Phase 0 - Technical Data Sheet Of Harmonic Filter (response Sht) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-12-11 | 2022-12-11 | 2022-12-11
200883C-400-SP-1673-5000 | [D] | 200883C | 400 | SP | 1673 | 5000 |  | 1 |  | Yuri Phase 0 - Technical Data Sheet Of Battery - Inverter (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-04-18 | 2022-04-18 | 2022-04-18 | 2022-04-18
200883C-400-SP-1673-5000 | [D] | 200883C | 400 | SP | 1673 | 5000 |  | 1 |  | Yuri Phase 0 - Technical Data Sheet Of Battery - Inverter (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-05-18 | 2022-05-18 | 2022-07-29 | 2022-07-29
200883C-400-SP-1673-5000 | [D] | 200883C | 400 | SP | 1673 | 5000 |  | 1 |  | Yuri Phase 0 - Technical Data Sheet Of Battery - Inverter (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-06-17 | 2022-06-17 | 2022-07-29 | 2022-07-29
200883C-400-SP-1680-5000 | [D] | 200883C | 400 | SP | 1680 | 5000 |  | 1 |  | Yuri Phase 0 - Inverter Settings Sheet - PV microgrid (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-07-29 | 2022-07-29
200883C-400-SP-1680-5000 | [D] | 200883C | 400 | SP | 1680 | 5000 |  | 1 |  | Yuri Phase 0 - Inverter Settings Sheet - PV microgrid (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-07-29 | 2022-07-29
200883C-400-SP-1680-5000 | [D] | 200883C | 400 | SP | 1680 | 5000 |  | 1 |  | Yuri Phase 0 - Inverter Settings Sheet - PV microgrid (DELETED 3-Aug-22) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-07-29 | 2022-07-29
200883C-500-CN-0008-4001 | [D] | 200883C | 500 | CN | 8 | 4001 |  | 47 |  | Yuri Phase 0 - Process calculations- Non critical | Code: E0201 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-500-CN-0008-4001 | [D] | 200883C | 500 | CN | 8 | 4001 |  | 47 |  | Yuri Phase 0 - Process calculations- Non critical | Code: E0201 | PRO | 500H2 |  |  |  |  | IFI | 100 |  |  | MPRO | 2022-06-10 | 2022-06-10 | 2022-07-28 | 2022-07-28
200883C-500-CN-0008-4002 | [D] | 200883C | 500 | CN | 8 | 4002 |  | 94 |  | Yuri Phase 0 - Process calculations- Critical | Code: E0201 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-500-CN-0008-4002 | [D] | 200883C | 500 | CN | 8 | 4002 |  | 94 |  | Yuri Phase 0 - Process calculations- Critical | Code: E0201 | PRO | 500H2 |  |  |  |  | IFI | 100 |  |  | MPRO | 2022-06-17 | 2022-06-17 | 2022-06-17
200883C-500-CN-0009-4000 | [D] | 200883C | 500 | CN | 9 | 4000 |  | 94 |  | Yuri Phase 0 - Operating Guide | Code: E0311 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2023-03-15 | 2023-03-15 | 2023-03-15
200883C-500-CN-0009-4000 | [D] | 200883C | 500 | CN | 9 | 4000 |  | 94 |  | Yuri Phase 0 - Operating Guide | Code: E0311 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2023-04-10 | 2023-04-10 | 2023-04-10
200883C-500-CN-0009-4000 | [D] | 200883C | 500 | CN | 9 | 4000 |  | 94 |  | Yuri Phase 0 - Operating Guide | Code: E0311 | PRO | 500H2 |  |  |  |  | IFU | 100 |  |  | MPRO | 2023-05-08 | 2023-05-08 | 2023-05-08
200883C-500-CN-1370-4000 | [D] | 200883C | 500 | CN | 1370 | 4000 |  | 180 |  | Yuri Phase 0-Stress Analysis Reports | Code: E0201 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2023-02-10 | 2023-02-10 | 2023-02-10
200883C-500-CN-1370-4000 | [D] | 200883C | 500 | CN | 1370 | 4000 |  | 180 |  | Yuri Phase 0-Stress Analysis Reports | Code: E0201 | PIP | 500H2 |  |  |  |  | IFI | 100 |  |  | MPIP | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-CN-1370-4001 | [D] | 200883C | 500 | CN | 1370 | 4001 |  | 90 |  | Yuri Phase 0-Material handling report | Code: E0201 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2023-02-10 | 2023-02-10 | 2023-02-10
200883C-500-CN-1370-4001 | [D] | 200883C | 500 | CN | 1370 | 4001 |  | 90 |  | Yuri Phase 0-Material handling report | Code: E0201 | PIP | 500H2 |  |  |  |  | IFI | 100 |  |  | MPIP | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-CN-1425-2000 | [D] | 200883C | 500 | CN | 1425 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Road Pavement Design - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-07-12 | 2022-07-12 | 2022-07-18 | 2022-07-18
200883C-500-CN-1425-2000 | [D] | 200883C | 500 | CN | 1425 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Road Pavement Design - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-07-18 | 2022-07-18 | 2022-08-26 | 2022-08-26
200883C-500-CN-1425-2000 | [D] | 200883C | 500 | CN | 1425 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Road Pavement Design - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFD | 100 |  |  | BCIV | 2022-10-12 | 2022-10-12 | 2022-10-12
200883C-500-CN-1441-2000 | [D] | 200883C | 500 | CN | 1441 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Drainage Design - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-08-25 | 2022-08-25 | 2022-07-23 | 2022-07-23
200883C-500-CN-1441-2000 | [D] | 200883C | 500 | CN | 1441 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Drainage Design - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-01 | 2022-09-01 | 2022-07-25 | 2022-07-25
200883C-500-CN-1441-2000 | [D] | 200883C | 500 | CN | 1441 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Drainage Design - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFD | 100 |  |  | BCIV | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-CN-1731-2000 | [D] | 200883C | 500 | CN | 1731 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Pipe / Cable - Sleeper foundations H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-08 | 2022-12-08 | 2022-12-08
200883C-500-CN-1731-2000 | [D] | 200883C | 500 | CN | 1731 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Pipe / Cable - Sleeper foundations H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-500-CN-1731-2000 | [D] | 200883C | 500 | CN | 1731 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Pipe / Cable - Sleeper foundations H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFD | 100 |  |  | BCIV | 2023-02-23 | 2023-02-23 | 2023-02-23
200883C-500-CN-1732-2000 | [D] | 200883C | 500 | CN | 1732 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Vent Encloser Shelter Foundation and Ground Floor - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-12 | 2022-12-12 | 2022-12-12
200883C-500-CN-1732-2000 | [D] | 200883C | 500 | CN | 1732 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Vent Encloser Shelter Foundation and Ground Floor - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-16 | 2022-12-16 | 2022-12-16
200883C-500-CN-1732-2000 | [D] | 200883C | 500 | CN | 1732 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Vent Encloser Shelter Foundation and Ground Floor - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFD | 100 |  |  | BCIV | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-CN-1732-2001 | [D] | 200883C | 500 | CN | 1732 | 2001 |  | 50 |  | Yuri Phase 0 - Calculation For Substation foundations - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-500-CN-1732-2001 | [D] | 200883C | 500 | CN | 1732 | 2001 |  | 50 |  | Yuri Phase 0 - Calculation For Substation foundations - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-21 | 2022-12-21 | 2022-12-21
200883C-500-CN-1732-2001 | [D] | 200883C | 500 | CN | 1732 | 2001 |  | 50 |  | Yuri Phase 0 - Calculation For Substation foundations - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFD | 100 |  |  | BCIV | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-CN-1733-2000 | [D] | 200883C | 500 | CN | 1733 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Vendor Assembled Skids and Equipment Foundations - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-09-02 | 2022-09-02 | 2022-09-02
200883C-500-CN-1733-2000 | [D] | 200883C | 500 | CN | 1733 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Vendor Assembled Skids and Equipment Foundations - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-08 | 2022-09-08 | 2022-09-08
200883C-500-CN-1733-2000 | [D] | 200883C | 500 | CN | 1733 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Vendor Assembled Skids and Equipment Foundations - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFD | 100 |  |  | BCIV | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-500-CN-1735-2000 | [D] | 200883C | 500 | CN | 1735 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Battery Limit Platform - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-09-15 | 2022-09-15 | 2022-09-15
200883C-500-CN-1735-2000 | [D] | 200883C | 500 | CN | 1735 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Battery Limit Platform - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-21 | 2022-09-21 | 2022-09-21
200883C-500-CN-1735-2000 | [D] | 200883C | 500 | CN | 1735 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Battery Limit Platform - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFD | 100 |  |  | BCIV | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-500-CN-3440-4000 | [D] | 200883C | 500 | CN | 3440 | 4000 |  | 113 |  | Calculations for HVAC | Code: E0311 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-12-09 | 2022-12-09 | 2022-12-09
200883C-500-CN-3440-4000 | [D] | 200883C | 500 | CN | 3440 | 4000 |  | 113 |  | Calculations for HVAC | Code: E0311 | MEC | 500H2 |  |  |  |  | IFR | 70 |  |  | MMEC | 2022-12-22 | 2022-12-22 | 2022-12-22
200883C-500-CN-3440-4000 | [D] | 200883C | 500 | CN | 3440 | 4000 |  | 113 |  | Calculations for HVAC | Code: E0311 | MEC | 500H2 |  |  |  |  | IFU | 100 |  |  | MMEC | 2023-01-19 | 2023-01-19 | 2023-01-19
200883C-500-DW-0051-4000 | [D] | 200883C | 500 | DW | 51 | 4000 |  | 45 |  | Yuri Phase 0-Equipment arrangement drawing | Code: E0401 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-23 | 2022-07-23 | 2022-07-23 | 2022-07-23
200883C-500-DW-0051-4000 | [D] | 200883C | 500 | DW | 51 | 4000 |  | 45 |  | Yuri Phase 0-Equipment arrangement drawing | Code: E0401 | PIP | 500H2 |  |  |  |  | IFR | 50 |  |  | MPIP | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-500-DW-0051-4000 | [D] | 200883C | 500 | DW | 51 | 4000 |  | 45 |  | Yuri Phase 0-Equipment arrangement drawing | Code: E0401 | PIP | 500H2 |  |  |  |  | IFD | 70 |  |  | MPIP | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-DW-0051-4000 | [D] | 200883C | 500 | DW | 51 | 4000 |  | 45 |  | Yuri Phase 0-Equipment arrangement drawing | Code: E0401 | PIP | 500H2 |  |  |  |  | IFC | 100 |  |  | MPIP | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-DW-0051-4001 | [D] | 200883C | 500 | DW | 51 | 4001 |  | 360 |  | Yuri Phase 0-Plant Plot Plan | Code: E0401 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-06-14 | 2022-06-14 | 2022-06-16 | 2022-06-16
200883C-500-DW-0051-4001 | [D] | 200883C | 500 | DW | 51 | 4001 |  | 360 |  | Yuri Phase 0-Plant Plot Plan | Code: E0401 | PIP | 500H2 |  |  |  |  | IFR | 50 |  |  | MPIP | 2022-06-27 | 2022-06-27 | 2022-06-16 | 2022-06-16
200883C-500-DW-0051-4001 | [D] | 200883C | 500 | DW | 51 | 4001 |  | 360 |  | Yuri Phase 0-Plant Plot Plan | Code: E0401 | PIP | 500H2 |  |  |  |  | IFD | 70 |  |  | MPIP | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-500-DW-0051-4001 | [D] | 200883C | 500 | DW | 51 | 4001 |  | 360 |  | Yuri Phase 0-Plant Plot Plan | Code: E0401 | PIP | 500H2 |  |  |  |  | IFC | 100 |  |  | MPIP | 2023-01-18 | 2023-01-18 | 2023-01-18
200883C-500-DW-0051-4002 | [D] | 200883C | 500 | DW | 51 | 4002 |  | 23 |  | Yuri Phase 0 - Area Division Drawing | Code: E0201 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-06-20 | 2022-06-20 | 2022-06-20 | 2022-06-20
200883C-500-DW-0051-4002 | [D] | 200883C | 500 | DW | 51 | 4002 |  | 23 |  | Yuri Phase 0 - Area Division Drawing | Code: E0201 | PIP | 500H2 |  |  |  |  | IFI | 100 |  |  | MPIP | 2022-06-27 | 2022-06-27 | 2022-07-06 | 2022-07-06
200883C-500-DW-0052-4000 | [D] | 200883C | 500 | DW | 52 | 4000 |  | 23 |  | Yuri Phase 0-Utility Station And Safety Shower Layout | Code: E0401 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-08-15 | 2022-08-15 | 2022-08-15 | 2022-08-15
200883C-500-DW-0052-4000 | [D] | 200883C | 500 | DW | 52 | 4000 |  | 23 |  | Yuri Phase 0-Utility Station And Safety Shower Layout | Code: E0401 | PIP | 500H2 |  |  |  |  | IFR | 50 |  |  | MPIP | 2022-08-30 | 2022-08-30 | 2022-08-30
200883C-500-DW-0052-4000 | [D] | 200883C | 500 | DW | 52 | 4000 |  | 23 |  | Yuri Phase 0-Utility Station And Safety Shower Layout | Code: E0401 | PIP | 500H2 |  |  |  |  | IFD | 70 |  |  | MPIP | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-DW-0052-4000 | [D] | 200883C | 500 | DW | 52 | 4000 |  | 23 |  | Yuri Phase 0-Utility Station And Safety Shower Layout | Code: E0401 | PIP | 500H2 |  |  |  |  | IFC | 100 |  |  | MPIP | 2023-02-15 | 2023-02-15 | 2023-02-15
200883C-500-DW-1322-4000 | [D] | 200883C | 500 | DW | 1322 | 4000 |  | 135 |  | Yuri Phase 0-Nozzle Orientation and Orientation of pipe support clips, ladder clips and platform clips | Code: E0201 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2023-01-05 | 2023-01-05 | 2023-01-05
200883C-500-DW-1322-4000 | [D] | 200883C | 500 | DW | 1322 | 4000 |  | 135 |  | Yuri Phase 0-Nozzle Orientation and Orientation of pipe support clips, ladder clips and platform clips | Code: E0201 | PIP | 500H2 |  |  |  |  | IFI | 100 |  |  | MPIP | 2023-01-20 | 2023-01-20 | 2023-01-20
200883C-500-DW-1332-4000 | [D] | 200883C | 500 | DW | 1332 | 4000 |  | 23 |  | Yuri Phase 0- Piping General Arrangement | Code: E0203 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2023-01-29 | 2023-01-29 | 2023-01-29
200883C-500-DW-1332-4000 | [D] | 200883C | 500 | DW | 1332 | 4000 |  | 23 |  | Yuri Phase 0- Piping General Arrangement | Code: E0203 | PIP | 500H2 |  |  |  |  | IFC | 100 |  |  | MPIP | 2023-02-13 | 2023-02-13 | 2023-02-13
200883C-500-DW-1421-2000 | [D] | 200883C | 500 | DW | 1421 | 2000 |  | 75 |  | Yuri Phase 0 - Site Plan Layout - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-07-05 | 2022-07-05 | 2022-06-30 | 2022-06-30
200883C-500-DW-1421-2000 | [D] | 200883C | 500 | DW | 1421 | 2000 |  | 75 |  | Yuri Phase 0 - Site Plan Layout - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-07-11 | 2022-07-11 | 2022-06-30 | 2022-06-30
200883C-500-DW-1421-2000 | [D] | 200883C | 500 | DW | 1421 | 2000 |  | 75 |  | Yuri Phase 0 - Site Plan Layout - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-10-04 | 2022-10-04 | 2022-10-04
200883C-500-DW-1423-2000 | [D] | 200883C | 500 | DW | 1423 | 2000 |  | 75 |  | Yuri Phase 0 - Bulk earthworks plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-07-12 | 2022-07-12 | 2022-06-30 | 2022-06-30
200883C-500-DW-1423-2000 | [D] | 200883C | 500 | DW | 1423 | 2000 |  | 75 |  | Yuri Phase 0 - Bulk earthworks plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-07-18 | 2022-07-18 | 2022-06-30 | 2022-06-30
200883C-500-DW-1423-2000 | [D] | 200883C | 500 | DW | 1423 | 2000 |  | 75 |  | Yuri Phase 0 - Bulk earthworks plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-10-12 | 2022-10-12 | 2022-10-12
200883C-500-DW-1423-2001 | [D] | 200883C | 500 | DW | 1423 | 2001 |  | 50 |  | Yuri Phase 0 - Bulk earthwork detailed sections - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-07-21 | 2022-07-21 | 2022-06-30 | 2022-06-30
200883C-500-DW-1423-2001 | [D] | 200883C | 500 | DW | 1423 | 2001 |  | 50 |  | Yuri Phase 0 - Bulk earthwork detailed sections - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-07-27 | 2022-07-27 | 2022-06-30 | 2022-06-30
200883C-500-DW-1423-2001 | [D] | 200883C | 500 | DW | 1423 | 2001 |  | 50 |  | Yuri Phase 0 - Bulk earthwork detailed sections - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-10-19 | 2022-10-19 | 2022-10-19
200883C-500-DW-1425-2000 | [D] | 200883C | 500 | DW | 1425 | 2000 |  | 75 |  | Yuri Phase 0 - Overall Road And Paving Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-07-12 | 2022-07-12 | 2022-06-30 | 2022-06-30
200883C-500-DW-1425-2000 | [D] | 200883C | 500 | DW | 1425 | 2000 |  | 75 |  | Yuri Phase 0 - Overall Road And Paving Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-07-18 | 2022-07-18 | 2022-06-30 | 2022-06-30
200883C-500-DW-1425-2000 | [D] | 200883C | 500 | DW | 1425 | 2000 |  | 75 |  | Yuri Phase 0 - Overall Road And Paving Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-10-12 | 2022-10-12 | 2022-10-12
200883C-500-DW-1425-2001 | [D] | 200883C | 500 | DW | 1425 | 2001 |  | 25 |  | Yuri Phase 0 - Road and car park marking plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-500-DW-1425-2001 | [D] | 200883C | 500 | DW | 1425 | 2001 |  | 25 |  | Yuri Phase 0 - Road and car park marking plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-500-DW-1425-2001 | [D] | 200883C | 500 | DW | 1425 | 2001 |  | 25 |  | Yuri Phase 0 - Road and car park marking plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-DW-1425-2002 | [D] | 200883C | 500 | DW | 1425 | 2002 |  | 25 |  | Yuri Phase 0 - Roadside drainage structure details (1) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-07-21 | 2022-07-21 | 2022-06-30 | 2022-06-30
200883C-500-DW-1425-2002 | [D] | 200883C | 500 | DW | 1425 | 2002 |  | 25 |  | Yuri Phase 0 - Roadside drainage structure details (1) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-07-27 | 2022-07-27 | 2022-06-30 | 2022-06-30
200883C-500-DW-1425-2002 | [D] | 200883C | 500 | DW | 1425 | 2002 |  | 25 |  | Yuri Phase 0 - Roadside drainage structure details (1) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-10-19 | 2022-10-19 | 2022-10-19
200883C-500-DW-1425-2003 | [D] | 200883C | 500 | DW | 1425 | 2003 |  | 25 |  | Yuri Phase 0 - Roadside drainage structure details (2) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-07-21 | 2022-07-21 | 2022-07-21 | 2022-07-21
200883C-500-DW-1425-2003 | [D] | 200883C | 500 | DW | 1425 | 2003 |  | 25 |  | Yuri Phase 0 - Roadside drainage structure details (2) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-07-27 | 2022-07-27 | 2022-07-27
200883C-500-DW-1425-2003 | [D] | 200883C | 500 | DW | 1425 | 2003 |  | 25 |  | Yuri Phase 0 - Roadside drainage structure details (2) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-10-19 | 2022-10-19 | 2022-10-19
200883C-500-DW-1425-2004 | [D] | 200883C | 500 | DW | 1425 | 2004 |  | 25 |  | Yuri Phase 0 - Roadside drainage structure details (3) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-07-21 | 2022-07-21 | 2022-07-21 | 2022-07-21
200883C-500-DW-1425-2004 | [D] | 200883C | 500 | DW | 1425 | 2004 |  | 25 |  | Yuri Phase 0 - Roadside drainage structure details (3) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-07-27 | 2022-07-27 | 2022-07-27
200883C-500-DW-1425-2004 | [D] | 200883C | 500 | DW | 1425 | 2004 |  | 25 |  | Yuri Phase 0 - Roadside drainage structure details (3) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-10-19 | 2022-10-19 | 2022-10-19
200883C-500-DW-1452-2000 | [D] | 200883C | 500 | DW | 1452 | 2000 |  | 99 |  | Yuri Phase 0 - Civil Works Installation Overall Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-08 | 2022-12-08 | 2022-06-25 | 2022-06-25
200883C-500-DW-1452-2000 | [D] | 200883C | 500 | DW | 1452 | 2000 |  | 99 |  | Yuri Phase 0 - Civil Works Installation Overall Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-14 | 2022-12-14 | 2022-07-06 | 2022-07-06
200883C-500-DW-1452-2000 | [D] | 200883C | 500 | DW | 1452 | 2000 |  | 99 |  | Yuri Phase 0 - Civil Works Installation Overall Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-DW-1452-2001 | [D] | 200883C | 500 | DW | 1452 | 2001 |  | 25 |  | Yuri Phase 0 - Civil Works Installation Area (1) Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-08 | 2022-12-08 | 2022-06-25 | 2022-06-25
200883C-500-DW-1452-2001 | [D] | 200883C | 500 | DW | 1452 | 2001 |  | 25 |  | Yuri Phase 0 - Civil Works Installation Area (1) Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-14 | 2022-12-14 | 2022-07-06 | 2022-07-06
200883C-500-DW-1452-2001 | [D] | 200883C | 500 | DW | 1452 | 2001 |  | 25 |  | Yuri Phase 0 - Civil Works Installation Area (1) Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-DW-1452-2002 | [D] | 200883C | 500 | DW | 1452 | 2002 |  | 25 |  | Yuri Phase 0 - Civil Works Installation Area (2) Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-08 | 2022-12-08 | 2022-06-25 | 2022-06-25
200883C-500-DW-1452-2002 | [D] | 200883C | 500 | DW | 1452 | 2002 |  | 25 |  | Yuri Phase 0 - Civil Works Installation Area (2) Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-14 | 2022-12-14 | 2022-07-06 | 2022-07-06
200883C-500-DW-1452-2002 | [D] | 200883C | 500 | DW | 1452 | 2002 |  | 25 |  | Yuri Phase 0 - Civil Works Installation Area (2) Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-DW-1454-2001 | [D] | 200883C | 500 | DW | 1454 | 2001 |  | 50 |  | Yuri Phase 0 - Hydraulic Systems Details Drawing - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-500-DW-1454-2001 | [D] | 200883C | 500 | DW | 1454 | 2001 |  | 50 |  | Yuri Phase 0 - Hydraulic Systems Details Drawing - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-500-DW-1454-2001 | [D] | 200883C | 500 | DW | 1454 | 2001 |  | 50 |  | Yuri Phase 0 - Hydraulic Systems Details Drawing - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-DW-1454-2002 | [D] | 200883C | 500 | DW | 1454 | 2002 |  | 25 |  | Yuri Phase 0 - Drainage Schedule - Table - Drainage Profile (1) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-08-25 | 2022-08-25 | 2022-08-25 | 2022-08-25
200883C-500-DW-1454-2002 | [D] | 200883C | 500 | DW | 1454 | 2002 |  | 25 |  | Yuri Phase 0 - Drainage Schedule - Table - Drainage Profile (1) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-01 | 2022-09-01 | 2022-09-01
200883C-500-DW-1454-2002 | [D] | 200883C | 500 | DW | 1454 | 2002 |  | 25 |  | Yuri Phase 0 - Drainage Schedule - Table - Drainage Profile (1) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-DW-1454-2003 | [D] | 200883C | 500 | DW | 1454 | 2003 |  | 25 |  | Yuri Phase 0 - Drainage Schedule - Table - Drainage Profile (2) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-08-25 | 2022-08-25 | 2022-08-25 | 2022-08-25
200883C-500-DW-1454-2003 | [D] | 200883C | 500 | DW | 1454 | 2003 |  | 25 |  | Yuri Phase 0 - Drainage Schedule - Table - Drainage Profile (2) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-01 | 2022-09-01 | 2022-09-01
200883C-500-DW-1454-2003 | [D] | 200883C | 500 | DW | 1454 | 2003 |  | 25 |  | Yuri Phase 0 - Drainage Schedule - Table - Drainage Profile (2) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-DW-1454-2004 | [D] | 200883C | 500 | DW | 1454 | 2004 |  | 50 |  | Yuri Phase 0 - Drainage Details - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-08-25 | 2022-08-25 | 2022-08-25 | 2022-08-25
200883C-500-DW-1454-2004 | [D] | 200883C | 500 | DW | 1454 | 2004 |  | 50 |  | Yuri Phase 0 - Drainage Details - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-01 | 2022-09-01 | 2022-09-01
200883C-500-DW-1454-2004 | [D] | 200883C | 500 | DW | 1454 | 2004 |  | 50 |  | Yuri Phase 0 - Drainage Details - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-DW-1612-4000 | [D] | 200883C | 500 | DW | 1612 | 4000 |  | 41 |  | Yuri Phase 0 - Earthing Layout Drawings - H2 | Code: E0303 | ELE | 500H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-19 | 2022-07-19 | 2022-06-29 | 2022-06-29
200883C-500-DW-1612-4000 | [D] | 200883C | 500 | DW | 1612 | 4000 |  | 41 |  | Yuri Phase 0 - Earthing Layout Drawings - H2 | Code: E0303 | ELE | 500H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-08-01 | 2022-08-01 | 2022-06-29 | 2022-06-29
200883C-500-DW-1612-4000 | [D] | 200883C | 500 | DW | 1612 | 4000 |  | 41 |  | Yuri Phase 0 - Earthing Layout Drawings - H2 | Code: E0303 | ELE | 500H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2023-02-09 | 2023-02-09 | 2023-02-09
200883C-500-DW-1622-4000 | [D] | 200883C | 500 | DW | 1622 | 4000 |  | 21 |  | Yuri Phase 0 - Electrical Lighting Layout Drawing - Key Plan | Code: E0303 | ELE | 500H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-08-25 | 2022-08-25 | 2022-08-25 | 2022-08-25
200883C-500-DW-1622-4000 | [D] | 200883C | 500 | DW | 1622 | 4000 |  | 21 |  | Yuri Phase 0 - Electrical Lighting Layout Drawing - Key Plan | Code: E0303 | ELE | 500H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-09-01 | 2022-09-01 | 2022-09-01
200883C-500-DW-1622-4000 | [D] | 200883C | 500 | DW | 1622 | 4000 |  | 21 |  | Yuri Phase 0 - Electrical Lighting Layout Drawing - Key Plan | Code: E0303 | ELE | 500H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-09-29 | 2022-09-29 | 2022-09-29
200883C-500-DW-1624-4000 | [D] | 200883C | 500 | DW | 1624 | 4000 |  | 41 |  | Yuri Phase 0 - Cable Rack Layout Drawings | Code: E0303 | ELE | 500H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-08-24 | 2022-08-24 | 2022-08-24 | 2022-08-24
200883C-500-DW-1624-4000 | [D] | 200883C | 500 | DW | 1624 | 4000 |  | 41 |  | Yuri Phase 0 - Cable Rack Layout Drawings | Code: E0303 | ELE | 500H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-09-07 | 2022-09-07 | 2022-08-26 | 2022-08-26
200883C-500-DW-1624-4000 | [D] | 200883C | 500 | DW | 1624 | 4000 |  | 41 |  | Yuri Phase 0 - Cable Rack Layout Drawings | Code: E0303 | ELE | 500H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2023-02-02 | 2023-02-02 | 2023-02-02
200883C-500-DW-1624-4001 | [D] | 200883C | 500 | DW | 1624 | 4001 |  | 21 |  | Yuri Phase 0 - Cable Rack Layout Drawing - Key Plan | Code: E0303 | ELE | 500H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-08-08 | 2022-08-08 | 2022-08-08 | 2022-08-08
200883C-500-DW-1624-4001 | [D] | 200883C | 500 | DW | 1624 | 4001 |  | 21 |  | Yuri Phase 0 - Cable Rack Layout Drawing - Key Plan | Code: E0303 | ELE | 500H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-08-15 | 2022-08-15 | 2022-08-15
200883C-500-DW-1624-4001 | [D] | 200883C | 500 | DW | 1624 | 4001 |  | 21 |  | Yuri Phase 0 - Cable Rack Layout Drawing - Key Plan | Code: E0303 | ELE | 500H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-DW-1632-4000 | [D] | 200883C | 500 | DW | 1632 | 4000 |  | 61 |  | Yuri Phase 0 - Lighting And Small Power Layout Drawings | Code: E0303 | ELE | 500H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-12-08 | 2022-12-08 | 2022-12-08
200883C-500-DW-1632-4000 | [D] | 200883C | 500 | DW | 1632 | 4000 |  | 61 |  | Yuri Phase 0 - Lighting And Small Power Layout Drawings | Code: E0303 | ELE | 500H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-12-21 | 2022-12-21 | 2022-12-21
200883C-500-DW-1632-4000 | [D] | 200883C | 500 | DW | 1632 | 4000 |  | 61 |  | Yuri Phase 0 - Lighting And Small Power Layout Drawings | Code: E0303 | ELE | 500H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2023-02-09 | 2023-02-09 | 2023-02-09
200883C-500-DW-1701-2000 | [D] | 200883C | 500 | DW | 1701 | 2000 |  | 99 |  | Yuri Phase 0 - Overall Foundation Layout Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-08-30 | 2022-08-30 | 2022-08-30
200883C-500-DW-1701-2000 | [D] | 200883C | 500 | DW | 1701 | 2000 |  | 99 |  | Yuri Phase 0 - Overall Foundation Layout Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-20 | 2022-09-20 | 2022-09-20
200883C-500-DW-1701-2000 | [D] | 200883C | 500 | DW | 1701 | 2000 |  | 99 |  | Yuri Phase 0 - Overall Foundation Layout Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-500-DW-1741-2000 | [D] | 200883C | 500 | DW | 1741 | 2000 |  | 50 |  | Yuri Phase 0 - Pipe / Cable Support - Foundation Layout Plan | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-08 | 2022-12-08 | 2022-12-08
200883C-500-DW-1741-2000 | [D] | 200883C | 500 | DW | 1741 | 2000 |  | 50 |  | Yuri Phase 0 - Pipe / Cable Support - Foundation Layout Plan | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-500-DW-1741-2000 | [D] | 200883C | 500 | DW | 1741 | 2000 |  | 50 |  | Yuri Phase 0 - Pipe / Cable Support - Foundation Layout Plan | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2023-02-23 | 2023-02-23 | 2023-02-23
200883C-500-DW-1741-2001 | [D] | 200883C | 500 | DW | 1741 | 2001 |  | 25 |  | Yuri Phase 0 - Pipe / Cable Support - Foundation Schedule and Details | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-08 | 2022-12-08 | 2022-12-08
200883C-500-DW-1741-2001 | [D] | 200883C | 500 | DW | 1741 | 2001 |  | 25 |  | Yuri Phase 0 - Pipe / Cable Support - Foundation Schedule and Details | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-500-DW-1741-2001 | [D] | 200883C | 500 | DW | 1741 | 2001 |  | 25 |  | Yuri Phase 0 - Pipe / Cable Support - Foundation Schedule and Details | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2023-02-23 | 2023-02-23 | 2023-02-23
200883C-500-DW-1742-2000 | [D] | 200883C | 500 | DW | 1742 | 2000 |  | 38 |  | Yuri Phase 0 - Battery Limit Platform Foundation Plans and Details | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-09-15 | 2022-09-15 | 2022-09-15
200883C-500-DW-1742-2000 | [D] | 200883C | 500 | DW | 1742 | 2000 |  | 38 |  | Yuri Phase 0 - Battery Limit Platform Foundation Plans and Details | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-21 | 2022-09-21 | 2022-09-21
200883C-500-DW-1742-2000 | [D] | 200883C | 500 | DW | 1742 | 2000 |  | 38 |  | Yuri Phase 0 - Battery Limit Platform Foundation Plans and Details | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-500-DW-1743-2000 | [D] | 200883C | 500 | DW | 1743 | 2000 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (1) | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-09-02 | 2022-09-02 | 2022-09-02
200883C-500-DW-1743-2000 | [D] | 200883C | 500 | DW | 1743 | 2000 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (1) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-08 | 2022-09-08 | 2022-09-08
200883C-500-DW-1743-2000 | [D] | 200883C | 500 | DW | 1743 | 2000 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (1) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-500-DW-1743-2001 | [D] | 200883C | 500 | DW | 1743 | 2001 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (2) | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-09-02 | 2022-09-02 | 2022-09-02
200883C-500-DW-1743-2001 | [D] | 200883C | 500 | DW | 1743 | 2001 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (2) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-08 | 2022-09-08 | 2022-09-08
200883C-500-DW-1743-2001 | [D] | 200883C | 500 | DW | 1743 | 2001 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (2) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-500-DW-1743-2002 | [D] | 200883C | 500 | DW | 1743 | 2002 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (3) | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-09-02 | 2022-09-02 | 2022-09-02
200883C-500-DW-1743-2002 | [D] | 200883C | 500 | DW | 1743 | 2002 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (3) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-08 | 2022-09-08 | 2022-09-08
200883C-500-DW-1743-2002 | [D] | 200883C | 500 | DW | 1743 | 2002 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (3) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-500-DW-1743-2003 | [D] | 200883C | 500 | DW | 1743 | 2003 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (4) | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-09-02 | 2022-09-02 | 2022-09-02
200883C-500-DW-1743-2003 | [D] | 200883C | 500 | DW | 1743 | 2003 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (4) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-08 | 2022-09-08 | 2022-09-08
200883C-500-DW-1743-2003 | [D] | 200883C | 500 | DW | 1743 | 2003 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (4) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-500-DW-1743-2004 | [D] | 200883C | 500 | DW | 1743 | 2004 |  | 38 |  | Yuri Phase 0 - Substation Foundation Plans and Details (1) | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-500-DW-1743-2004 | [D] | 200883C | 500 | DW | 1743 | 2004 |  | 38 |  | Yuri Phase 0 - Substation Foundation Plans and Details (1) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-21 | 2022-12-21 | 2022-12-21
200883C-500-DW-1743-2004 | [D] | 200883C | 500 | DW | 1743 | 2004 |  | 38 |  | Yuri Phase 0 - Substation Foundation Plans and Details (1) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-DW-1743-2005 | [D] | 200883C | 500 | DW | 1743 | 2005 |  | 38 |  | Yuri Phase 0 - Substation Foundation Plans and Details (2) | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-500-DW-1743-2005 | [D] | 200883C | 500 | DW | 1743 | 2005 |  | 38 |  | Yuri Phase 0 - Substation Foundation Plans and Details (2) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-21 | 2022-12-21 | 2022-12-21
200883C-500-DW-1743-2005 | [D] | 200883C | 500 | DW | 1743 | 2005 |  | 38 |  | Yuri Phase 0 - Substation Foundation Plans and Details (2) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-DW-1743-2006 | [D] | 200883C | 500 | DW | 1743 | 2006 |  | 25 |  | Yuri Phase 0 - Air Cooled Heat Exchanger Foundation Plans and Details | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-500-DW-1743-2006 | [D] | 200883C | 500 | DW | 1743 | 2006 |  | 25 |  | Yuri Phase 0 - Air Cooled Heat Exchanger Foundation Plans and Details | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-DW-1743-2006 | [D] | 200883C | 500 | DW | 1743 | 2006 |  | 25 |  | Yuri Phase 0 - Air Cooled Heat Exchanger Foundation Plans and Details | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-DW-1760-2000 | [D] | 200883C | 500 | DW | 1760 | 2000 |  | 50 |  | Yuri Phase 0 - H2 Ventilated Enclosure Slab Set out Plan | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-08 | 2022-12-08 | 2022-12-08
200883C-500-DW-1760-2000 | [D] | 200883C | 500 | DW | 1760 | 2000 |  | 50 |  | Yuri Phase 0 - H2 Ventilated Enclosure Slab Set out Plan | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-500-DW-1760-2000 | [D] | 200883C | 500 | DW | 1760 | 2000 |  | 50 |  | Yuri Phase 0 - H2 Ventilated Enclosure Slab Set out Plan | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-DW-1760-2001 | [D] | 200883C | 500 | DW | 1760 | 2001 |  | 25 |  | Yuri Phase 0 - H2 Ventilated Enclosure Slab and Foundation Details (1) | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-12 | 2022-12-12 | 2022-12-12
200883C-500-DW-1760-2001 | [D] | 200883C | 500 | DW | 1760 | 2001 |  | 25 |  | Yuri Phase 0 - H2 Ventilated Enclosure Slab and Foundation Details (1) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-16 | 2022-12-16 | 2022-12-16
200883C-500-DW-1760-2001 | [D] | 200883C | 500 | DW | 1760 | 2001 |  | 25 |  | Yuri Phase 0 - H2 Ventilated Enclosure Slab and Foundation Details (1) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-DW-1760-2002 | [D] | 200883C | 500 | DW | 1760 | 2002 |  | 25 |  | Yuri Phase 0 - H2 Ventilated Enclosure Slab and Foundation Details (2) | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-12 | 2022-12-12 | 2022-12-12
200883C-500-DW-1760-2002 | [D] | 200883C | 500 | DW | 1760 | 2002 |  | 25 |  | Yuri Phase 0 - H2 Ventilated Enclosure Slab and Foundation Details (2) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-16 | 2022-12-16 | 2022-12-16
200883C-500-DW-1760-2002 | [D] | 200883C | 500 | DW | 1760 | 2002 |  | 25 |  | Yuri Phase 0 - H2 Ventilated Enclosure Slab and Foundation Details (2) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-DW-1760-2003 | [D] | 200883C | 500 | DW | 1760 | 2003 |  | 25 |  | Yuri Phase 0 - H2 Ventilated Enclosure Slab and Foundation Details (3) | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-12 | 2022-12-12 | 2022-12-12
200883C-500-DW-1760-2003 | [D] | 200883C | 500 | DW | 1760 | 2003 |  | 25 |  | Yuri Phase 0 - H2 Ventilated Enclosure Slab and Foundation Details (3) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-16 | 2022-12-16 | 2022-12-16
200883C-500-DW-1760-2003 | [D] | 200883C | 500 | DW | 1760 | 2003 |  | 25 |  | Yuri Phase 0 - H2 Ventilated Enclosure Slab and Foundation Details (3) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-DW-1760-2004 | [D] | 200883C | 500 | DW | 1760 | 2004 |  | 25 |  | Yuri Phase 0 - H2 Ventilated Enclosure Slab and Foundation Details (4) | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-12-12 | 2022-12-12 | 2022-12-12
200883C-500-DW-1760-2004 | [D] | 200883C | 500 | DW | 1760 | 2004 |  | 25 |  | Yuri Phase 0 - H2 Ventilated Enclosure Slab and Foundation Details (4) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-12-16 | 2022-12-16 | 2022-12-16
200883C-500-DW-1760-2004 | [D] | 200883C | 500 | DW | 1760 | 2004 |  | 25 |  | Yuri Phase 0 - H2 Ventilated Enclosure Slab and Foundation Details (4) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-DW-1821-4001 | [D] | 200883C | 500 | DW | 1821 | 4001 |  | 0 |  | Piperack Module - PR1- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-23 | 2022-09-23
200883C-500-DW-1821-4001 | [D] | 200883C | 500 | DW | 1821 | 4001 |  | 0 |  | Piperack Module - PR1- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-30 | 2022-09-30
200883C-500-DW-1821-4001 | [D] | 200883C | 500 | DW | 1821 | 4001 |  | 0 |  | Piperack Module - PR1- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4002 | [D] | 200883C | 500 | DW | 1821 | 4002 |  | 0 |  | Piperack Module - PR1- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-23 | 2022-09-23
200883C-500-DW-1821-4002 | [D] | 200883C | 500 | DW | 1821 | 4002 |  | 0 |  | Piperack Module - PR1- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-30 | 2022-09-30
200883C-500-DW-1821-4002 | [D] | 200883C | 500 | DW | 1821 | 4002 |  | 0 |  | Piperack Module - PR1- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4003 | [D] | 200883C | 500 | DW | 1821 | 4003 |  | 0 |  | Piperack Module - PR1- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-23 | 2022-09-23
200883C-500-DW-1821-4003 | [D] | 200883C | 500 | DW | 1821 | 4003 |  | 0 |  | Piperack Module - PR1- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-30 | 2022-09-30
200883C-500-DW-1821-4003 | [D] | 200883C | 500 | DW | 1821 | 4003 |  | 0 |  | Piperack Module - PR1- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4004 | [D] | 200883C | 500 | DW | 1821 | 4004 |  | 0 |  | Piperack Module - PR1- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-23 | 2022-09-23
200883C-500-DW-1821-4004 | [D] | 200883C | 500 | DW | 1821 | 4004 |  | 0 |  | Piperack Module - PR1- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-30 | 2022-09-30
200883C-500-DW-1821-4004 | [D] | 200883C | 500 | DW | 1821 | 4004 |  | 0 |  | Piperack Module - PR1- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4005 | [D] | 200883C | 500 | DW | 1821 | 4005 |  | 0 |  | Piperack Module - PR1- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-23 | 2022-09-23
200883C-500-DW-1821-4005 | [D] | 200883C | 500 | DW | 1821 | 4005 |  | 0 |  | Piperack Module - PR1- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-30 | 2022-09-30
200883C-500-DW-1821-4005 | [D] | 200883C | 500 | DW | 1821 | 4005 |  | 0 |  | Piperack Module - PR1- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4006 | [D] | 200883C | 500 | DW | 1821 | 4006 |  | 0 |  | Piperack Module - PR2- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-DW-1821-4006 | [D] | 200883C | 500 | DW | 1821 | 4006 |  | 0 |  | Piperack Module - PR2- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-23 | 2022-09-23
200883C-500-DW-1821-4006 | [D] | 200883C | 500 | DW | 1821 | 4006 |  | 0 |  | Piperack Module - PR2- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4007 | [D] | 200883C | 500 | DW | 1821 | 4007 |  | 0 |  | Piperack Module - PR2- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-DW-1821-4007 | [D] | 200883C | 500 | DW | 1821 | 4007 |  | 0 |  | Piperack Module - PR2- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-23 | 2022-09-23
200883C-500-DW-1821-4007 | [D] | 200883C | 500 | DW | 1821 | 4007 |  | 0 |  | Piperack Module - PR2- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4008 | [D] | 200883C | 500 | DW | 1821 | 4008 |  | 0 |  | Piperack Module - PR2- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-DW-1821-4008 | [D] | 200883C | 500 | DW | 1821 | 4008 |  | 0 |  | Piperack Module - PR2- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-23 | 2022-09-23
200883C-500-DW-1821-4008 | [D] | 200883C | 500 | DW | 1821 | 4008 |  | 0 |  | Piperack Module - PR2- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4009 | [D] | 200883C | 500 | DW | 1821 | 4009 |  | 0 |  | Piperack Module - PR2- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-DW-1821-4009 | [D] | 200883C | 500 | DW | 1821 | 4009 |  | 0 |  | Piperack Module - PR2- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-23 | 2022-09-23
200883C-500-DW-1821-4009 | [D] | 200883C | 500 | DW | 1821 | 4009 |  | 0 |  | Piperack Module - PR2- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4010 | [D] | 200883C | 500 | DW | 1821 | 4010 |  | 0 |  | Piperack Module - PR2- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-DW-1821-4010 | [D] | 200883C | 500 | DW | 1821 | 4010 |  | 0 |  | Piperack Module - PR2- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-23 | 2022-09-23
200883C-500-DW-1821-4010 | [D] | 200883C | 500 | DW | 1821 | 4010 |  | 0 |  | Piperack Module - PR2- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4011 | [D] | 200883C | 500 | DW | 1821 | 4011 |  | 0 |  | Piperack Module - PR3- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-09 | 2022-09-09
200883C-500-DW-1821-4011 | [D] | 200883C | 500 | DW | 1821 | 4011 |  | 0 |  | Piperack Module - PR3- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-DW-1821-4011 | [D] | 200883C | 500 | DW | 1821 | 4011 |  | 0 |  | Piperack Module - PR3- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4012 | [D] | 200883C | 500 | DW | 1821 | 4012 |  | 0 |  | Piperack Module - PR3- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-09 | 2022-09-09
200883C-500-DW-1821-4012 | [D] | 200883C | 500 | DW | 1821 | 4012 |  | 0 |  | Piperack Module - PR3- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-DW-1821-4012 | [D] | 200883C | 500 | DW | 1821 | 4012 |  | 0 |  | Piperack Module - PR3- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4013 | [D] | 200883C | 500 | DW | 1821 | 4013 |  | 0 |  | Piperack Module - PR3- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-09 | 2022-09-09
200883C-500-DW-1821-4013 | [D] | 200883C | 500 | DW | 1821 | 4013 |  | 0 |  | Piperack Module - PR3- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-DW-1821-4013 | [D] | 200883C | 500 | DW | 1821 | 4013 |  | 0 |  | Piperack Module - PR3- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4014 | [D] | 200883C | 500 | DW | 1821 | 4014 |  | 0 |  | Piperack Module - PR3- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-09 | 2022-09-09
200883C-500-DW-1821-4014 | [D] | 200883C | 500 | DW | 1821 | 4014 |  | 0 |  | Piperack Module - PR3- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-DW-1821-4014 | [D] | 200883C | 500 | DW | 1821 | 4014 |  | 0 |  | Piperack Module - PR3- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4015 | [D] | 200883C | 500 | DW | 1821 | 4015 |  | 0 |  | Piperack Module - PR3- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-09 | 2022-09-09
200883C-500-DW-1821-4015 | [D] | 200883C | 500 | DW | 1821 | 4015 |  | 0 |  | Piperack Module - PR3- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-DW-1821-4015 | [D] | 200883C | 500 | DW | 1821 | 4015 |  | 0 |  | Piperack Module - PR3- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4016 | [D] | 200883C | 500 | DW | 1821 | 4016 |  | 0 |  | Piperack Module - PR4- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-08-23 | 2022-08-23
200883C-500-DW-1821-4016 | [D] | 200883C | 500 | DW | 1821 | 4016 |  | 0 |  | Piperack Module - PR4- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-08-30 | 2022-08-30
200883C-500-DW-1821-4016 | [D] | 200883C | 500 | DW | 1821 | 4016 |  | 0 |  | Piperack Module - PR4- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4017 | [D] | 200883C | 500 | DW | 1821 | 4017 |  | 0 |  | Piperack Module - PR4- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-08-23 | 2022-08-23
200883C-500-DW-1821-4017 | [D] | 200883C | 500 | DW | 1821 | 4017 |  | 0 |  | Piperack Module - PR4- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-08-30 | 2022-08-30
200883C-500-DW-1821-4017 | [D] | 200883C | 500 | DW | 1821 | 4017 |  | 0 |  | Piperack Module - PR4- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4018 | [D] | 200883C | 500 | DW | 1821 | 4018 |  | 0 |  | Piperack Module - PR4- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-08-23 | 2022-08-23
200883C-500-DW-1821-4018 | [D] | 200883C | 500 | DW | 1821 | 4018 |  | 0 |  | Piperack Module - PR4- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-08-30 | 2022-08-30
200883C-500-DW-1821-4018 | [D] | 200883C | 500 | DW | 1821 | 4018 |  | 0 |  | Piperack Module - PR4- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4019 | [D] | 200883C | 500 | DW | 1821 | 4019 |  | 0 |  | Piperack Module - PR4- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-08-23 | 2022-08-23
200883C-500-DW-1821-4019 | [D] | 200883C | 500 | DW | 1821 | 4019 |  | 0 |  | Piperack Module - PR4- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-08-30 | 2022-08-30
200883C-500-DW-1821-4019 | [D] | 200883C | 500 | DW | 1821 | 4019 |  | 0 |  | Piperack Module - PR4- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1821-4020 | [D] | 200883C | 500 | DW | 1821 | 4020 |  | 0 |  | Piperack Module - PR4- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-08-23 | 2022-08-23
200883C-500-DW-1821-4020 | [D] | 200883C | 500 | DW | 1821 | 4020 |  | 0 |  | Piperack Module - PR4- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-08-30 | 2022-08-30
200883C-500-DW-1821-4020 | [D] | 200883C | 500 | DW | 1821 | 4020 |  | 0 |  | Piperack Module - PR4- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-DW-1824-4000 | [D] | 200883C | 500 | DW | 1824 | 4000 |  | 46 |  | Structural Layout for Battery Limit Platform | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-09-08 | 2022-09-08 | 2022-08-16 | 2022-08-16
200883C-500-DW-1824-4000 | [D] | 200883C | 500 | DW | 1824 | 4000 |  | 46 |  | Structural Layout for Battery Limit Platform | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-09-14 | 2022-09-14 | 2022-08-16 | 2022-08-16
200883C-500-DW-1824-4000 | [D] | 200883C | 500 | DW | 1824 | 4000 |  | 46 |  | Structural Layout for Battery Limit Platform | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-12-07 | 2022-12-07 | 2022-08-16 | 2022-08-16
200883C-500-DW-1824-4001 | [D] | 200883C | 500 | DW | 1824 | 4001 |  | 46 |  | Structural Details for Battery Limit Platform | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-09-08 | 2022-09-08 | 2022-08-16 | 2022-08-16
200883C-500-DW-1824-4001 | [D] | 200883C | 500 | DW | 1824 | 4001 |  | 46 |  | Structural Details for Battery Limit Platform | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-09-14 | 2022-09-14 | 2022-08-16 | 2022-08-16
200883C-500-DW-1824-4001 | [D] | 200883C | 500 | DW | 1824 | 4001 |  | 46 |  | Structural Details for Battery Limit Platform | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-12-07 | 2022-12-07 | 2022-08-16 | 2022-08-16
200883C-500-DW-1825-4000 | [D] | 200883C | 500 | DW | 1825 | 4000 |  | 77 |  | Structural Layout for Skid-1 | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-500-DW-1825-4000 | [D] | 200883C | 500 | DW | 1825 | 4000 |  | 77 |  | Structural Layout for Skid-1 | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-500-DW-1825-4000 | [D] | 200883C | 500 | DW | 1825 | 4000 |  | 77 |  | Structural Layout for Skid-1 | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-500-DW-1825-4001 | [D] | 200883C | 500 | DW | 1825 | 4001 |  | 77 |  | Structural Detailst for Skid-1 | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-500-DW-1825-4001 | [D] | 200883C | 500 | DW | 1825 | 4001 |  | 77 |  | Structural Detailst for Skid-1 | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-500-DW-1825-4001 | [D] | 200883C | 500 | DW | 1825 | 4001 |  | 77 |  | Structural Detailst for Skid-1 | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-12-14 | 2022-12-14 | 2022-12-14
200883C-500-DW-1825-4004 | [D] | 200883C | 500 | DW | 1825 | 4004 |  | 77 |  | Structural Layout for Pipe/Cable Tray Supports | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-500-DW-1825-4004 | [D] | 200883C | 500 | DW | 1825 | 4004 |  | 77 |  | Structural Layout for Pipe/Cable Tray Supports | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-DW-1825-4004 | [D] | 200883C | 500 | DW | 1825 | 4004 |  | 77 |  | Structural Layout for Pipe/Cable Tray Supports | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-DW-1825-4005 | [D] | 200883C | 500 | DW | 1825 | 4005 |  | 77 |  | Structural Layout for Pipe/Cable Tray Supports | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-500-DW-1825-4005 | [D] | 200883C | 500 | DW | 1825 | 4005 |  | 77 |  | Structural Layout for Pipe/Cable Tray Supports | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-DW-1825-4005 | [D] | 200883C | 500 | DW | 1825 | 4005 |  | 77 |  | Structural Layout for Pipe/Cable Tray Supports | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-DW-1825-4006 | [D] | 200883C | 500 | DW | 1825 | 4006 |  | 31 |  | Miscllaneous Supports/Access Way Details-1 | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-07-04 | 2022-07-04 | 2022-07-01 | 2022-07-01
200883C-500-DW-1825-4006 | [D] | 200883C | 500 | DW | 1825 | 4006 |  | 31 |  | Miscllaneous Supports/Access Way Details-1 | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-07-08 | 2022-07-08 | 2022-12-01
200883C-500-DW-1825-4006 | [D] | 200883C | 500 | DW | 1825 | 4006 |  | 31 |  | Miscllaneous Supports/Access Way Details-1 | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-07-29 | 2022-07-29 | 2022-12-22
200883C-500-DW-1825-4007 | [D] | 200883C | 500 | DW | 1825 | 4007 |  | 31 |  | Miscllaneous Supports/Access Way Details-2 | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-07-04 | 2022-07-04 | 2022-07-01 | 2022-07-01
200883C-500-DW-1825-4007 | [D] | 200883C | 500 | DW | 1825 | 4007 |  | 31 |  | Miscllaneous Supports/Access Way Details-2 | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-07-08 | 2022-07-08 | 2022-12-01
200883C-500-DW-1825-4007 | [D] | 200883C | 500 | DW | 1825 | 4007 |  | 31 |  | Miscllaneous Supports/Access Way Details-2 | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-07-29 | 2022-07-29 | 2022-12-22
200883C-500-DW-1825-4010 | [D] | 200883C | 500 | DW | 1825 | 4010 |  | 62 |  | Structural Layout- Support Structure for Prefabricated Substation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-500-DW-1825-4010 | [D] | 200883C | 500 | DW | 1825 | 4010 |  | 62 |  | Structural Layout- Support Structure for Prefabricated Substation | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-12-09 | 2022-12-09 | 2022-12-09
200883C-500-DW-1825-4010 | [D] | 200883C | 500 | DW | 1825 | 4010 |  | 62 |  | Structural Layout- Support Structure for Prefabricated Substation | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2023-02-10 | 2023-02-10 | 2023-02-10
200883C-500-DW-1825-4011 | [D] | 200883C | 500 | DW | 1825 | 4011 |  | 62 |  | Structural Details -Support Structure for Prefabricated Substation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-500-DW-1825-4011 | [D] | 200883C | 500 | DW | 1825 | 4011 |  | 62 |  | Structural Details -Support Structure for Prefabricated Substation | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-12-09 | 2022-12-09 | 2022-12-09
200883C-500-DW-1825-4011 | [D] | 200883C | 500 | DW | 1825 | 4011 |  | 62 |  | Structural Details -Support Structure for Prefabricated Substation | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2023-02-10 | 2023-02-10 | 2023-02-10
200883C-500-DW-2025-2000 | [D] | 200883C | 500 | DW | 2025 | 2000 |  | 0 |  | Yuri Phase 0 - H2 Ventilated Enclosure Architectural Conceptual Plans and Elevations | Code: E0302 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV |  | 2022-08-19 | 2022-08-19
200883C-500-DW-2025-2000 | [D] | 200883C | 500 | DW | 2025 | 2000 |  | 0 |  | Yuri Phase 0 - H2 Ventilated Enclosure Architectural Conceptual Plans and Elevations | Code: E0302 | CIV | 500H2 |  |  |  |  | IFI | 70 |  |  | BCIV |  | 2022-08-31 | 2022-08-31
200883C-500-DW-2025-2000 | [D] | 200883C | 500 | DW | 2025 | 2000 |  | 0 |  | Yuri Phase 0 - H2 Ventilated Enclosure Architectural Conceptual Plans and Elevations | Code: E0302 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV |  | 2022-09-30 | 2022-09-30
200883C-500-EL-4000 | [D] | 200883C | 500 | EL |  | 4000 |  | 24 |  | Yuri Phase 0 - Process Equipment List | Code: E0201 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-06-14 | 2022-06-14 | 2022-06-15 | 2022-06-15
200883C-500-EL-4000 | [D] | 200883C | 500 | EL |  | 4000 |  | 24 |  | Yuri Phase 0 - Process Equipment List | Code: E0201 | PRO | 500H2 |  |  |  |  | IFI | 100 |  |  | MPRO | 2022-06-18 | 2022-06-18 | 2022-06-15 | 2022-06-15
200883C-500-JSC-1450-2000 | [D] | 200883C | 500 | JSC | 1450 | 2000 |  | 75 |  | Yuri Phase 0 - Specification for Plant Roads and Pavements - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-05-30 | 2022-05-30 | 2022-06-03 | 2022-06-03
200883C-500-JSC-1450-2000 | [D] | 200883C | 500 | JSC | 1450 | 2000 |  | 75 |  | Yuri Phase 0 - Specification for Plant Roads and Pavements - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-06-03 | 2022-06-03 | 2022-06-28 | 2022-06-28
200883C-500-JSC-1450-2000 | [D] | 200883C | 500 | JSC | 1450 | 2000 |  | 75 |  | Yuri Phase 0 - Specification for Plant Roads and Pavements - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-07-01 | 2022-07-01 | 2022-07-01
200883C-500-JSC-1450-2001 | [D] | 200883C | 500 | JSC | 1450 | 2001 |  | 75 |  | Yuri Phase 0 - Specification for Stormwater Drainage- H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-06-06 | 2022-06-06 | 2022-06-10 | 2022-06-10
200883C-500-JSC-1450-2001 | [D] | 200883C | 500 | JSC | 1450 | 2001 |  | 75 |  | Yuri Phase 0 - Specification for Stormwater Drainage- H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-06-10 | 2022-06-10 | 2022-06-28 | 2022-06-28
200883C-500-JSC-1450-2001 | [D] | 200883C | 500 | JSC | 1450 | 2001 |  | 75 |  | Yuri Phase 0 - Specification for Stormwater Drainage- H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-07-08 | 2022-07-08 | 2022-08-16 | 2022-08-16
200883C-500-JSC-1450-2002 | [D] | 200883C | 500 | JSC | 1450 | 2002 |  | 75 |  | Yuri Phase 0 - Specification for Bulk Earthworks - H2 Plant | Code: E0303 | CIV | 000H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-05-30 | 2022-05-30 | 2022-06-03 | 2022-06-03
200883C-500-JSC-1450-2002 | [D] | 200883C | 500 | JSC | 1450 | 2002 |  | 75 |  | Yuri Phase 0 - Specification for Bulk Earthworks - H2 Plant | Code: E0303 | CIV | 000H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-06-03 | 2022-06-03 | 2022-06-22 | 2022-06-22
200883C-500-JSC-1450-2002 | [D] | 200883C | 500 | JSC | 1450 | 2002 |  | 75 |  | Yuri Phase 0 - Specification for Bulk Earthworks - H2 Plant | Code: E0303 | CIV | 000H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-07-01 | 2022-07-01 | 2022-07-29 | 2022-07-29
200883C-500-JSC-1700-2000 | [D] | 200883C | 500 | JSC | 1700 | 2000 |  | 75 |  | Yuri Phase 0 - Specification for Concrete Works | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-06-06 | 2022-06-06 | 2022-06-06 | 2022-06-06
200883C-500-JSC-1700-2000 | [D] | 200883C | 500 | JSC | 1700 | 2000 |  | 75 |  | Yuri Phase 0 - Specification for Concrete Works | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-06-10 | 2022-06-10 | 2022-07-06 | 2022-07-06
200883C-500-JSC-1700-2000 | [D] | 200883C | 500 | JSC | 1700 | 2000 |  | 75 |  | Yuri Phase 0 - Specification for Concrete Works | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-07-08 | 2022-07-08 | 2022-08-22 | 2022-08-22
200883C-500-JSD-0400-1000 | [D] | 200883C | 500 | JSD | 400 | 1000 |  | 200 |  | Yuri Phase 0 - Functional Specification for Electrolyser Package | Code: E0303 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | AMEC | 2022-04-02 | 2022-04-02 | 2022-05-24 | 2022-05-24
200883C-500-JSD-0400-1000 | [D] | 200883C | 500 | JSD | 400 | 1000 |  | 200 |  | Yuri Phase 0 - Functional Specification for Electrolyser Package | Code: E0303 | MEC | 500H2 |  |  |  |  | IFR | 70 |  |  | AMEC | 2022-04-02 | 2022-04-02 | 2022-05-24 | 2022-05-24
200883C-500-JSD-0400-1000 | [D] | 200883C | 500 | JSD | 400 | 1000 |  | 200 |  | Yuri Phase 0 - Functional Specification for Electrolyser Package | Code: E0303 | MEC | 500H2 |  |  |  |  | IFC | 100 |  |  | AMEC | 2022-07-16 | 2022-07-16 | 2022-07-13 | 2022-07-13
200883C-500-JSD-1400-2000 | [D] | 200883C | 500 | JSD | 1400 | 2000 |  | 99 |  | Yuri Phase 0 - Basis Of Design For Civil Works - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-05-25 | 2022-05-25 | 2022-05-25 | 2022-05-25
200883C-500-JSD-1400-2000 | [D] | 200883C | 500 | JSD | 1400 | 2000 |  | 99 |  | Yuri Phase 0 - Basis Of Design For Civil Works - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-05-31 | 2022-05-31 | 2022-06-22 | 2022-06-22
200883C-500-JSD-1400-2000 | [D] | 200883C | 500 | JSD | 1400 | 2000 |  | 99 |  | Yuri Phase 0 - Basis Of Design For Civil Works - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFD | 100 |  |  | BCIV | 2022-06-28 | 2022-06-28 | 2022-06-28
200883C-500-JSD-1510-1000 | [D] | 200883C | 500 | JSD | 1510 | 1000 |  | 240 |  | Yuri Phase 0 - Hydrogen Facility Control Philosophy | Code: E0303 | INS | 500H2 |  |  |  |  | STA | 10 |  |  | AINS | 2022-04-02 | 2022-04-02 | 2022-04-02 | 2022-04-02
200883C-500-JSD-1510-1000 | [D] | 200883C | 500 | JSD | 1510 | 1000 |  | 240 |  | Yuri Phase 0 - Hydrogen Facility Control Philosophy | Code: E0303 | INS | 500H2 |  |  |  |  | IFR | 70 |  |  | AINS | 2022-07-09 | 2022-07-09 | 2022-09-16
200883C-500-JSD-1510-1000 | [D] | 200883C | 500 | JSD | 1510 | 1000 |  | 240 |  | Yuri Phase 0 - Hydrogen Facility Control Philosophy | Code: E0303 | INS | 500H2 |  |  |  |  | IFC | 100 |  |  | AINS | 2022-08-31 | 2022-08-31 | 2022-10-17
200883C-500-JSS-0710-4000 | [D] | 200883C | 500 | JSS | 710 | 4000 |  | 113 |  | Yuri Phase 0 - Specification for Air Cooled Heat Exchanger | Code: E0201 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-06-13 | 2022-06-13 | 2022-06-13 | 2022-06-13
200883C-500-JSS-0710-4000 | [D] | 200883C | 500 | JSS | 710 | 4000 |  | 113 |  | Yuri Phase 0 - Specification for Air Cooled Heat Exchanger | Code: E0201 | MEC | 500H2 |  |  |  |  | IFI | 100 |  |  | MMEC | 2022-06-24 | 2022-06-24 | 2022-06-30 | 2022-06-30
200883C-500-JSS-0811-4000 | [D] | 200883C | 500 | JSS | 811 | 4000 |  | 46 |  | Yuri Phase 0 - Specification for Vessels | Code: E0311 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-06-09 | 2022-06-09 | 2022-06-09 | 2022-06-09
200883C-500-JSS-0811-4000 | [D] | 200883C | 500 | JSS | 811 | 4000 |  | 46 |  | Yuri Phase 0 - Specification for Vessels | Code: E0311 | MEC | 500H2 |  |  |  |  | IFR | 70 |  |  | MMEC | 2022-06-22 | 2022-06-22 | 2022-07-01 | 2022-07-01
200883C-500-JSS-0811-4000 | [D] | 200883C | 500 | JSS | 811 | 4000 |  | 46 |  | Yuri Phase 0 - Specification for Vessels | Code: E0311 | MEC | 500H2 |  |  |  |  | IFU | 100 |  |  | MMEC | 2022-07-20 | 2022-07-20 | 2022-07-21 | 2022-07-21
200883C-500-JSS-0910-4000 | [D] | 200883C | 500 | JSS | 910 | 4000 |  | 45 |  | Yuri Phase 0 - Specification for Centrifugal Pumps | Code: E0201 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-06-14
200883C-500-JSS-0910-4000 | [D] | 200883C | 500 | JSS | 910 | 4000 |  | 45 |  | Yuri Phase 0 - Specification for Centrifugal Pumps | Code: E0201 | MEC | 500H2 |  |  |  |  | IFI | 100 |  |  | MMEC | 2022-06-24 | 2022-06-24 | 2022-07-01 | 2022-07-01
200883C-500-JSS-1641-4000 | [D] | 200883C | 500 | JSS | 1641 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Distribution Oil Filled Transformer - H2 Plant | Code: E0301 | ELE | 500H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-05-25 | 2022-05-25 | 2022-05-25 | 2022-05-25
200883C-500-JSS-1641-4000 | [D] | 200883C | 500 | JSS | 1641 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Distribution Oil Filled Transformer - H2 Plant | Code: E0301 | ELE | 500H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-05-31 | 2022-05-31 | 2022-06-03 | 2022-06-03
200883C-500-JSS-1641-4000 | [D] | 200883C | 500 | JSS | 1641 | 4000 |  | 21 |  | Yuri Phase 0 - Specification for Distribution Oil Filled Transformer - H2 Plant | Code: E0301 | ELE | 500H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-06-21 | 2022-06-21 | 2022-07-29 | 2022-07-29
200883C-500-JSS-1680-1000 | [D] | 200883C | 500 | JSS | 1680 | 1000 |  | 120 |  | Yuri Phase 0 - Electrolyser Package Electrical - Instrumentation and Control Specification | Code: E0304 | ELE | 500H2 |  |  |  |  | STA | 10 |  |  | AELE | 2022-04-26 | 2022-04-26 | 2022-05-26 | 2022-05-26
200883C-500-JSS-1680-1000 | [D] | 200883C | 500 | JSS | 1680 | 1000 |  | 120 |  | Yuri Phase 0 - Electrolyser Package Electrical - Instrumentation and Control Specification | Code: E0304 | ELE | 500H2 |  |  |  |  | IFD | 70 |  |  | AELE | 2022-05-16 | 2022-05-16 | 2022-05-26 | 2022-05-26
200883C-500-JSS-1680-1000 | [D] | 200883C | 500 | JSS | 1680 | 1000 |  | 120 |  | Yuri Phase 0 - Electrolyser Package Electrical - Instrumentation and Control Specification | Code: E0304 | ELE | 500H2 |  |  |  |  | IFC | 100 |  |  | AELE | 2022-08-31 | 2022-08-31 | 2022-08-31
200883C-500-JSS-1700-1000 | [D] | 200883C | 500 | JSS | 1700 | 1000 |  | 103 |  | Yuri Phase 0 - Specification for Vented Enclosure | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | ASTR | 2022-07-19 | 2022-07-19 | 2022-08-22
200883C-500-JSS-1700-1000 | [D] | 200883C | 500 | JSS | 1700 | 1000 |  | 103 |  | Yuri Phase 0 - Specification for Vented Enclosure | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | ASTR | 2022-08-08 | 2022-08-08 | 2022-09-09
200883C-500-JSS-1700-1000 | [D] | 200883C | 500 | JSS | 1700 | 1000 |  | 103 |  | Yuri Phase 0 - Specification for Vented Enclosure | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | ASTR | 2022-09-05 | 2022-09-05 | 2022-10-10
200883C-500-JSS-4064-4000 | [D] | 200883C | 500 | JSS | 4064 | 4000 |  | 45 |  | Specification for Handling Equipment (required for items in MOC scope) | Code: E0201 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-12-15 | 2022-12-15 | 2022-12-15
200883C-500-JSS-4064-4000 | [D] | 200883C | 500 | JSS | 4064 | 4000 |  | 45 |  | Specification for Handling Equipment (required for items in MOC scope) | Code: E0201 | MEC | 500H2 |  |  |  |  | IFI | 100 |  |  | MMEC | 2022-12-28 | 2022-12-28 | 2022-12-28
200883C-500-JSS-4150-4000 | [D] | 200883C | 500 | JSS | 4150 | 4000 |  | 113 |  | Yuri Phase 0 - Specification for Refrigeration Package | Code: E0311 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-05-24 | 2022-05-24 | 2022-05-24 | 2022-05-24
200883C-500-JSS-4150-4000 | [D] | 200883C | 500 | JSS | 4150 | 4000 |  | 113 |  | Yuri Phase 0 - Specification for Refrigeration Package | Code: E0311 | MEC | 500H2 |  |  |  |  | IFR | 70 |  |  | MMEC | 2022-06-06 | 2022-06-06 | 2022-06-16 | 2022-06-16
200883C-500-JSS-4150-4000 | [D] | 200883C | 500 | JSS | 4150 | 4000 |  | 113 |  | Yuri Phase 0 - Specification for Refrigeration Package | Code: E0311 | MEC | 500H2 |  |  |  |  | IFU | 100 |  |  | MMEC | 2022-07-04 | 2022-07-04 | 2022-07-12 | 2022-07-12
200883C-500-MR-0400-1000 | [D] | 200883C | 500 | MR | 400 | 1000 |  | 200 |  | Yuri Phase 0 - Material Requisition for Electrolyser Package | Code: E0301 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | AMEC | 2022-06-10 | 2022-06-10 | 2022-05-24 | 2022-05-24
200883C-500-MR-0400-1000 | [D] | 200883C | 500 | MR | 400 | 1000 |  | 200 |  | Yuri Phase 0 - Material Requisition for Electrolyser Package | Code: E0301 | MEC | 500H2 |  |  |  |  | IFR | 70 |  |  | AMEC | 2022-06-23 | 2022-06-23 | 2022-05-24 | 2022-05-24
200883C-500-MR-0400-1000 | [D] | 200883C | 500 | MR | 400 | 1000 |  | 200 |  | Yuri Phase 0 - Material Requisition for Electrolyser Package | Code: E0301 | MEC | 500H2 |  |  |  |  | IFD | 100 |  |  | AMEC | 2022-07-31 | 2022-07-31 | 2022-07-12 | 2022-07-12
200883C-500-MR-0710-4000 | [D] | 200883C | 500 | MR | 710 | 4000 |  | 203 |  | MR for Air Cooled Heat Exchanger | Code: E0610 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-06-27 | 2022-06-27 | 2022-06-27 | 2022-06-27
200883C-500-MR-0710-4000 | [D] | 200883C | 500 | MR | 710 | 4000 |  | 203 |  | MR for Air Cooled Heat Exchanger | Code: E0610 | MEC | 500H2 |  |  |  |  | IFQ | 40 |  |  | MMEC | 2022-07-01 | 2022-07-01 | 2022-07-05 | 2022-07-05
200883C-500-MR-0710-4000 | [D] | 200883C | 500 | MR | 710 | 4000 |  | 203 |  | MR for Air Cooled Heat Exchanger | Code: E0610 | MEC | 500H2 |  |  |  |  | IFP | 70 |  |  | MMEC | 2022-10-19 | 2022-10-19 | 2022-10-19
200883C-500-MR-0710-4000 | [D] | 200883C | 500 | MR | 710 | 4000 |  | 203 |  | MR for Air Cooled Heat Exchanger | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR1 | 80 |  |  | MMEC | 2022-11-30 | 2022-11-30 | 2022-11-30
200883C-500-MR-0710-4000 | [D] | 200883C | 500 | MR | 710 | 4000 |  | 203 |  | MR for Air Cooled Heat Exchanger | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR2 | 90 |  |  | MMEC | 2022-12-30 | 2022-12-30 | 2022-12-30
200883C-500-MR-0710-4000 | [D] | 200883C | 500 | MR | 710 | 4000 |  | 203 |  | MR for Air Cooled Heat Exchanger | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR3 | 100 |  |  | MMEC | 2023-02-03 | 2023-02-03 | 2023-02-03
200883C-500-MR-0811-4000 | [D] | 200883C | 500 | MR | 811 | 4000 |  | 136 |  | MR for Vessels (Instrument Air storage vessel) | Code: E0610 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-06-23 | 2022-06-23 | 2022-06-23 | 2022-06-23
200883C-500-MR-0811-4000 | [D] | 200883C | 500 | MR | 811 | 4000 |  | 136 |  | MR for Vessels (Instrument Air storage vessel) | Code: E0610 | MEC | 500H2 |  |  |  |  | IFQ | 40 |  |  | MMEC | 2022-06-29 | 2022-06-29 | 2022-08-11 | 2022-08-11
200883C-500-MR-0811-4000 | [D] | 200883C | 500 | MR | 811 | 4000 |  | 136 |  | MR for Vessels (Instrument Air storage vessel) | Code: E0610 | MEC | 500H2 |  |  |  |  | IFP | 70 |  |  | MMEC | 2022-09-30 | 2022-09-30 | 2022-09-30
200883C-500-MR-0811-4000 | [D] | 200883C | 500 | MR | 811 | 4000 |  | 136 |  | MR for Vessels (Instrument Air storage vessel) | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR1 | 80 |  |  | MMEC | 2022-11-11 | 2022-11-11 | 2022-11-11
200883C-500-MR-0811-4000 | [D] | 200883C | 500 | MR | 811 | 4000 |  | 136 |  | MR for Vessels (Instrument Air storage vessel) | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR2 | 90 |  |  | MMEC | 2022-12-11 | 2022-12-11 | 2022-12-11
200883C-500-MR-0811-4000 | [D] | 200883C | 500 | MR | 811 | 4000 |  | 136 |  | MR for Vessels (Instrument Air storage vessel) | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR3 | 100 |  |  | MMEC | 2023-01-15 | 2023-01-15 | 2023-01-15
200883C-500-MR-0910-4000 | [D] | 200883C | 500 | MR | 910 | 4000 |  | 90 |  | MR for Centrifugal Pumps (Cooling Water, Chilled Water Circulation, Potable Water) | Code: E0610 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-06-14 | 2022-06-14 | 2022-06-14 | 2022-06-14
200883C-500-MR-0910-4000 | [D] | 200883C | 500 | MR | 910 | 4000 |  | 90 |  | MR for Centrifugal Pumps (Cooling Water, Chilled Water Circulation, Potable Water) | Code: E0610 | MEC | 500H2 |  |  |  |  | IFQ | 40 |  |  | MMEC | 2022-06-27 | 2022-06-27 | 2022-07-05 | 2022-07-05
200883C-500-MR-0910-4000 | [D] | 200883C | 500 | MR | 910 | 4000 |  | 90 |  | MR for Centrifugal Pumps (Cooling Water, Chilled Water Circulation, Potable Water) | Code: E0610 | MEC | 500H2 |  |  |  |  | IFP | 70 |  |  | MMEC | 2022-10-24 | 2022-10-24 | 2022-10-24
200883C-500-MR-0910-4000 | [D] | 200883C | 500 | MR | 910 | 4000 |  | 90 |  | MR for Centrifugal Pumps (Cooling Water, Chilled Water Circulation, Potable Water) | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR1 | 80 |  |  | MMEC | 2022-12-05 | 2022-12-05 | 2022-12-05
200883C-500-MR-0910-4000 | [D] | 200883C | 500 | MR | 910 | 4000 |  | 90 |  | MR for Centrifugal Pumps (Cooling Water, Chilled Water Circulation, Potable Water) | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR2 | 90 |  |  | MMEC | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-MR-0910-4000 | [D] | 200883C | 500 | MR | 910 | 4000 |  | 90 |  | MR for Centrifugal Pumps (Cooling Water, Chilled Water Circulation, Potable Water) | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR3 | 100 |  |  | MMEC | 2023-02-08 | 2023-02-08 | 2023-02-08
200883C-500-MR-1310-4000 | [D] | 200883C | 500 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Cast Gate Globe Check Valve | Code: E0610 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-06 | 2022-09-06 | 2022-09-06
200883C-500-MR-1310-4000 | [D] | 200883C | 500 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Cast Gate Globe Check Valve | Code: E0610 | PIP | 500H2 |  |  |  |  | IFQ | 40 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1310-4000 | [D] | 200883C | 500 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Cast Gate Globe Check Valve | Code: E0610 | PIP | 500H2 |  |  |  |  | IFP | 70 |  |  | MPIP | 2023-01-02 | 2023-01-02 | 2023-01-02
200883C-500-MR-1310-4000 | [D] | 200883C | 500 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Cast Gate Globe Check Valve | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR1 | 80 |  |  | MPIP | 2023-02-06 | 2023-02-06 | 2023-02-06
200883C-500-MR-1310-4000 | [D] | 200883C | 500 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Cast Gate Globe Check Valve | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR2 | 90 |  |  | MPIP | 2023-03-06 | 2023-03-06 | 2023-03-06
200883C-500-MR-1310-4000 | [D] | 200883C | 500 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Cast Gate Globe Check Valve | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR3 | 100 |  |  | MPIP | 2023-04-03 | 2023-04-03 | 2023-04-03
200883C-500-MR-1310-4001 | [D] | 200883C | 500 | MR | 1310 | 4001 |  | 23 |  | Yuri Phase 0-MR for Ball Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-06 | 2022-09-06 | 2022-09-06
200883C-500-MR-1310-4001 | [D] | 200883C | 500 | MR | 1310 | 4001 |  | 23 |  | Yuri Phase 0-MR for Ball Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | IFQ | 40 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1310-4001 | [D] | 200883C | 500 | MR | 1310 | 4001 |  | 23 |  | Yuri Phase 0-MR for Ball Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | IFP | 70 |  |  | MPIP | 2023-01-02 | 2023-01-02 | 2023-01-02
200883C-500-MR-1310-4001 | [D] | 200883C | 500 | MR | 1310 | 4001 |  | 23 |  | Yuri Phase 0-MR for Ball Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR1 | 80 |  |  | MPIP | 2023-02-06 | 2023-02-06 | 2023-02-06
200883C-500-MR-1310-4001 | [D] | 200883C | 500 | MR | 1310 | 4001 |  | 23 |  | Yuri Phase 0-MR for Ball Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR2 | 90 |  |  | MPIP | 2023-03-06 | 2023-03-06 | 2023-03-06
200883C-500-MR-1310-4001 | [D] | 200883C | 500 | MR | 1310 | 4001 |  | 23 |  | Yuri Phase 0-MR for Ball Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR3 | 100 |  |  | MPIP | 2023-04-03 | 2023-04-03 | 2023-04-03
200883C-500-MR-1310-4002 | [D] | 200883C | 500 | MR | 1310 | 4002 |  | 23 |  | Yuri Phase 0-MR for Butterfly Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-06 | 2022-09-06 | 2022-09-06
200883C-500-MR-1310-4002 | [D] | 200883C | 500 | MR | 1310 | 4002 |  | 23 |  | Yuri Phase 0-MR for Butterfly Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | IFQ | 40 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1310-4002 | [D] | 200883C | 500 | MR | 1310 | 4002 |  | 23 |  | Yuri Phase 0-MR for Butterfly Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | IFP | 70 |  |  | MPIP | 2023-01-02 | 2023-01-02 | 2023-01-02
200883C-500-MR-1310-4002 | [D] | 200883C | 500 | MR | 1310 | 4002 |  | 23 |  | Yuri Phase 0-MR for Butterfly Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR1 | 80 |  |  | MPIP | 2023-02-06 | 2023-02-06 | 2023-02-06
200883C-500-MR-1310-4002 | [D] | 200883C | 500 | MR | 1310 | 4002 |  | 23 |  | Yuri Phase 0-MR for Butterfly Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR2 | 90 |  |  | MPIP | 2023-03-06 | 2023-03-06 | 2023-03-06
200883C-500-MR-1310-4002 | [D] | 200883C | 500 | MR | 1310 | 4002 |  | 23 |  | Yuri Phase 0-MR for Butterfly Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR3 | 100 |  |  | MPIP | 2023-04-03 | 2023-04-03 | 2023-04-03
200883C-500-MR-1310-4003 | [D] | 200883C | 500 | MR | 1310 | 4003 |  | 23 |  | Yuri Phase 0-MR for Dual Plate Check Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-06 | 2022-09-06 | 2022-09-06
200883C-500-MR-1310-4003 | [D] | 200883C | 500 | MR | 1310 | 4003 |  | 23 |  | Yuri Phase 0-MR for Dual Plate Check Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | IFQ | 40 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1310-4003 | [D] | 200883C | 500 | MR | 1310 | 4003 |  | 23 |  | Yuri Phase 0-MR for Dual Plate Check Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | IFP | 70 |  |  | MPIP | 2023-01-02 | 2023-01-02 | 2023-01-02
200883C-500-MR-1310-4003 | [D] | 200883C | 500 | MR | 1310 | 4003 |  | 23 |  | Yuri Phase 0-MR for Dual Plate Check Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR1 | 80 |  |  | MPIP | 2023-02-06 | 2023-02-06 | 2023-02-06
200883C-500-MR-1310-4003 | [D] | 200883C | 500 | MR | 1310 | 4003 |  | 23 |  | Yuri Phase 0-MR for Dual Plate Check Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR2 | 90 |  |  | MPIP | 2023-03-06 | 2023-03-06 | 2023-03-06
200883C-500-MR-1310-4003 | [D] | 200883C | 500 | MR | 1310 | 4003 |  | 23 |  | Yuri Phase 0-MR for Dual Plate Check Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR3 | 100 |  |  | MPIP | 2023-04-03 | 2023-04-03 | 2023-04-03
200883C-500-MR-1320-4000 | [D] | 200883C | 500 | MR | 1320 | 4000 |  | 23 |  | Yuri Phase 0-MR for LTCS,CS Seamless Pipes | Code: E0310 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1320-4000 | [D] | 200883C | 500 | MR | 1320 | 4000 |  | 23 |  | Yuri Phase 0-MR for LTCS,CS Seamless Pipes | Code: E0310 | PIP | 500H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-09-20 | 2022-09-20 | 2022-09-20
200883C-500-MR-1320-4000 | [D] | 200883C | 500 | MR | 1320 | 4000 |  | 23 |  | Yuri Phase 0-MR for LTCS,CS Seamless Pipes | Code: E0310 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2023-01-09 | 2023-01-09 | 2023-01-09
200883C-500-MR-1320-4001 | [D] | 200883C | 500 | MR | 1320 | 4001 |  | 23 |  | Yuri Phase 0-MR for LTCS,CS Welded ,Galvanized Pipes | Code: E0310 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1320-4001 | [D] | 200883C | 500 | MR | 1320 | 4001 |  | 23 |  | Yuri Phase 0-MR for LTCS,CS Welded ,Galvanized Pipes | Code: E0310 | PIP | 500H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-09-20 | 2022-09-20 | 2022-09-20
200883C-500-MR-1320-4001 | [D] | 200883C | 500 | MR | 1320 | 4001 |  | 23 |  | Yuri Phase 0-MR for LTCS,CS Welded ,Galvanized Pipes | Code: E0310 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2023-01-09 | 2023-01-09 | 2023-01-09
200883C-500-MR-1324-4000 | [D] | 200883C | 500 | MR | 1324 | 4000 |  | 23 |  | Yuri Phase 0-MR for SS Seamless/ Welded Pipes | Code: E0310 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1324-4000 | [D] | 200883C | 500 | MR | 1324 | 4000 |  | 23 |  | Yuri Phase 0-MR for SS Seamless/ Welded Pipes | Code: E0310 | PIP | 500H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-09-20 | 2022-09-20 | 2022-09-20
200883C-500-MR-1324-4000 | [D] | 200883C | 500 | MR | 1324 | 4000 |  | 23 |  | Yuri Phase 0-MR for SS Seamless/ Welded Pipes | Code: E0310 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-12-29 | 2022-12-29 | 2022-12-29
200883C-500-MR-1330-4000 | [D] | 200883C | 500 | MR | 1330 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Wrought Fittings | Code: E0310 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1330-4000 | [D] | 200883C | 500 | MR | 1330 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Wrought Fittings | Code: E0310 | PIP | 500H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-09-20 | 2022-09-20 | 2022-09-20
200883C-500-MR-1330-4000 | [D] | 200883C | 500 | MR | 1330 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Wrought Fittings | Code: E0310 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2023-01-09 | 2023-01-09 | 2023-01-09
200883C-500-MR-1340-4000 | [D] | 200883C | 500 | MR | 1340 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Fittings | Code: E0310 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1340-4000 | [D] | 200883C | 500 | MR | 1340 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Fittings | Code: E0310 | PIP | 500H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-09-20 | 2022-09-20 | 2022-09-20
200883C-500-MR-1340-4000 | [D] | 200883C | 500 | MR | 1340 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Fittings | Code: E0310 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2023-01-09 | 2023-01-09 | 2023-01-09
200883C-500-MR-1350-4000 | [D] | 200883C | 500 | MR | 1350 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS Flanges, Spectacle Blinds, Paddle & Blanks | Code: E0310 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-500-MR-1350-4000 | [D] | 200883C | 500 | MR | 1350 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS Flanges, Spectacle Blinds, Paddle & Blanks | Code: E0310 | PIP | 500H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-10-04 | 2022-10-04 | 2022-10-04
200883C-500-MR-1350-4000 | [D] | 200883C | 500 | MR | 1350 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS Flanges, Spectacle Blinds, Paddle & Blanks | Code: E0310 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2023-01-05 | 2023-01-05 | 2023-01-05
200883C-500-MR-1360-4000 | [D] | 200883C | 500 | MR | 1360 | 4000 |  | 23 |  | Yuri Phase 0-MR for Gaskets | Code: E0310 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-500-MR-1360-4000 | [D] | 200883C | 500 | MR | 1360 | 4000 |  | 23 |  | Yuri Phase 0-MR for Gaskets | Code: E0310 | PIP | 500H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-10-04 | 2022-10-04 | 2022-10-04
200883C-500-MR-1360-4000 | [D] | 200883C | 500 | MR | 1360 | 4000 |  | 23 |  | Yuri Phase 0-MR for Gaskets | Code: E0310 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2023-01-23 | 2023-01-23 | 2023-01-23
200883C-500-MR-1370-4000 | [D] | 200883C | 500 | MR | 1370 | 4000 |  | 23 |  | Yuri Phase 0-MR for Machine Bolts, Stud Bolts & Nuts | Code: E0310 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-500-MR-1370-4000 | [D] | 200883C | 500 | MR | 1370 | 4000 |  | 23 |  | Yuri Phase 0-MR for Machine Bolts, Stud Bolts & Nuts | Code: E0310 | PIP | 500H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-10-04 | 2022-10-04 | 2022-10-04
200883C-500-MR-1370-4000 | [D] | 200883C | 500 | MR | 1370 | 4000 |  | 23 |  | Yuri Phase 0-MR for Machine Bolts, Stud Bolts & Nuts | Code: E0310 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2023-01-23 | 2023-01-23 | 2023-01-23
200883C-500-MR-1383-4000 | [D] | 200883C | 500 | MR | 1383 | 4000 |  | 23 |  | Yuri Phase 0-MR for Spring Hangers / Spring / Rigid Strut Supports | Code: E0610 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-500-MR-1383-4000 | [D] | 200883C | 500 | MR | 1383 | 4000 |  | 23 |  | Yuri Phase 0-MR for Spring Hangers / Spring / Rigid Strut Supports | Code: E0610 | PIP | 500H2 |  |  |  |  | IFQ | 40 |  |  | MPIP | 2022-10-04 | 2022-10-04 | 2022-10-04
200883C-500-MR-1383-4000 | [D] | 200883C | 500 | MR | 1383 | 4000 |  | 23 |  | Yuri Phase 0-MR for Spring Hangers / Spring / Rigid Strut Supports | Code: E0610 | PIP | 500H2 |  |  |  |  | IFP | 70 |  |  | MPIP | 2023-01-30 | 2023-01-30 | 2023-01-30
200883C-500-MR-1383-4000 | [D] | 200883C | 500 | MR | 1383 | 4000 |  | 23 |  | Yuri Phase 0-MR for Spring Hangers / Spring / Rigid Strut Supports | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR1 | 80 |  |  | MPIP | 2023-03-06 | 2023-03-06 | 2023-03-06
200883C-500-MR-1383-4000 | [D] | 200883C | 500 | MR | 1383 | 4000 |  | 23 |  | Yuri Phase 0-MR for Spring Hangers / Spring / Rigid Strut Supports | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR2 | 90 |  |  | MPIP | 2023-04-03 | 2023-04-03 | 2023-04-03
200883C-500-MR-1383-4000 | [D] | 200883C | 500 | MR | 1383 | 4000 |  | 23 |  | Yuri Phase 0-MR for Spring Hangers / Spring / Rigid Strut Supports | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR3 | 100 |  |  | MPIP | 2023-05-01 | 2023-05-01 | 2023-05-01
200883C-500-MR-1383-4003 | [D] | 200883C | 500 | MR | 1383 | 4003 |  | 23 |  | Yuri Phase 0-MR for Anti- vibrating clamp and sliding plates | Code: E0610 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-12-21 | 2022-12-21 | 2022-12-21
200883C-500-MR-1383-4003 | [D] | 200883C | 500 | MR | 1383 | 4003 |  | 23 |  | Yuri Phase 0-MR for Anti- vibrating clamp and sliding plates | Code: E0610 | PIP | 500H2 |  |  |  |  | IFQ | 40 |  |  | MPIP | 2022-12-28 | 2022-12-28 | 2022-12-28
200883C-500-MR-1383-4003 | [D] | 200883C | 500 | MR | 1383 | 4003 |  | 23 |  | Yuri Phase 0-MR for Anti- vibrating clamp and sliding plates | Code: E0610 | PIP | 500H2 |  |  |  |  | IFP | 70 |  |  | MPIP | 2023-03-23 | 2023-03-23 | 2023-03-23
200883C-500-MR-1383-4003 | [D] | 200883C | 500 | MR | 1383 | 4003 |  | 23 |  | Yuri Phase 0-MR for Anti- vibrating clamp and sliding plates | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR1 | 80 |  |  | MPIP | 2023-04-27 | 2023-04-27 | 2023-04-27
200883C-500-MR-1383-4003 | [D] | 200883C | 500 | MR | 1383 | 4003 |  | 23 |  | Yuri Phase 0-MR for Anti- vibrating clamp and sliding plates | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR2 | 90 |  |  | MPIP | 2023-05-25 | 2023-05-25 | 2023-05-25
200883C-500-MR-1383-4003 | [D] | 200883C | 500 | MR | 1383 | 4003 |  | 23 |  | Yuri Phase 0-MR for Anti- vibrating clamp and sliding plates | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR3 | 100 |  |  | MPIP | 2023-06-22 | 2023-06-22 | 2023-06-22
200883C-500-MR-1394-4000 | [D] | 200883C | 500 | MR | 1394 | 4000 |  | 23 |  | Yuri Phase 0-MR for Flexible Hoses, Quick-Connect Couplers & Adaptors | Code: E0610 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-500-MR-1394-4000 | [D] | 200883C | 500 | MR | 1394 | 4000 |  | 23 |  | Yuri Phase 0-MR for Flexible Hoses, Quick-Connect Couplers & Adaptors | Code: E0610 | PIP | 500H2 |  |  |  |  | IFQ | 40 |  |  | MPIP | 2022-10-04 | 2022-10-04 | 2022-10-04
200883C-500-MR-1394-4000 | [D] | 200883C | 500 | MR | 1394 | 4000 |  | 23 |  | Yuri Phase 0-MR for Flexible Hoses, Quick-Connect Couplers & Adaptors | Code: E0610 | PIP | 500H2 |  |  |  |  | IFP | 70 |  |  | MPIP | 2023-01-30 | 2023-01-30 | 2023-01-30
200883C-500-MR-1394-4000 | [D] | 200883C | 500 | MR | 1394 | 4000 |  | 23 |  | Yuri Phase 0-MR for Flexible Hoses, Quick-Connect Couplers & Adaptors | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR1 | 80 |  |  | MPIP | 2023-03-06 | 2023-03-06 | 2023-03-06
200883C-500-MR-1394-4000 | [D] | 200883C | 500 | MR | 1394 | 4000 |  | 23 |  | Yuri Phase 0-MR for Flexible Hoses, Quick-Connect Couplers & Adaptors | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR2 | 90 |  |  | MPIP | 2023-04-03 | 2023-04-03 | 2023-04-03
200883C-500-MR-1394-4000 | [D] | 200883C | 500 | MR | 1394 | 4000 |  | 23 |  | Yuri Phase 0-MR for Flexible Hoses, Quick-Connect Couplers & Adaptors | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR3 | 100 |  |  | MPIP | 2023-05-01 | 2023-05-01 | 2023-05-01
200883C-500-MR-1395-4000 | [D] | 200883C | 500 | MR | 1395 | 4000 |  | 23 |  | Yuri Phase 0-MR for Strainers (T & Y type) | Code: E0610 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-500-MR-1395-4000 | [D] | 200883C | 500 | MR | 1395 | 4000 |  | 23 |  | Yuri Phase 0-MR for Strainers (T & Y type) | Code: E0610 | PIP | 500H2 |  |  |  |  | IFQ | 40 |  |  | MPIP | 2022-10-04 | 2022-10-04 | 2022-10-04
200883C-500-MR-1395-4000 | [D] | 200883C | 500 | MR | 1395 | 4000 |  | 23 |  | Yuri Phase 0-MR for Strainers (T & Y type) | Code: E0610 | PIP | 500H2 |  |  |  |  | IFP | 70 |  |  | MPIP | 2023-01-30 | 2023-01-30 | 2023-01-30
200883C-500-MR-1395-4000 | [D] | 200883C | 500 | MR | 1395 | 4000 |  | 23 |  | Yuri Phase 0-MR for Strainers (T & Y type) | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR1 | 80 |  |  | MPIP | 2023-03-06 | 2023-03-06 | 2023-03-06
200883C-500-MR-1395-4000 | [D] | 200883C | 500 | MR | 1395 | 4000 |  | 23 |  | Yuri Phase 0-MR for Strainers (T & Y type) | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR2 | 90 |  |  | MPIP | 2023-04-03 | 2023-04-03 | 2023-04-03
200883C-500-MR-1395-4000 | [D] | 200883C | 500 | MR | 1395 | 4000 |  | 23 |  | Yuri Phase 0-MR for Strainers (T & Y type) | Code: E0610 | PIP | 500H2 |  |  |  |  | VDR3 | 100 |  |  | MPIP | 2023-05-01 | 2023-05-01 | 2023-05-01
200883C-500-MR-1399-4002 | [D] | 200883C | 500 | MR | 1399 | 4002 |  | 23 |  | Yuri Phase 0-MR for U bolts & clamps | Code: E0310 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-12-21 | 2022-12-21 | 2022-12-21
200883C-500-MR-1399-4002 | [D] | 200883C | 500 | MR | 1399 | 4002 |  | 23 |  | Yuri Phase 0-MR for U bolts & clamps | Code: E0310 | PIP | 500H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-12-28 | 2022-12-28 | 2022-12-28
200883C-500-MR-1399-4002 | [D] | 200883C | 500 | MR | 1399 | 4002 |  | 23 |  | Yuri Phase 0-MR for U bolts & clamps | Code: E0310 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2023-03-30 | 2023-03-30 | 2023-03-30
200883C-500-MR-1900-4000 | [D] | 200883C | 500 | MR | 1900 | 4000 |  | 45 |  | MR for Safety Equipment | Code: E0610 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-07-01 | 2022-07-01 | 2022-07-01 | 2022-07-01
200883C-500-MR-1900-4000 | [D] | 200883C | 500 | MR | 1900 | 4000 |  | 45 |  | MR for Safety Equipment | Code: E0610 | MEC | 500H2 |  |  |  |  | IFQ | 40 |  |  | MMEC | 2022-07-07 | 2022-07-07 | 2022-07-07
200883C-500-MR-1900-4000 | [D] | 200883C | 500 | MR | 1900 | 4000 |  | 45 |  | MR for Safety Equipment | Code: E0610 | MEC | 500H2 |  |  |  |  | IFP | 70 |  |  | MMEC | 2022-10-27 | 2022-10-27 | 2022-10-27
200883C-500-MR-1900-4000 | [D] | 200883C | 500 | MR | 1900 | 4000 |  | 45 |  | MR for Safety Equipment | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR1 | 80 |  |  | MMEC | 2022-12-08 | 2022-12-08 | 2022-12-08
200883C-500-MR-1900-4000 | [D] | 200883C | 500 | MR | 1900 | 4000 |  | 45 |  | MR for Safety Equipment | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR2 | 90 |  |  | MMEC | 2023-01-07 | 2023-01-07 | 2023-01-07
200883C-500-MR-1900-4000 | [D] | 200883C | 500 | MR | 1900 | 4000 |  | 45 |  | MR for Safety Equipment | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR3 | 100 |  |  | MMEC | 2023-02-11 | 2023-02-11 | 2023-02-11
200883C-500-MR-2600-1000 | [D] | 200883C | 500 | MR | 2600 | 1000 |  | 1 |  | Yuri Phase 0 - Electrolyser Chemicals (KOH and V2O5) | Code: E0303 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | APRO |  | 2022-09-02 | 2022-09-02
200883C-500-MR-2600-1000 | [D] | 200883C | 500 | MR | 2600 | 1000 |  | 1 |  | Yuri Phase 0 - Electrolyser Chemicals (KOH and V2O5) | Code: E0303 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | APRO |  | 2022-09-16 | 2022-09-16
200883C-500-MR-2600-1000 | [D] | 200883C | 500 | MR | 2600 | 1000 |  | 1 |  | Yuri Phase 0 - Electrolyser Chemicals (KOH and V2O5) | Code: E0303 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | APRO |  | 2022-10-07 | 2022-10-07
200883C-500-MR-4064-4000 | [D] | 200883C | 500 | MR | 4064 | 4000 |  | 90 |  | MR for Handling Equipment (required for items in MOC scope) | Code: E0610 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2023-02-10 | 2023-02-10 | 2023-02-10
200883C-500-MR-4064-4000 | [D] | 200883C | 500 | MR | 4064 | 4000 |  | 90 |  | MR for Handling Equipment (required for items in MOC scope) | Code: E0610 | MEC | 500H2 |  |  |  |  | IFQ | 40 |  |  | MMEC | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-MR-4064-4000 | [D] | 200883C | 500 | MR | 4064 | 4000 |  | 90 |  | MR for Handling Equipment (required for items in MOC scope) | Code: E0610 | MEC | 500H2 |  |  |  |  | IFP | 70 |  |  | MMEC | 2023-06-07 | 2023-06-07 | 2023-06-07
200883C-500-MR-4064-4000 | [D] | 200883C | 500 | MR | 4064 | 4000 |  | 90 |  | MR for Handling Equipment (required for items in MOC scope) | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR1 | 80 |  |  | MMEC | 2023-07-19 | 2023-07-19 | 2023-07-19
200883C-500-MR-4064-4000 | [D] | 200883C | 500 | MR | 4064 | 4000 |  | 90 |  | MR for Handling Equipment (required for items in MOC scope) | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR2 | 90 |  |  | MMEC | 2023-08-18 | 2023-08-18 | 2023-08-18
200883C-500-MR-4064-4000 | [D] | 200883C | 500 | MR | 4064 | 4000 |  | 90 |  | MR for Handling Equipment (required for items in MOC scope) | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR3 | 100 |  |  | MMEC | 2023-09-22 | 2023-09-22 | 2023-09-22
200883C-500-MR-4150-4000 | [D] | 200883C | 500 | MR | 4150 | 4000 |  | 202 |  | MR for Refrigeration package | Code: E0610 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-06-27 | 2022-06-27 | 2022-06-01 | 2022-06-01
200883C-500-MR-4150-4000 | [D] | 200883C | 500 | MR | 4150 | 4000 |  | 202 |  | MR for Refrigeration package | Code: E0610 | MEC | 500H2 |  |  |  |  | IFQ | 40 |  |  | MMEC | 2022-07-01 | 2022-07-01 | 2022-06-16 | 2022-06-16
200883C-500-MR-4150-4000 | [D] | 200883C | 500 | MR | 4150 | 4000 |  | 202 |  | MR for Refrigeration package | Code: E0610 | MEC | 500H2 |  |  |  |  | IFP | 70 |  |  | MMEC | 2022-10-21 | 2022-10-21 | 2022-10-21
200883C-500-MR-4150-4000 | [D] | 200883C | 500 | MR | 4150 | 4000 |  | 202 |  | MR for Refrigeration package | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR1 | 80 |  |  | MMEC | 2022-12-02 | 2022-12-02 | 2022-12-02
200883C-500-MR-4150-4000 | [D] | 200883C | 500 | MR | 4150 | 4000 |  | 202 |  | MR for Refrigeration package | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR2 | 90 |  |  | MMEC | 2023-01-01 | 2023-01-01 | 2023-01-01
200883C-500-MR-4150-4000 | [D] | 200883C | 500 | MR | 4150 | 4000 |  | 202 |  | MR for Refrigeration package | Code: E0610 | MEC | 500H2 |  |  |  |  | VDR3 | 100 |  |  | MMEC | 2023-02-05 | 2023-02-05 | 2023-02-05
200883C-500-MTO-1311-4000 | [D] | 200883C | 500 | MTO | 1311 | 4000 |  | 45 |  | Yuri Phase 0-Insulation MTO | Code: E0306 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-500-MTO-1311-4000 | [D] | 200883C | 500 | MTO | 1311 | 4000 |  | 45 |  | Yuri Phase 0-Insulation MTO | Code: E0306 | PIP | 500H2 |  |  |  |  | IFP1 | 70 |  |  | MPIP | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-MTO-1311-4000 | [D] | 200883C | 500 | MTO | 1311 | 4000 |  | 45 |  | Yuri Phase 0-Insulation MTO | Code: E0306 | PIP | 500H2 |  |  |  |  | IFP2 | 100 |  |  | MPIP | 2023-04-10 | 2023-04-10 | 2023-04-10
200883C-500-MTO-1311-4001 | [D] | 200883C | 500 | MTO | 1311 | 4001 |  | 45 |  | Yuri Phase 0-Painting MTO | Code: E0306 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-500-MTO-1311-4001 | [D] | 200883C | 500 | MTO | 1311 | 4001 |  | 45 |  | Yuri Phase 0-Painting MTO | Code: E0306 | PIP | 500H2 |  |  |  |  | IFP1 | 70 |  |  | MPIP | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-MTO-1311-4001 | [D] | 200883C | 500 | MTO | 1311 | 4001 |  | 45 |  | Yuri Phase 0-Painting MTO | Code: E0306 | PIP | 500H2 |  |  |  |  | IFP2 | 100 |  |  | MPIP | 2023-03-23 | 2023-03-23 | 2023-03-23
200883C-500-MTO-1311-4002 | [D] | 200883C | 500 | MTO | 1311 | 4002 |  | 23 |  | Yuri Phase 0-Support MTO | Code: E0306 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-01 | 2022-07-01 | 2022-07-01 | 2022-07-01
200883C-500-MTO-1311-4002 | [D] | 200883C | 500 | MTO | 1311 | 4002 |  | 23 |  | Yuri Phase 0-Support MTO | Code: E0306 | PIP | 500H2 |  |  |  |  | IFP1 | 70 |  |  | MPIP | 2022-12-21 | 2022-12-21 | 2022-12-21
200883C-500-MTO-1311-4002 | [D] | 200883C | 500 | MTO | 1311 | 4002 |  | 23 |  | Yuri Phase 0-Support MTO | Code: E0306 | PIP | 500H2 |  |  |  |  | IFP2 | 100 |  |  | MPIP | 2023-02-16 | 2023-02-16 | 2023-02-16
200883C-500-MTO-1311-4003 | [D] | 200883C | 500 | MTO | 1311 | 4003 |  | 338 |  | Yuri Phase 0-Piping Bulk MTO-1 | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-25 | 2022-07-25 | 2022-07-25 | 2022-07-25
200883C-500-MTO-1311-4003 | [D] | 200883C | 500 | MTO | 1311 | 4003 |  | 338 |  | Yuri Phase 0-Piping Bulk MTO-1 | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-09-06 | 2022-09-06 | 2022-09-06
200883C-500-MTO-1311-4004 | [D] | 200883C | 500 | MTO | 1311 | 4004 |  | 282 |  | Yuri Phase 0-Piping Bulk MTO-2 | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-500-MTO-1311-4004 | [D] | 200883C | 500 | MTO | 1311 | 4004 |  | 282 |  | Yuri Phase 0-Piping Bulk MTO-2 | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-12-21 | 2022-12-21 | 2022-12-21
200883C-500-MTO-1311-4005 | [D] | 200883C | 500 | MTO | 1311 | 4005 |  | 169 |  | Yuri Phase 0-Piping Bulk MTO-3 | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2023-02-10 | 2023-02-10 | 2023-02-10
200883C-500-MTO-1311-4005 | [D] | 200883C | 500 | MTO | 1311 | 4005 |  | 169 |  | Yuri Phase 0-Piping Bulk MTO-3 | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2023-02-23 | 2023-02-23 | 2023-02-23
200883C-500-MTO-1410-2000 | [D] | 200883C | 500 | MTO | 1410 | 2000 |  | 50 |  | Yuri Phase 0 - Earthwork MTO - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-07-19 | 2022-07-19 | 2022-07-19 | 2022-07-19
200883C-500-MTO-1410-2000 | [D] | 200883C | 500 | MTO | 1410 | 2000 |  | 50 |  | Yuri Phase 0 - Earthwork MTO - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-07-25 | 2022-07-25 | 2022-08-11 | 2022-08-11
200883C-500-MTO-1410-2000 | [D] | 200883C | 500 | MTO | 1410 | 2000 |  | 50 |  | Yuri Phase 0 - Earthwork MTO - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFD | 100 |  |  | BCIV | 2022-09-20 | 2022-09-20 | 2022-09-20
200883C-500-MTO-1410-2001 | [D] | 200883C | 500 | MTO | 1410 | 2001 |  | 50 |  | Yuri Phase 0 - Road - Pathway - graded track and car park MTO- H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-500-MTO-1410-2001 | [D] | 200883C | 500 | MTO | 1410 | 2001 |  | 50 |  | Yuri Phase 0 - Road - Pathway - graded track and car park MTO- H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-500-MTO-1410-2001 | [D] | 200883C | 500 | MTO | 1410 | 2001 |  | 50 |  | Yuri Phase 0 - Road - Pathway - graded track and car park MTO- H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFD | 100 |  |  | BCIV | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-MTO-1410-2002 | [D] | 200883C | 500 | MTO | 1410 | 2002 |  | 50 |  | Yuri Phase 0 - Stormwater Drainage MTO- H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-08-23 | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-500-MTO-1410-2002 | [D] | 200883C | 500 | MTO | 1410 | 2002 |  | 50 |  | Yuri Phase 0 - Stormwater Drainage MTO- H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-500-MTO-1410-2002 | [D] | 200883C | 500 | MTO | 1410 | 2002 |  | 50 |  | Yuri Phase 0 - Stormwater Drainage MTO- H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFD | 100 |  |  | BCIV | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-NM-0003-4000 | [D] | 200883C | 500 | NM | 3 | 4000 |  | 24 |  | Yuri Phase 0 - Utilities Summary Air - Nitrogen - Potable Water - Chemicals - etc | Code: E0311 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-09-13 | 2022-09-13 | 2022-06-23 | 2022-06-23
200883C-500-NM-0003-4000 | [D] | 200883C | 500 | NM | 3 | 4000 |  | 24 |  | Yuri Phase 0 - Utilities Summary Air - Nitrogen - Potable Water - Chemicals - etc | Code: E0311 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-09-19 | 2022-09-19 | 2022-06-23 | 2022-06-23
200883C-500-NM-0003-4000 | [D] | 200883C | 500 | NM | 3 | 4000 |  | 24 |  | Yuri Phase 0 - Utilities Summary Air - Nitrogen - Potable Water - Chemicals - etc | Code: E0311 | PRO | 500H2 |  |  |  |  | IFU | 100 |  |  | MPRO | 2022-10-17 | 2022-10-17 | 2022-07-25 | 2022-07-25
200883C-500-NM-0005-4000 | [D] | 200883C | 500 | NM | 5 | 4000 |  | 24 |  | Yuri Phase 0 - Overall Effluent List | Code: E0311 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-NM-0005-4000 | [D] | 200883C | 500 | NM | 5 | 4000 |  | 24 |  | Yuri Phase 0 - Overall Effluent List | Code: E0311 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-09-19 | 2022-09-19 | 2022-09-19
200883C-500-NM-0005-4000 | [D] | 200883C | 500 | NM | 5 | 4000 |  | 24 |  | Yuri Phase 0 - Overall Effluent List | Code: E0311 | PRO | 500H2 |  |  |  |  | IFU | 100 |  |  | MPRO | 2022-10-17 | 2022-10-17 | 2022-10-17
200883C-500-NM-0006-4000 | [D] | 200883C | 500 | NM | 6 | 4000 |  | 24 |  | Yuri Phase 0 - Overall Relief Load Summary | Code: E0311 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-NM-0006-4000 | [D] | 200883C | 500 | NM | 6 | 4000 |  | 24 |  | Yuri Phase 0 - Overall Relief Load Summary | Code: E0311 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-09-19 | 2022-09-19 | 2022-09-19
200883C-500-NM-0006-4000 | [D] | 200883C | 500 | NM | 6 | 4000 |  | 24 |  | Yuri Phase 0 - Overall Relief Load Summary | Code: E0311 | PRO | 500H2 |  |  |  |  | IFU | 100 |  |  | MPRO | 2022-10-17 | 2022-10-17 | 2022-10-17
200883C-500-NM-0013-4000 | [D] | 200883C | 500 | NM | 13 | 4000 |  | 71 |  | Yuri Phase 0 - Cause And Effect Chart | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-500-NM-0013-4000 | [D] | 200883C | 500 | NM | 13 | 4000 |  | 71 |  | Yuri Phase 0 - Cause And Effect Chart | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-06-20 | 2022-06-20 | 2022-06-22 | 2022-06-22
200883C-500-NM-0013-4000 | [D] | 200883C | 500 | NM | 13 | 4000 |  | 71 |  | Yuri Phase 0 - Cause And Effect Chart | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-25 | 2022-07-25 | 2022-07-27 | 2022-07-27
200883C-500-NM-0013-4000 | [D] | 200883C | 500 | NM | 13 | 4000 |  | 71 |  | Yuri Phase 0 - Cause And Effect Chart | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-10-06 | 2022-10-06 | 2022-10-06
200883C-500-NM-0013-4000 | [D] | 200883C | 500 | NM | 13 | 4000 |  | 71 |  | Yuri Phase 0 - Cause And Effect Chart | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-30 | 2023-01-30 | 2023-01-30
200883C-500-NM-0022-4000 | [D] | 200883C | 500 | NM | 22 | 4000 |  | 94 |  | Yuri Phase 0 - Process and Utility Line List | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-500-NM-0022-4000 | [D] | 200883C | 500 | NM | 22 | 4000 |  | 94 |  | Yuri Phase 0 - Process and Utility Line List | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-06-10 | 2022-06-10 | 2022-06-22 | 2022-06-22
200883C-500-NM-0022-4000 | [D] | 200883C | 500 | NM | 22 | 4000 |  | 94 |  | Yuri Phase 0 - Process and Utility Line List | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-15 | 2022-07-15 | 2022-07-25 | 2022-07-25
200883C-500-NM-0022-4000 | [D] | 200883C | 500 | NM | 22 | 4000 |  | 94 |  | Yuri Phase 0 - Process and Utility Line List | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-20 | 2022-09-20 | 2022-09-20
200883C-500-NM-0022-4000 | [D] | 200883C | 500 | NM | 22 | 4000 |  | 94 |  | Yuri Phase 0 - Process and Utility Line List | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-11 | 2023-01-11 | 2023-01-11
200883C-500-NM-1350-4000 | [D] | 200883C | 500 | NM | 1350 | 4000 |  | 135 |  | Yuri Phase 0-MIFU/ Isometric Index | Code: E0201 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-500-NM-1350-4000 | [D] | 200883C | 500 | NM | 1350 | 4000 |  | 135 |  | Yuri Phase 0-MIFU/ Isometric Index | Code: E0201 | PIP | 500H2 |  |  |  |  | IFI | 100 |  |  | MPIP | 2022-12-15 | 2022-12-15 | 2022-12-15
200883C-500-NM-1350-4001 | [D] | 200883C | 500 | NM | 1350 | 4001 |  | 585 |  | Yuri Phase 0-Isometric drawings- Large Bore | Code: E0203 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2023-01-19 | 2023-01-19 | 2023-01-19
200883C-500-NM-1350-4001 | [D] | 200883C | 500 | NM | 1350 | 4001 |  | 585 |  | Yuri Phase 0-Isometric drawings- Large Bore | Code: E0203 | PIP | 500H2 |  |  |  |  | IFC | 100 |  |  | MPIP | 2023-03-31 | 2023-03-31 | 2023-03-31
200883C-500-NM-1350-4002 | [D] | 200883C | 500 | NM | 1350 | 4002 |  | 394 |  | Yuri Phase 0-Isometric drawings- Small Bore | Code: E0203 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2023-01-19 | 2023-01-19 | 2023-01-19
200883C-500-NM-1350-4002 | [D] | 200883C | 500 | NM | 1350 | 4002 |  | 394 |  | Yuri Phase 0-Isometric drawings- Small Bore | Code: E0203 | PIP | 500H2 |  |  |  |  | IFC | 100 |  |  | MPIP | 2023-03-31 | 2023-03-31 | 2023-03-31
200883C-500-NM-1370-4000 | [D] | 200883C | 500 | NM | 1370 | 4000 |  | 90 |  | Yuri Phase 0-Stress Critical Line List | Code: E0301 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-06-13 | 2022-06-13 | 2022-06-13 | 2022-06-13
200883C-500-NM-1370-4000 | [D] | 200883C | 500 | NM | 1370 | 4000 |  | 90 |  | Yuri Phase 0-Stress Critical Line List | Code: E0301 | PIP | 500H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2022-06-24 | 2022-06-24 | 2022-07-01 | 2022-07-01
200883C-500-NM-1370-4000 | [D] | 200883C | 500 | NM | 1370 | 4000 |  | 90 |  | Yuri Phase 0-Stress Critical Line List | Code: E0301 | PIP | 500H2 |  |  |  |  | IFD | 100 |  |  | MPIP | 2022-09-19 | 2022-09-19 | 2022-09-19
200883C-500-NM-1380-4000 | [D] | 200883C | 500 | NM | 1380 | 4000 |  | 12 |  | Yuri Phase 0-Special Piping Material list | Code: E0201 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-500-NM-1380-4000 | [D] | 200883C | 500 | NM | 1380 | 4000 |  | 12 |  | Yuri Phase 0-Special Piping Material list | Code: E0201 | PIP | 500H2 |  |  |  |  | IFI | 100 |  |  | MPIP | 2022-07-15 | 2022-07-15 | 2022-07-29 | 2022-07-29
200883C-500-NM-4000 | [D] | 200883C | 500 | NM | 4000 |  |  | 113 |  | Template for Noise Level | Code: E0201 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-500-NM-4000 | [D] | 200883C | 500 | NM | 4000 |  |  | 113 |  | Template for Noise Level | Code: E0201 | MEC | 500H2 |  |  |  |  | IFI | 100 |  |  | MMEC | 2022-07-15 | 2022-07-15 | 2022-07-22 | 2022-07-22
200883C-500-NM-4001 | [D] | 200883C | 500 | NM | 4001 |  |  | 113 |  | Template for Spare Parts | Code: E0201 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30
200883C-500-NM-4001 | [D] | 200883C | 500 | NM | 4001 |  |  | 113 |  | Template for Spare Parts | Code: E0201 | MEC | 500H2 |  |  |  |  | IFI | 100 |  |  | MMEC | 2022-07-15 | 2022-07-15 | 2022-07-22 | 2022-07-22
200883C-500-PDS-0610-4000 | [D] | 200883C | 500 | PDS | 610 | 4000 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Cooling water exchnager | Code: E0301 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-500-PDS-0610-4000 | [D] | 200883C | 500 | PDS | 610 | 4000 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Cooling water exchnager | Code: E0301 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-06-10 | 2022-06-10 | 2022-06-01 | 2022-06-01
200883C-500-PDS-0610-4000 | [D] | 200883C | 500 | PDS | 610 | 4000 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Cooling water exchnager | Code: E0301 | PRO | 500H2 |  |  |  |  | IFD | 100 |  |  | MPRO | 2022-07-01 | 2022-07-01 | 2022-06-13 | 2022-06-13
200883C-500-PDS-0811-4000 | [D] | 200883C | 500 | PDS | 811 | 4000 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Instrument Air Receiver | Code: E0301 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-500-PDS-0811-4000 | [D] | 200883C | 500 | PDS | 811 | 4000 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Instrument Air Receiver | Code: E0301 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-06-07 | 2022-06-07 | 2022-07-25 | 2022-07-25
200883C-500-PDS-0811-4000 | [D] | 200883C | 500 | PDS | 811 | 4000 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Instrument Air Receiver | Code: E0301 | PRO | 500H2 |  |  |  |  | IFD | 100 |  |  | MPRO | 2022-07-05 | 2022-07-05 | 2022-07-25 | 2022-07-25
200883C-500-PDS-0811-4001 | [D] | 200883C | 500 | PDS | 811 | 4001 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Cooling water expansion vessel | Code: E0301 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-500-PDS-0811-4001 | [D] | 200883C | 500 | PDS | 811 | 4001 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Cooling water expansion vessel | Code: E0301 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-06-07 | 2022-06-07 | 2022-07-25 | 2022-07-25
200883C-500-PDS-0811-4001 | [D] | 200883C | 500 | PDS | 811 | 4001 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Cooling water expansion vessel | Code: E0301 | PRO | 500H2 |  |  |  |  | IFD | 100 |  |  | MPRO | 2022-07-05 | 2022-07-05 | 2022-08-02 | 2022-08-02
200883C-500-PDS-0811-4002 | [D] | 200883C | 500 | PDS | 811 | 4002 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Chilled water expansion vessel | Code: E0301 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-500-PDS-0811-4002 | [D] | 200883C | 500 | PDS | 811 | 4002 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Chilled water expansion vessel | Code: E0301 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-06-07 | 2022-06-07 | 2022-07-25 | 2022-07-25
200883C-500-PDS-0811-4002 | [D] | 200883C | 500 | PDS | 811 | 4002 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Chilled water expansion vessel | Code: E0301 | PRO | 500H2 |  |  |  |  | IFD | 100 |  |  | MPRO | 2022-07-05 | 2022-07-05 | 2022-08-02 | 2022-08-02
200883C-500-PDS-0910-4000 | [D] | 200883C | 500 | PDS | 910 | 4000 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Cooling water Circulation Pump | Code: E0301 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-500-PDS-0910-4000 | [D] | 200883C | 500 | PDS | 910 | 4000 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Cooling water Circulation Pump | Code: E0301 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-06-07 | 2022-06-07 | 2022-07-25 | 2022-07-25
200883C-500-PDS-0910-4000 | [D] | 200883C | 500 | PDS | 910 | 4000 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Cooling water Circulation Pump | Code: E0301 | PRO | 500H2 |  |  |  |  | IFD | 100 |  |  | MPRO | 2022-07-05 | 2022-07-05 | 2022-08-02 | 2022-08-02
200883C-500-PDS-0910-4001 | [D] | 200883C | 500 | PDS | 910 | 4001 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Chilled water Circulation pump | Code: E0301 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-500-PDS-0910-4001 | [D] | 200883C | 500 | PDS | 910 | 4001 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Chilled water Circulation pump | Code: E0301 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-06-07 | 2022-06-07 | 2022-07-25 | 2022-07-25
200883C-500-PDS-0910-4001 | [D] | 200883C | 500 | PDS | 910 | 4001 |  | 24 |  | Yuri Phase 0 - Equipment Process datasheet - Chilled water Circulation pump | Code: E0301 | PRO | 500H2 |  |  |  |  | IFD | 100 |  |  | MPRO | 2022-07-05 | 2022-07-05 | 2022-08-02 | 2022-08-02
200883C-500-PDS-1541-4000 | [D] | 200883C | 500 | PDS | 1541 | 4000 |  | 24 |  | Yuri Phase 0 - Control valve Process datasheet | Code: E0301 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-500-PDS-1541-4000 | [D] | 200883C | 500 | PDS | 1541 | 4000 |  | 24 |  | Yuri Phase 0 - Control valve Process datasheet | Code: E0301 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-06-03 | 2022-06-03 | 2022-07-27 | 2022-07-27
200883C-500-PDS-1541-4000 | [D] | 200883C | 500 | PDS | 1541 | 4000 |  | 24 |  | Yuri Phase 0 - Control valve Process datasheet | Code: E0301 | PRO | 500H2 |  |  |  |  | IFD | 100 |  |  | MPRO | 2022-07-22 | 2022-07-22 | 2022-08-23 | 2022-08-23
200883C-500-PDS-1545-4000 | [D] | 200883C | 500 | PDS | 1545 | 4000 |  | 24 |  | Yuri Phase 0 - Safety relief valve Process datasheet | Code: E0301 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-500-PDS-1545-4000 | [D] | 200883C | 500 | PDS | 1545 | 4000 |  | 24 |  | Yuri Phase 0 - Safety relief valve Process datasheet | Code: E0301 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-06-03 | 2022-06-03 | 2022-06-03
200883C-500-PDS-1545-4000 | [D] | 200883C | 500 | PDS | 1545 | 4000 |  | 24 |  | Yuri Phase 0 - Safety relief valve Process datasheet | Code: E0301 | PRO | 500H2 |  |  |  |  | IFD | 100 |  |  | MPRO | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-500-PDS-1546-4000 | [D] | 200883C | 500 | PDS | 1546 | 4000 |  | 24 |  | Yuri Phase 0 - Flow Instrument Process datasheet | Code: E0301 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-500-PDS-1546-4000 | [D] | 200883C | 500 | PDS | 1546 | 4000 |  | 24 |  | Yuri Phase 0 - Flow Instrument Process datasheet | Code: E0301 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-06-03 | 2022-06-03 | 2022-07-26 | 2022-07-26
200883C-500-PDS-1546-4000 | [D] | 200883C | 500 | PDS | 1546 | 4000 |  | 24 |  | Yuri Phase 0 - Flow Instrument Process datasheet | Code: E0301 | PRO | 500H2 |  |  |  |  | IFD | 100 |  |  | MPRO | 2022-07-15 | 2022-07-15 | 2022-08-23 | 2022-08-23
200883C-500-PDS-1584-4000 | [D] | 200883C | 500 | PDS | 1584 | 4000 |  | 24 |  | Yuri Phase 0 - Process datasheet - Metering skid package | Code: E0301 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-16 | 2022-05-16 | 2022-05-16 | 2022-05-16
200883C-500-PDS-1584-4000 | [D] | 200883C | 500 | PDS | 1584 | 4000 |  | 24 |  | Yuri Phase 0 - Process datasheet - Metering skid package | Code: E0301 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-13 | 2022-06-13
200883C-500-PDS-1584-4000 | [D] | 200883C | 500 | PDS | 1584 | 4000 |  | 24 |  | Yuri Phase 0 - Process datasheet - Metering skid package | Code: E0301 | PRO | 500H2 |  |  |  |  | IFD | 100 |  |  | MPRO | 2022-06-17 | 2022-06-17 | 2022-07-23 | 2022-07-23
200883C-500-PDS-4151-4000 | [D] | 200883C | 500 | PDS | 4151 | 4000 |  | 24 |  | Yuri Phase 0 - Package Process datasheet - Refrigeration package | Code: E0301 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-10 | 2022-05-10 | 2022-05-10 | 2022-05-10
200883C-500-PDS-4151-4000 | [D] | 200883C | 500 | PDS | 4151 | 4000 |  | 24 |  | Yuri Phase 0 - Package Process datasheet - Refrigeration package | Code: E0301 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-05-23 | 2022-05-23 | 2022-05-23 | 2022-05-23
200883C-500-PDS-4151-4000 | [D] | 200883C | 500 | PDS | 4151 | 4000 |  | 24 |  | Yuri Phase 0 - Package Process datasheet - Refrigeration package | Code: E0301 | PRO | 500H2 |  |  |  |  | IFD | 100 |  |  | MPRO | 2022-06-13 | 2022-06-13 | 2022-06-13 | 2022-06-13
200883C-500-PFD-0010-4000 | [D] | 200883C | 500 | PFD | 10 | 4000 |  | 71 |  | Yuri Phase 0 - PFD & H&MB No.1 | Code: E0301 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-25 | 2022-04-25 | 2022-04-25 | 2022-04-25
200883C-500-PFD-0010-4000 | [D] | 200883C | 500 | PFD | 10 | 4000 |  | 71 |  | Yuri Phase 0 - PFD & H&MB No.1 | Code: E0301 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-05-16 | 2022-05-16 | 2022-06-30 | 2022-06-30
200883C-500-PFD-0010-4000 | [D] | 200883C | 500 | PFD | 10 | 4000 |  | 71 |  | Yuri Phase 0 - PFD & H&MB No.1 | Code: E0301 | PRO | 500H2 |  |  |  |  | IFD | 100 |  |  | MPRO | 2022-06-13 | 2022-06-13 | 2022-07-20 | 2022-07-20
200883C-500-PFD-0010-4001 | [D] | 200883C | 500 | PFD | 10 | 4001 |  | 71 |  | Yuri Phase 0 - PFD & H&MB No.2 | Code: E0301 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-25 | 2022-04-25 | 2022-04-25 | 2022-04-25
200883C-500-PFD-0010-4001 | [D] | 200883C | 500 | PFD | 10 | 4001 |  | 71 |  | Yuri Phase 0 - PFD & H&MB No.2 | Code: E0301 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-05-16 | 2022-05-16 | 2022-06-30 | 2022-06-30
200883C-500-PFD-0010-4001 | [D] | 200883C | 500 | PFD | 10 | 4001 |  | 71 |  | Yuri Phase 0 - PFD & H&MB No.2 | Code: E0301 | PRO | 500H2 |  |  |  |  | IFD | 100 |  |  | MPRO | 2022-06-13 | 2022-06-13 | 2022-07-20 | 2022-07-20
200883C-500-PID-0021-4000 | [D] | 200883C | 500 | PID | 21 | 4000 |  | 71 |  | Yuri Phase 0 - PID OSBL Battery Limit (Process and Utility) | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4000 | [D] | 200883C | 500 | PID | 21 | 4000 |  | 71 |  | Yuri Phase 0 - PID OSBL Battery Limit (Process and Utility) | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-02 | 2022-06-02
200883C-500-PID-0021-4000 | [D] | 200883C | 500 | PID | 21 | 4000 |  | 71 |  | Yuri Phase 0 - PID OSBL Battery Limit (Process and Utility) | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4000 | [D] | 200883C | 500 | PID | 21 | 4000 |  | 71 |  | Yuri Phase 0 - PID OSBL Battery Limit (Process and Utility) | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4000 | [D] | 200883C | 500 | PID | 21 | 4000 |  | 71 |  | Yuri Phase 0 - PID OSBL Battery Limit (Process and Utility) | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0021-4001 | [D] | 200883C | 500 | PID | 21 | 4001 |  | 71 |  | Yuri Phase 0 - PID Electrolyser Stacks | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4001 | [D] | 200883C | 500 | PID | 21 | 4001 |  | 71 |  | Yuri Phase 0 - PID Electrolyser Stacks | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-01 | 2022-06-01
200883C-500-PID-0021-4001 | [D] | 200883C | 500 | PID | 21 | 4001 |  | 71 |  | Yuri Phase 0 - PID Electrolyser Stacks | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4001 | [D] | 200883C | 500 | PID | 21 | 4001 |  | 71 |  | Yuri Phase 0 - PID Electrolyser Stacks | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4001 | [D] | 200883C | 500 | PID | 21 | 4001 |  | 71 |  | Yuri Phase 0 - PID Electrolyser Stacks | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0021-4002 | [D] | 200883C | 500 | PID | 21 | 4002 |  | 71 |  | Yuri Phase 0 - PID Gas Liquid Treater Skid A | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4002 | [D] | 200883C | 500 | PID | 21 | 4002 |  | 71 |  | Yuri Phase 0 - PID Gas Liquid Treater Skid A | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-01 | 2022-06-01
200883C-500-PID-0021-4002 | [D] | 200883C | 500 | PID | 21 | 4002 |  | 71 |  | Yuri Phase 0 - PID Gas Liquid Treater Skid A | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4002 | [D] | 200883C | 500 | PID | 21 | 4002 |  | 71 |  | Yuri Phase 0 - PID Gas Liquid Treater Skid A | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4002 | [D] | 200883C | 500 | PID | 21 | 4002 |  | 71 |  | Yuri Phase 0 - PID Gas Liquid Treater Skid A | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0021-4003 | [D] | 200883C | 500 | PID | 21 | 4003 |  | 71 |  | Yuri Phase 0 - PID Gas Liquid Treater Skid B | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4003 | [D] | 200883C | 500 | PID | 21 | 4003 |  | 71 |  | Yuri Phase 0 - PID Gas Liquid Treater Skid B | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-01 | 2022-06-01
200883C-500-PID-0021-4003 | [D] | 200883C | 500 | PID | 21 | 4003 |  | 71 |  | Yuri Phase 0 - PID Gas Liquid Treater Skid B | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4003 | [D] | 200883C | 500 | PID | 21 | 4003 |  | 71 |  | Yuri Phase 0 - PID Gas Liquid Treater Skid B | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4003 | [D] | 200883C | 500 | PID | 21 | 4003 |  | 71 |  | Yuri Phase 0 - PID Gas Liquid Treater Skid B | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0021-4004 | [D] | 200883C | 500 | PID | 21 | 4004 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Purification Package | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4004 | [D] | 200883C | 500 | PID | 21 | 4004 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Purification Package | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-02 | 2022-06-02
200883C-500-PID-0021-4004 | [D] | 200883C | 500 | PID | 21 | 4004 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Purification Package | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4004 | [D] | 200883C | 500 | PID | 21 | 4004 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Purification Package | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4004 | [D] | 200883C | 500 | PID | 21 | 4004 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Purification Package | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0021-4005 | [D] | 200883C | 500 | PID | 21 | 4005 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Buffer tank & Compressor | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4005 | [D] | 200883C | 500 | PID | 21 | 4005 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Buffer tank & Compressor | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-02 | 2022-06-02
200883C-500-PID-0021-4005 | [D] | 200883C | 500 | PID | 21 | 4005 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Buffer tank & Compressor | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4005 | [D] | 200883C | 500 | PID | 21 | 4005 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Buffer tank & Compressor | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4005 | [D] | 200883C | 500 | PID | 21 | 4005 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Buffer tank & Compressor | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0021-4006 | [D] | 200883C | 500 | PID | 21 | 4006 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Product Metering Package | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4006 | [D] | 200883C | 500 | PID | 21 | 4006 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Product Metering Package | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-02 | 2022-06-02
200883C-500-PID-0021-4006 | [D] | 200883C | 500 | PID | 21 | 4006 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Product Metering Package | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4006 | [D] | 200883C | 500 | PID | 21 | 4006 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Product Metering Package | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4006 | [D] | 200883C | 500 | PID | 21 | 4006 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Product Metering Package | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0021-4007 | [D] | 200883C | 500 | PID | 21 | 4007 |  | 71 |  | Yuri Phase 0 - PID Chilled Water System | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4007 | [D] | 200883C | 500 | PID | 21 | 4007 |  | 71 |  | Yuri Phase 0 - PID Chilled Water System | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-02 | 2022-06-02
200883C-500-PID-0021-4007 | [D] | 200883C | 500 | PID | 21 | 4007 |  | 71 |  | Yuri Phase 0 - PID Chilled Water System | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4007 | [D] | 200883C | 500 | PID | 21 | 4007 |  | 71 |  | Yuri Phase 0 - PID Chilled Water System | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4007 | [D] | 200883C | 500 | PID | 21 | 4007 |  | 71 |  | Yuri Phase 0 - PID Chilled Water System | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0021-4008 | [D] | 200883C | 500 | PID | 21 | 4008 |  | 71 |  | Yuri Phase 0 - PID Chilled Water Refrigeration Package | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4008 | [D] | 200883C | 500 | PID | 21 | 4008 |  | 71 |  | Yuri Phase 0 - PID Chilled Water Refrigeration Package | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-02 | 2022-06-02
200883C-500-PID-0021-4008 | [D] | 200883C | 500 | PID | 21 | 4008 |  | 71 |  | Yuri Phase 0 - PID Chilled Water Refrigeration Package | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4008 | [D] | 200883C | 500 | PID | 21 | 4008 |  | 71 |  | Yuri Phase 0 - PID Chilled Water Refrigeration Package | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4008 | [D] | 200883C | 500 | PID | 21 | 4008 |  | 71 |  | Yuri Phase 0 - PID Chilled Water Refrigeration Package | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0021-4009 | [D] | 200883C | 500 | PID | 21 | 4009 |  | 47 |  | Yuri Phase 0 - PID Cooing water system | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4009 | [D] | 200883C | 500 | PID | 21 | 4009 |  | 47 |  | Yuri Phase 0 - PID Cooing water system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-02 | 2022-06-02
200883C-500-PID-0021-4009 | [D] | 200883C | 500 | PID | 21 | 4009 |  | 47 |  | Yuri Phase 0 - PID Cooing water system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4009 | [D] | 200883C | 500 | PID | 21 | 4009 |  | 47 |  | Yuri Phase 0 - PID Cooing water system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4009 | [D] | 200883C | 500 | PID | 21 | 4009 |  | 47 |  | Yuri Phase 0 - PID Cooing water system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0021-4010 | [D] | 200883C | 500 | PID | 21 | 4010 |  | 71 |  | Yuri Phase 0 - PID Rectifier cooling water system | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4010 | [D] | 200883C | 500 | PID | 21 | 4010 |  | 71 |  | Yuri Phase 0 - PID Rectifier cooling water system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-02 | 2022-06-02
200883C-500-PID-0021-4010 | [D] | 200883C | 500 | PID | 21 | 4010 |  | 71 |  | Yuri Phase 0 - PID Rectifier cooling water system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4010 | [D] | 200883C | 500 | PID | 21 | 4010 |  | 71 |  | Yuri Phase 0 - PID Rectifier cooling water system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4010 | [D] | 200883C | 500 | PID | 21 | 4010 |  | 71 |  | Yuri Phase 0 - PID Rectifier cooling water system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0021-4011 | [D] | 200883C | 500 | PID | 21 | 4011 |  | 71 |  | Yuri Phase 0 - PID DM Water and Lye System | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4011 | [D] | 200883C | 500 | PID | 21 | 4011 |  | 71 |  | Yuri Phase 0 - PID DM Water and Lye System | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-02 | 2022-06-02
200883C-500-PID-0021-4011 | [D] | 200883C | 500 | PID | 21 | 4011 |  | 71 |  | Yuri Phase 0 - PID DM Water and Lye System | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4011 | [D] | 200883C | 500 | PID | 21 | 4011 |  | 71 |  | Yuri Phase 0 - PID DM Water and Lye System | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4011 | [D] | 200883C | 500 | PID | 21 | 4011 |  | 71 |  | Yuri Phase 0 - PID DM Water and Lye System | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0021-4012 | [D] | 200883C | 500 | PID | 21 | 4012 |  | 71 |  | Yuri Phase 0 - PID Instrument Air Receiver | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4012 | [D] | 200883C | 500 | PID | 21 | 4012 |  | 71 |  | Yuri Phase 0 - PID Instrument Air Receiver | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-02 | 2022-06-02
200883C-500-PID-0021-4012 | [D] | 200883C | 500 | PID | 21 | 4012 |  | 71 |  | Yuri Phase 0 - PID Instrument Air Receiver | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4012 | [D] | 200883C | 500 | PID | 21 | 4012 |  | 71 |  | Yuri Phase 0 - PID Instrument Air Receiver | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4012 | [D] | 200883C | 500 | PID | 21 | 4012 |  | 71 |  | Yuri Phase 0 - PID Instrument Air Receiver | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0021-4013 | [D] | 200883C | 500 | PID | 21 | 4013 |  | 71 |  | Yuri Phase 0 - PID Nitrogen distribution system | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4013 | [D] | 200883C | 500 | PID | 21 | 4013 |  | 71 |  | Yuri Phase 0 - PID Nitrogen distribution system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-02 | 2022-06-02
200883C-500-PID-0021-4013 | [D] | 200883C | 500 | PID | 21 | 4013 |  | 71 |  | Yuri Phase 0 - PID Nitrogen distribution system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4013 | [D] | 200883C | 500 | PID | 21 | 4013 |  | 71 |  | Yuri Phase 0 - PID Nitrogen distribution system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4013 | [D] | 200883C | 500 | PID | 21 | 4013 |  | 71 |  | Yuri Phase 0 - PID Nitrogen distribution system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0021-4014 | [D] | 200883C | 500 | PID | 21 | 4014 |  | 71 |  | Yuri Phase 0 - PID Potable Water distribution system | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4014 | [D] | 200883C | 500 | PID | 21 | 4014 |  | 71 |  | Yuri Phase 0 - PID Potable Water distribution system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-02 | 2022-06-02
200883C-500-PID-0021-4014 | [D] | 200883C | 500 | PID | 21 | 4014 |  | 71 |  | Yuri Phase 0 - PID Potable Water distribution system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4014 | [D] | 200883C | 500 | PID | 21 | 4014 |  | 71 |  | Yuri Phase 0 - PID Potable Water distribution system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4014 | [D] | 200883C | 500 | PID | 21 | 4014 |  | 71 |  | Yuri Phase 0 - PID Potable Water distribution system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0021-4019 | [D] | 200883C | 500 | PID | 21 | 4019 |  | 24 |  | Yuri Phase 0 - PID Air Cooler System | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0021-4019 | [D] | 200883C | 500 | PID | 21 | 4019 |  | 24 |  | Yuri Phase 0 - PID Air Cooler System | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-02 | 2022-06-02
200883C-500-PID-0021-4019 | [D] | 200883C | 500 | PID | 21 | 4019 |  | 24 |  | Yuri Phase 0 - PID Air Cooler System | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0021-4019 | [D] | 200883C | 500 | PID | 21 | 4019 |  | 24 |  | Yuri Phase 0 - PID Air Cooler System | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4019 | [D] | 200883C | 500 | PID | 21 | 4019 |  | 24 |  | Yuri Phase 0 - PID Air Cooler System | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0090-4000 | [D] | 200883C | 500 | PID | 90 | 4000 |  | 47 |  | Yuri Phase 0 - PID Drawing Index | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0090-4000 | [D] | 200883C | 500 | PID | 90 | 4000 |  | 47 |  | Yuri Phase 0 - PID Drawing Index | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-21 | 2022-06-21
200883C-500-PID-0090-4000 | [D] | 200883C | 500 | PID | 90 | 4000 |  | 47 |  | Yuri Phase 0 - PID Drawing Index | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0090-4000 | [D] | 200883C | 500 | PID | 90 | 4000 |  | 47 |  | Yuri Phase 0 - PID Drawing Index | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0090-4000 | [D] | 200883C | 500 | PID | 90 | 4000 |  | 47 |  | Yuri Phase 0 - PID Drawing Index | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0090-4001 | [D] | 200883C | 500 | PID | 90 | 4001 |  | 71 |  | Yuri Phase 0 - PID Piping Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0090-4001 | [D] | 200883C | 500 | PID | 90 | 4001 |  | 71 |  | Yuri Phase 0 - PID Piping Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-21 | 2022-06-21
200883C-500-PID-0090-4001 | [D] | 200883C | 500 | PID | 90 | 4001 |  | 71 |  | Yuri Phase 0 - PID Piping Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0090-4001 | [D] | 200883C | 500 | PID | 90 | 4001 |  | 71 |  | Yuri Phase 0 - PID Piping Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0090-4001 | [D] | 200883C | 500 | PID | 90 | 4001 |  | 71 |  | Yuri Phase 0 - PID Piping Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0090-4002 | [D] | 200883C | 500 | PID | 90 | 4002 |  | 71 |  | Yuri Phase 0 - PID Piping Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0090-4002 | [D] | 200883C | 500 | PID | 90 | 4002 |  | 71 |  | Yuri Phase 0 - PID Piping Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-21 | 2022-06-21
200883C-500-PID-0090-4002 | [D] | 200883C | 500 | PID | 90 | 4002 |  | 71 |  | Yuri Phase 0 - PID Piping Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0090-4002 | [D] | 200883C | 500 | PID | 90 | 4002 |  | 71 |  | Yuri Phase 0 - PID Piping Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0090-4002 | [D] | 200883C | 500 | PID | 90 | 4002 |  | 71 |  | Yuri Phase 0 - PID Piping Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-PID-0090-4003 | [D] | 200883C | 500 | PID | 90 | 4003 |  | 71 |  | Yuri Phase 0 - PID Instrument Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-500-PID-0090-4003 | [D] | 200883C | 500 | PID | 90 | 4003 |  | 71 |  | Yuri Phase 0 - PID Instrument Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-21 | 2022-06-21
200883C-500-PID-0090-4003 | [D] | 200883C | 500 | PID | 90 | 4003 |  | 71 |  | Yuri Phase 0 - PID Instrument Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-07-16 | 2022-07-16
200883C-500-PID-0090-4003 | [D] | 200883C | 500 | PID | 90 | 4003 |  | 71 |  | Yuri Phase 0 - PID Instrument Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0090-4003 | [D] | 200883C | 500 | PID | 90 | 4003 |  | 71 |  | Yuri Phase 0 - PID Instrument Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-500-RT-0800-4000 | [D] | 200883C | 500 | RT | 800 | 4000 |  | 113 |  | Presure Vessel Registration | Code: E0201 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-06-15 | 2022-06-15 | 2022-06-15 | 2022-06-15
200883C-500-RT-0800-4000 | [D] | 200883C | 500 | RT | 800 | 4000 |  | 113 |  | Presure Vessel Registration | Code: E0201 | MEC | 500H2 |  |  |  |  | IFI | 100 |  |  | MMEC | 2022-06-25 | 2022-06-25 | 2022-06-25
200883C-500-RT-1300-4000 | [D] | 200883C | 500 | RT | 1300 | 4000 |  | 23 |  | Yuri Phase 0-30% 3D Model Review Reports. | Code: E0311 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-08-22 | 2022-08-22 | 2022-07-29 | 2022-07-29
200883C-500-RT-1300-4000 | [D] | 200883C | 500 | RT | 1300 | 4000 |  | 23 |  | Yuri Phase 0-30% 3D Model Review Reports. | Code: E0311 | PIP | 500H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2022-09-19 | 2022-09-19 | 2022-08-04 | 2022-08-04
200883C-500-RT-1300-4000 | [D] | 200883C | 500 | RT | 1300 | 4000 |  | 23 |  | Yuri Phase 0-30% 3D Model Review Reports. | Code: E0311 | PIP | 500H2 |  |  |  |  | IFU | 100 |  |  | MPIP | 2022-10-17 | 2022-10-17 | 2022-10-17
200883C-500-RT-1300-4001 | [D] | 200883C | 500 | RT | 1300 | 4001 |  | 23 |  | Yuri Phase 0-60% 3D Model Review Reports. | Code: E0311 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-11-30 | 2022-11-30 | 2022-11-30
200883C-500-RT-1300-4001 | [D] | 200883C | 500 | RT | 1300 | 4001 |  | 23 |  | Yuri Phase 0-60% 3D Model Review Reports. | Code: E0311 | PIP | 500H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2022-12-28 | 2022-12-28 | 2022-12-28
200883C-500-RT-1300-4001 | [D] | 200883C | 500 | RT | 1300 | 4001 |  | 23 |  | Yuri Phase 0-60% 3D Model Review Reports. | Code: E0311 | PIP | 500H2 |  |  |  |  | IFU | 100 |  |  | MPIP | 2023-01-25 | 2023-01-25 | 2023-01-25
200883C-500-RT-1300-4002 | [D] | 200883C | 500 | RT | 1300 | 4002 |  | 23 |  | Yuri Phase 0-90% 3D Model Review Reports. | Code: E0311 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2023-02-09 | 2023-02-09 | 2023-02-09
200883C-500-RT-1300-4002 | [D] | 200883C | 500 | RT | 1300 | 4002 |  | 23 |  | Yuri Phase 0-90% 3D Model Review Reports. | Code: E0311 | PIP | 500H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2023-03-09 | 2023-03-09 | 2023-03-09
200883C-500-RT-1300-4002 | [D] | 200883C | 500 | RT | 1300 | 4002 |  | 23 |  | Yuri Phase 0-90% 3D Model Review Reports. | Code: E0311 | PIP | 500H2 |  |  |  |  | IFU | 100 |  |  | MPIP | 2023-04-06 | 2023-04-06 | 2023-04-06
200883C-500-RT-1300-4007 | [D] | 200883C | 500 | RT | 1300 | 4007 |  | 12 |  | Yuri Phase 0-ASME bolt tension & Torque valves | Code: E0301 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2023-01-12 | 2023-01-12 | 2023-01-12
200883C-500-RT-1300-4007 | [D] | 200883C | 500 | RT | 1300 | 4007 |  | 12 |  | Yuri Phase 0-ASME bolt tension & Torque valves | Code: E0301 | PIP | 500H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2023-01-27 | 2023-01-27 | 2023-01-27
200883C-500-RT-1300-4007 | [D] | 200883C | 500 | RT | 1300 | 4007 |  | 12 |  | Yuri Phase 0-ASME bolt tension & Torque valves | Code: E0301 | PIP | 500H2 |  |  |  |  | IFD | 100 |  |  | MPIP | 2023-02-24 | 2023-02-24 | 2023-02-24
200883C-500-RT-1800-4000 | [D] | 200883C | 500 | RT | 1800 | 4000 |  | 62 |  | Structural Steel Design Report for Skid-1 | Code: E0301 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-08-30 | 2022-08-30 | 2022-08-30
200883C-500-RT-1800-4000 | [D] | 200883C | 500 | RT | 1800 | 4000 |  | 62 |  | Structural Steel Design Report for Skid-1 | Code: E0301 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-09-06 | 2022-09-06 | 2022-09-06
200883C-500-RT-1800-4000 | [D] | 200883C | 500 | RT | 1800 | 4000 |  | 62 |  | Structural Steel Design Report for Skid-1 | Code: E0301 | STR | 500H2 |  |  |  |  | IFD | 100 |  |  | MSTR | 2022-12-07 | 2022-12-07 | 2022-12-07
200883C-500-RT-1800-4002 | [D] | 200883C | 500 | RT | 1800 | 4002 |  | 62 |  | Structural Steel Design Report for Pipe Supports, Battery Limit Platform | Code: E0301 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-09-08 | 2022-09-08 | 2022-09-08
200883C-500-RT-1800-4002 | [D] | 200883C | 500 | RT | 1800 | 4002 |  | 62 |  | Structural Steel Design Report for Pipe Supports, Battery Limit Platform | Code: E0301 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-09-14 | 2022-09-14 | 2022-09-14
200883C-500-RT-1800-4002 | [D] | 200883C | 500 | RT | 1800 | 4002 |  | 62 |  | Structural Steel Design Report for Pipe Supports, Battery Limit Platform | Code: E0301 | STR | 500H2 |  |  |  |  | IFD | 100 |  |  | MSTR | 2022-12-15 | 2022-12-15 | 2022-12-15
200883C-500-RT-1800-4003 | [D] | 200883C | 500 | RT | 1800 | 4003 |  | 92 |  | Structural Steel Design Report- Support Structure for Prefabricated Substation | Code: E0301 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-12-01 | 2022-12-01 | 2022-12-01
200883C-500-RT-1800-4003 | [D] | 200883C | 500 | RT | 1800 | 4003 |  | 92 |  | Structural Steel Design Report- Support Structure for Prefabricated Substation | Code: E0301 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-12-09 | 2022-12-09 | 2022-12-09
200883C-500-RT-1800-4003 | [D] | 200883C | 500 | RT | 1800 | 4003 |  | 92 |  | Structural Steel Design Report- Support Structure for Prefabricated Substation | Code: E0301 | STR | 500H2 |  |  |  |  | IFD | 100 |  |  | MSTR | 2023-02-10 | 2023-02-10 | 2023-02-10
200883C-500-RT-1800-4004 | [D] | 200883C | 500 | RT | 1800 | 4004 |  | 0 |  | Structural Steel Design Report-Module PR1- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-23 | 2022-09-23
200883C-500-RT-1800-4004 | [D] | 200883C | 500 | RT | 1800 | 4004 |  | 0 |  | Structural Steel Design Report-Module PR1- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-30 | 2022-09-30
200883C-500-RT-1800-4004 | [D] | 200883C | 500 | RT | 1800 | 4004 |  | 0 |  | Structural Steel Design Report-Module PR1- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-RT-1800-4005 | [D] | 200883C | 500 | RT | 1800 | 4005 |  | 0 |  | Structural Steel Design Report-Module PR1- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-23 | 2022-09-23
200883C-500-RT-1800-4005 | [D] | 200883C | 500 | RT | 1800 | 4005 |  | 0 |  | Structural Steel Design Report-Module PR1- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-30 | 2022-09-30
200883C-500-RT-1800-4005 | [D] | 200883C | 500 | RT | 1800 | 4005 |  | 0 |  | Structural Steel Design Report-Module PR1- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-RT-1800-4006 | [D] | 200883C | 500 | RT | 1800 | 4006 |  | 0 |  | Structural Steel Design Report-Module PR2- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-RT-1800-4006 | [D] | 200883C | 500 | RT | 1800 | 4006 |  | 0 |  | Structural Steel Design Report-Module PR2- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-23 | 2022-09-23
200883C-500-RT-1800-4006 | [D] | 200883C | 500 | RT | 1800 | 4006 |  | 0 |  | Structural Steel Design Report-Module PR2- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-RT-1800-4007 | [D] | 200883C | 500 | RT | 1800 | 4007 |  | 0 |  | Structural Steel Design Report-Module PR2- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-RT-1800-4007 | [D] | 200883C | 500 | RT | 1800 | 4007 |  | 0 |  | Structural Steel Design Report-Module PR2- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-23 | 2022-09-23
200883C-500-RT-1800-4007 | [D] | 200883C | 500 | RT | 1800 | 4007 |  | 0 |  | Structural Steel Design Report-Module PR2- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-RT-1800-4008 | [D] | 200883C | 500 | RT | 1800 | 4008 |  | 0 |  | Structural Steel Design Report-Module PR3- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-09 | 2022-09-09
200883C-500-RT-1800-4008 | [D] | 200883C | 500 | RT | 1800 | 4008 |  | 0 |  | Structural Steel Design Report-Module PR3- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-RT-1800-4008 | [D] | 200883C | 500 | RT | 1800 | 4008 |  | 0 |  | Structural Steel Design Report-Module PR3- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-RT-1800-4009 | [D] | 200883C | 500 | RT | 1800 | 4009 |  | 0 |  | Structural Steel Design Report-Module PR3- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-09 | 2022-09-09
200883C-500-RT-1800-4009 | [D] | 200883C | 500 | RT | 1800 | 4009 |  | 0 |  | Structural Steel Design Report-Module PR3- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-RT-1800-4009 | [D] | 200883C | 500 | RT | 1800 | 4009 |  | 0 |  | Structural Steel Design Report-Module PR3- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-RT-1800-4010 | [D] | 200883C | 500 | RT | 1800 | 4010 |  | 0 |  | Structural Steel Design Report-Module PR4- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-08-23 | 2022-08-23
200883C-500-RT-1800-4010 | [D] | 200883C | 500 | RT | 1800 | 4010 |  | 0 |  | Structural Steel Design Report-Module PR4- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-08-30 | 2022-08-30
200883C-500-RT-1800-4010 | [D] | 200883C | 500 | RT | 1800 | 4010 |  | 0 |  | Structural Steel Design Report-Module PR4- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-RT-1800-4011 | [D] | 200883C | 500 | RT | 1800 | 4011 |  | 0 |  | Structural Steel Design Report-Module PR4- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-08-23 | 2022-08-23
200883C-500-RT-1800-4011 | [D] | 200883C | 500 | RT | 1800 | 4011 |  | 0 |  | Structural Steel Design Report-Module PR4- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-08-30 | 2022-08-30
200883C-500-RT-1800-4011 | [D] | 200883C | 500 | RT | 1800 | 4011 |  | 0 |  | Structural Steel Design Report-Module PR4- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | IFC | 100 |  |  | MSTR |  | 2022-12-15 | 2022-12-15
200883C-500-TBT-0400-1000 | [D] | 200883C | 500 | TBT | 400 | 1000 |  | 500 |  | Yuri Phase 0 - Technical Bid Evaluation Electrolyse | Code: E0303 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | AMEC | 2022-04-26 | 2022-04-26 | 2022-04-26 | 2022-04-26
200883C-500-TBT-0400-1000 | [D] | 200883C | 500 | TBT | 400 | 1000 |  | 500 |  | Yuri Phase 0 - Technical Bid Evaluation Electrolyse | Code: E0303 | MEC | 500H2 |  |  |  |  | IFR | 70 |  |  | AMEC | 2022-06-30 | 2022-06-30 | 2022-07-13 | 2022-07-13
200883C-500-TBT-0400-1000 | [D] | 200883C | 500 | TBT | 400 | 1000 |  | 500 |  | Yuri Phase 0 - Technical Bid Evaluation Electrolyse | Code: E0303 | MEC | 500H2 |  |  |  |  | IFC | 100 |  |  | AMEC | 2022-07-30 | 2022-07-30 | 2022-07-13 | 2022-07-13
200883C-500-TBT-0710-4000 | [D] | 200883C | 500 | TBT | 710 | 4000 |  | 203 |  | TBT for Air Cooled Heat Exchanger | Code: E0204 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-08-03 | 2022-08-03 | 2022-08-06 | 2022-08-06
200883C-500-TBT-0710-4000 | [D] | 200883C | 500 | TBT | 710 | 4000 |  | 203 |  | TBT for Air Cooled Heat Exchanger | Code: E0204 | MEC | 500H2 |  |  |  |  | IFP | 100 |  |  | MMEC | 2022-08-31 | 2022-08-31 | 2022-08-31
200883C-500-TBT-0811-4000 | [D] | 200883C | 500 | TBT | 811 | 4000 |  | 46 |  | TBT for Vessels (Instrument Air storage vessel) | Code: E0204 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-07-30 | 2022-07-30 | 2022-07-30
200883C-500-TBT-0811-4000 | [D] | 200883C | 500 | TBT | 811 | 4000 |  | 46 |  | TBT for Vessels (Instrument Air storage vessel) | Code: E0204 | MEC | 500H2 |  |  |  |  | IFP | 100 |  |  | MMEC | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-500-TBT-0910-4000 | [D] | 200883C | 500 | TBT | 910 | 4000 |  | 90 |  | TBT for Centrifugal Pumps (Cooling Water, Chilled Water Circulation, Potable Water) | Code: E0204 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-08-04 | 2022-08-04 | 2022-08-04
200883C-500-TBT-0910-4000 | [D] | 200883C | 500 | TBT | 910 | 4000 |  | 90 |  | TBT for Centrifugal Pumps (Cooling Water, Chilled Water Circulation, Potable Water) | Code: E0204 | MEC | 500H2 |  |  |  |  | IFP | 100 |  |  | MMEC | 2022-09-01 | 2022-09-01 | 2022-09-01
200883C-500-TBT-1310-4000 | [D] | 200883C | 500 | TBT | 1310 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Forged Gate Globe Check Needle Valve | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-05 | 2022-10-05 | 2022-10-05
200883C-500-TBT-1310-4000 | [D] | 200883C | 500 | TBT | 1310 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Forged Gate Globe Check Needle Valve | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-02 | 2022-11-02 | 2022-11-02
200883C-500-TBT-1310-4001 | [D] | 200883C | 500 | TBT | 1310 | 4001 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Cast Gate Globe Check Valve | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-05 | 2022-10-05 | 2022-10-05
200883C-500-TBT-1310-4001 | [D] | 200883C | 500 | TBT | 1310 | 4001 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Cast Gate Globe Check Valve | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-02 | 2022-11-02 | 2022-11-02
200883C-500-TBT-1310-4002 | [D] | 200883C | 500 | TBT | 1310 | 4002 |  | 23 |  | Yuri Phase 0-TBT for Ball Valves | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-05 | 2022-10-05 | 2022-10-05
200883C-500-TBT-1310-4002 | [D] | 200883C | 500 | TBT | 1310 | 4002 |  | 23 |  | Yuri Phase 0-TBT for Ball Valves | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-02 | 2022-11-02 | 2022-11-02
200883C-500-TBT-1310-4003 | [D] | 200883C | 500 | TBT | 1310 | 4003 |  | 23 |  | Yuri Phase 0-TBT for Butterfly Valves | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-05 | 2022-10-05 | 2022-10-05
200883C-500-TBT-1310-4003 | [D] | 200883C | 500 | TBT | 1310 | 4003 |  | 23 |  | Yuri Phase 0-TBT for Butterfly Valves | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-02 | 2022-11-02 | 2022-11-02
200883C-500-TBT-1310-4004 | [D] | 200883C | 500 | TBT | 1310 | 4004 |  | 23 |  | Yuri Phase 0-TBT for Dual Plate Check Valves | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-05 | 2022-10-05 | 2022-10-05
200883C-500-TBT-1310-4004 | [D] | 200883C | 500 | TBT | 1310 | 4004 |  | 23 |  | Yuri Phase 0-TBT for Dual Plate Check Valves | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-02 | 2022-11-02 | 2022-11-02
200883C-500-TBT-1320-4000 | [D] | 200883C | 500 | TBT | 1320 | 4000 |  | 23 |  | Yuri Phase 0-TBT for LTCS,CS Seamless Pipes | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-12 | 2022-10-12 | 2022-10-12
200883C-500-TBT-1320-4000 | [D] | 200883C | 500 | TBT | 1320 | 4000 |  | 23 |  | Yuri Phase 0-TBT for LTCS,CS Seamless Pipes | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-09 | 2022-11-09 | 2022-11-09
200883C-500-TBT-1320-4001 | [D] | 200883C | 500 | TBT | 1320 | 4001 |  | 23 |  | Yuri Phase 0-TBT for LTCS,CS Welded ,Galvanized Pipes | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-12 | 2022-10-12 | 2022-10-12
200883C-500-TBT-1320-4001 | [D] | 200883C | 500 | TBT | 1320 | 4001 |  | 23 |  | Yuri Phase 0-TBT for LTCS,CS Welded ,Galvanized Pipes | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-09 | 2022-11-09 | 2022-11-09
200883C-500-TBT-1324-4000 | [D] | 200883C | 500 | TBT | 1324 | 4000 |  | 23 |  | Yuri Phase 0-TBT for SS Seamless/ Welded Pipes | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-12 | 2022-10-12 | 2022-10-12
200883C-500-TBT-1324-4000 | [D] | 200883C | 500 | TBT | 1324 | 4000 |  | 23 |  | Yuri Phase 0-TBT for SS Seamless/ Welded Pipes | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-09 | 2022-11-09 | 2022-11-09
200883C-500-TBT-1330-4000 | [D] | 200883C | 500 | TBT | 1330 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Wrought Fittings | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-12 | 2022-10-12 | 2022-10-12
200883C-500-TBT-1330-4000 | [D] | 200883C | 500 | TBT | 1330 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Wrought Fittings | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-09 | 2022-11-09 | 2022-11-09
200883C-500-TBT-1340-4000 | [D] | 200883C | 500 | TBT | 1340 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Forged Fittings | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-12 | 2022-10-12 | 2022-10-12
200883C-500-TBT-1340-4000 | [D] | 200883C | 500 | TBT | 1340 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Forged Fittings | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-09 | 2022-11-09 | 2022-11-09
200883C-500-TBT-1350-4000 | [D] | 200883C | 500 | TBT | 1350 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS Flanges, Spectacle Blinds, Paddle & Blanks | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-26 | 2022-10-26 | 2022-10-26
200883C-500-TBT-1350-4000 | [D] | 200883C | 500 | TBT | 1350 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS Flanges, Spectacle Blinds, Paddle & Blanks | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-23 | 2022-11-23 | 2022-11-23
200883C-500-TBT-1360-4000 | [D] | 200883C | 500 | TBT | 1360 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Gaskets | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-26 | 2022-10-26 | 2022-10-26
200883C-500-TBT-1360-4000 | [D] | 200883C | 500 | TBT | 1360 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Gaskets | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-23 | 2022-11-23 | 2022-11-23
200883C-500-TBT-1370-4000 | [D] | 200883C | 500 | TBT | 1370 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Machine Bolts, Stud Bolts & Nuts | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-26 | 2022-10-26 | 2022-10-26
200883C-500-TBT-1370-4000 | [D] | 200883C | 500 | TBT | 1370 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Machine Bolts, Stud Bolts & Nuts | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-23 | 2022-11-23 | 2022-11-23
200883C-500-TBT-1383-4000 | [D] | 200883C | 500 | TBT | 1383 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Spring Hangers / Spring / Rigid Strut Supports | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-26 | 2022-10-26 | 2022-10-26
200883C-500-TBT-1383-4000 | [D] | 200883C | 500 | TBT | 1383 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Spring Hangers / Spring / Rigid Strut Supports | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-23 | 2022-11-23 | 2022-11-23
200883C-500-TBT-1383-4003 | [D] | 200883C | 500 | TBT | 1383 | 4003 |  | 23 |  | Yuri Phase 0-TBT for Anti- vibrating clamp and sliding plates | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-12-19 | 2022-12-19 | 2022-12-19
200883C-500-TBT-1383-4003 | [D] | 200883C | 500 | TBT | 1383 | 4003 |  | 23 |  | Yuri Phase 0-TBT for Anti- vibrating clamp and sliding plates | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2023-01-16 | 2023-01-16 | 2023-01-16
200883C-500-TBT-1394-4000 | [D] | 200883C | 500 | TBT | 1394 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Flexible Hoses, Quick-Connect Couplers & Adaptors | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-26 | 2022-10-26 | 2022-10-26
200883C-500-TBT-1394-4000 | [D] | 200883C | 500 | TBT | 1394 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Flexible Hoses, Quick-Connect Couplers & Adaptors | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-23 | 2022-11-23 | 2022-11-23
200883C-500-TBT-1395-4000 | [D] | 200883C | 500 | TBT | 1395 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Strainers (T & Y type) | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-10-26 | 2022-10-26 | 2022-10-26
200883C-500-TBT-1395-4000 | [D] | 200883C | 500 | TBT | 1395 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Strainers (T & Y type) | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-11-23 | 2022-11-23 | 2022-11-23
200883C-500-TBT-1399-4002 | [D] | 200883C | 500 | TBT | 1399 | 4002 |  | 23 |  | Yuri Phase 0-TBT for U bolts & clamps | Code: E0204 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-12-19 | 2022-12-19 | 2022-12-19
200883C-500-TBT-1399-4002 | [D] | 200883C | 500 | TBT | 1399 | 4002 |  | 23 |  | Yuri Phase 0-TBT for U bolts & clamps | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2023-01-16 | 2023-01-16 | 2023-01-16
200883C-500-TBT-1900-4000 | [D] | 200883C | 500 | TBT | 1900 | 4000 |  | 45 |  | TBT for Safety Equipment | Code: E0204 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-08-07 | 2022-08-07 | 2022-08-07
200883C-500-TBT-1900-4000 | [D] | 200883C | 500 | TBT | 1900 | 4000 |  | 45 |  | TBT for Safety Equipment | Code: E0204 | MEC | 500H2 |  |  |  |  | IFP | 100 |  |  | MMEC | 2022-09-04 | 2022-09-04 | 2022-09-04
200883C-500-TBT-4064-4000 | [D] | 200883C | 500 | TBT | 4064 | 4000 |  | 90 |  | TBT for Handling Equipment (required for items in MOC scope) | Code: E0204 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2023-03-19 | 2023-03-19 | 2023-03-19
200883C-500-TBT-4064-4000 | [D] | 200883C | 500 | TBT | 4064 | 4000 |  | 90 |  | TBT for Handling Equipment (required for items in MOC scope) | Code: E0204 | MEC | 500H2 |  |  |  |  | IFP | 100 |  |  | MMEC | 2023-04-16 | 2023-04-16 | 2023-04-16
200883C-500-TBT-4150-4000 | [D] | 200883C | 500 | TBT | 4150 | 4000 |  | 202 |  | TBT for Refrigeration package | Code: E0204 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-08-03 | 2022-08-03 | 2022-08-08 | 2022-08-08
200883C-500-TBT-4150-4000 | [D] | 200883C | 500 | TBT | 4150 | 4000 |  | 202 |  | TBT for Refrigeration package | Code: E0204 | MEC | 500H2 |  |  |  |  | IFP | 100 |  |  | MMEC | 2022-08-31 | 2022-08-31 | 2022-08-31
200883C-600-CN-1735-2000 | [D] | 200883C | 600 | CN | 1735 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Brownfield Pipe Support / Cable Tray Support Foundation | Code: E0301 | CIV | 600H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-07-08 | 2022-07-08 | 2022-07-08 | 2022-07-08
200883C-600-CN-1735-2000 | [D] | 200883C | 600 | CN | 1735 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Brownfield Pipe Support / Cable Tray Support Foundation | Code: E0301 | CIV | 600H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-07-15 | 2022-07-15 | 2022-08-22 | 2022-08-22
200883C-600-CN-1735-2000 | [D] | 200883C | 600 | CN | 1735 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Brownfield Pipe Support / Cable Tray Support Foundation | Code: E0301 | CIV | 600H2 |  |  |  |  | IFD | 100 |  |  | BCIV | 2022-08-05 | 2022-08-05 | 2022-09-13
200883C-600-DW-1624-4000 | [D] | 200883C | 600 | DW | 1624 | 4000 |  | 41 |  | Yuri Phase 0 - YARA Plant Cable Routing Layout | Code: E0303 | ELE | 600H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-10-03 | 2022-10-03 | 2022-10-03
200883C-600-DW-1624-4000 | [D] | 200883C | 600 | DW | 1624 | 4000 |  | 41 |  | Yuri Phase 0 - YARA Plant Cable Routing Layout | Code: E0303 | ELE | 600H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-10-10 | 2022-10-10 | 2022-10-10
200883C-600-DW-1624-4000 | [D] | 200883C | 600 | DW | 1624 | 4000 |  | 41 |  | Yuri Phase 0 - YARA Plant Cable Routing Layout | Code: E0303 | ELE | 600H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2023-01-31 | 2023-01-31 | 2023-01-31
200883C-600-DW-1624-4001 | [D] | 200883C | 600 | DW | 1624 | 4001 |  | 21 |  | Yuri Phase 0 - YARA Plant Cable Routing Layout (Brown Field scope) | Code: E0303 | ELE | 600H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-11 | 2022-07-11 | 2022-07-16 | 2022-07-16
200883C-600-DW-1624-4001 | [D] | 200883C | 600 | DW | 1624 | 4001 |  | 21 |  | Yuri Phase 0 - YARA Plant Cable Routing Layout (Brown Field scope) | Code: E0303 | ELE | 600H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-07-15 | 2022-07-15 | 2022-08-22 | 2022-08-22
200883C-600-DW-1624-4001 | [D] | 200883C | 600 | DW | 1624 | 4001 |  | 21 |  | Yuri Phase 0 - YARA Plant Cable Routing Layout (Brown Field scope) | Code: E0303 | ELE | 600H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-08-04 | 2022-08-04 | 2022-09-14
200883C-600-DW-1741-2000 | [D] | 200883C | 600 | DW | 1741 | 2000 |  | 38 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (1) | Code: E0303 | CIV | 600H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-07-29 | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-600-DW-1741-2000 | [D] | 200883C | 600 | DW | 1741 | 2000 |  | 38 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (1) | Code: E0303 | CIV | 600H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-08-04 | 2022-08-04 | 2022-08-22 | 2022-08-22
200883C-600-DW-1741-2000 | [D] | 200883C | 600 | DW | 1741 | 2000 |  | 38 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (1) | Code: E0303 | CIV | 600H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-08-22 | 2022-08-22 | 2022-09-13
200883C-600-DW-1741-2001 | [D] | 200883C | 600 | DW | 1741 | 2001 |  | 38 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (2) | Code: E0303 | CIV | 600H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-07-29 | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-600-DW-1741-2001 | [D] | 200883C | 600 | DW | 1741 | 2001 |  | 38 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (2) | Code: E0303 | CIV | 600H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-08-04 | 2022-08-04 | 2022-08-22 | 2022-08-22
200883C-600-DW-1741-2001 | [D] | 200883C | 600 | DW | 1741 | 2001 |  | 38 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (2) | Code: E0303 | CIV | 600H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-08-22 | 2022-08-22 | 2022-09-13
200883C-600-DW-1741-2002 | [D] | 200883C | 600 | DW | 1741 | 2002 |  | 31 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (3) | Code: E0303 | CIV | 600H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-07-29 | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-600-DW-1741-2002 | [D] | 200883C | 600 | DW | 1741 | 2002 |  | 31 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (3) | Code: E0303 | CIV | 600H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-08-04 | 2022-08-04 | 2022-08-22 | 2022-08-22
200883C-600-DW-1741-2002 | [D] | 200883C | 600 | DW | 1741 | 2002 |  | 31 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (3) | Code: E0303 | CIV | 600H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-08-22 | 2022-08-22 | 2022-09-13
200883C-600-DW-1741-2003 | [D] | 200883C | 600 | DW | 1741 | 2003 |  | 31 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (4) | Code: E0303 | CIV | 600H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-07-29 | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-600-DW-1741-2003 | [D] | 200883C | 600 | DW | 1741 | 2003 |  | 31 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (4) | Code: E0303 | CIV | 600H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-08-04 | 2022-08-04 | 2022-08-04
200883C-600-DW-1741-2003 | [D] | 200883C | 600 | DW | 1741 | 2003 |  | 31 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (4) | Code: E0303 | CIV | 600H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-08-22 | 2022-08-22 | 2022-08-22
200883C-600-DW-1821-4000 | [D] | 200883C | 600 | DW | 1821 | 4000 |  | 62 |  | Structural Layout And Section For New Pipe Support Structure PS-1 Inside Existing Plant | Code: E0303 | STR | 600H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-07-04 | 2022-07-04 | 2022-07-01 | 2022-07-01
200883C-600-DW-1821-4000 | [D] | 200883C | 600 | DW | 1821 | 4000 |  | 62 |  | Structural Layout And Section For New Pipe Support Structure PS-1 Inside Existing Plant | Code: E0303 | STR | 600H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-07-08 | 2022-07-08 | 2022-07-07 | 2022-07-07
200883C-600-DW-1821-4000 | [D] | 200883C | 600 | DW | 1821 | 4000 |  | 62 |  | Structural Layout And Section For New Pipe Support Structure PS-1 Inside Existing Plant | Code: E0303 | STR | 600H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-07-29 | 2022-07-29 | 2022-08-12 | 2022-08-12
200883C-600-DW-1821-4001 | [D] | 200883C | 600 | DW | 1821 | 4001 |  | 62 |  | Structural Layout And Section For New Pipe Support Structure PS-2 And Cable Tray Support CT-1 Inside Existing Plant | Code: E0303 | STR | 600H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-07-04 | 2022-07-04 | 2022-07-01 | 2022-07-01
200883C-600-DW-1821-4001 | [D] | 200883C | 600 | DW | 1821 | 4001 |  | 62 |  | Structural Layout And Section For New Pipe Support Structure PS-2 And Cable Tray Support CT-1 Inside Existing Plant | Code: E0303 | STR | 600H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-07-08 | 2022-07-08 | 2022-07-07 | 2022-07-07
200883C-600-DW-1821-4001 | [D] | 200883C | 600 | DW | 1821 | 4001 |  | 62 |  | Structural Layout And Section For New Pipe Support Structure PS-2 And Cable Tray Support CT-1 Inside Existing Plant | Code: E0303 | STR | 600H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-07-29 | 2022-07-29 | 2022-08-12 | 2022-08-12
200883C-600-DW-1821-4002 | [D] | 200883C | 600 | DW | 1821 | 4002 |  | 62 |  | Structural Connection Details For New Pipe Support Structure | Code: E0303 | STR | 600H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-07-04 | 2022-07-04 | 2022-07-01 | 2022-07-01
200883C-600-DW-1821-4002 | [D] | 200883C | 600 | DW | 1821 | 4002 |  | 62 |  | Structural Connection Details For New Pipe Support Structure | Code: E0303 | STR | 600H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-07-08 | 2022-07-08 | 2022-07-07 | 2022-07-07
200883C-600-DW-1821-4002 | [D] | 200883C | 600 | DW | 1821 | 4002 |  | 62 |  | Structural Connection Details For New Pipe Support Structure | Code: E0303 | STR | 600H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-07-29 | 2022-07-29 | 2022-08-12 | 2022-08-12
200883C-600-DW-1821-4003 | [D] | 200883C | 600 | DW | 1821 | 4003 |  | 62 |  | Structural Layout for Brownfield Structural Modification | Code: E0303 | STR | 600H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-07-04 | 2022-07-04 | 2022-07-01 | 2022-07-01
200883C-600-DW-1821-4003 | [D] | 200883C | 600 | DW | 1821 | 4003 |  | 62 |  | Structural Layout for Brownfield Structural Modification | Code: E0303 | STR | 600H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-07-08 | 2022-07-08 | 2022-07-20 | 2022-07-20
200883C-600-DW-1821-4003 | [D] | 200883C | 600 | DW | 1821 | 4003 |  | 62 |  | Structural Layout for Brownfield Structural Modification | Code: E0303 | STR | 600H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-07-29 | 2022-07-29 | 2022-08-16 | 2022-08-16
200883C-600-DW-1821-4004 | [D] | 200883C | 600 | DW | 1821 | 4004 |  | 62 |  | Structural Details for Brownfield Structural Modifications-1 | Code: E0303 | STR | 600H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-07-04 | 2022-07-04 | 2022-07-01 | 2022-07-01
200883C-600-DW-1821-4004 | [D] | 200883C | 600 | DW | 1821 | 4004 |  | 62 |  | Structural Details for Brownfield Structural Modifications-1 | Code: E0303 | STR | 600H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-07-08 | 2022-07-08 | 2022-07-20 | 2022-07-20
200883C-600-DW-1821-4004 | [D] | 200883C | 600 | DW | 1821 | 4004 |  | 62 |  | Structural Details for Brownfield Structural Modifications-1 | Code: E0303 | STR | 600H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-07-29 | 2022-07-29 | 2022-08-16 | 2022-08-16
200883C-600-DW-1821-4005 | [D] | 200883C | 600 | DW | 1821 | 4005 |  | 46 |  | Structural Details for Brownfield Structural Modifications-2 | Code: E0303 | STR | 600H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-07-04 | 2022-07-04 | 2022-07-01 | 2022-07-01
200883C-600-DW-1821-4005 | [D] | 200883C | 600 | DW | 1821 | 4005 |  | 46 |  | Structural Details for Brownfield Structural Modifications-2 | Code: E0303 | STR | 600H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-07-08 | 2022-07-08 | 2022-07-23 | 2022-07-23
200883C-600-DW-1821-4005 | [D] | 200883C | 600 | DW | 1821 | 4005 |  | 46 |  | Structural Details for Brownfield Structural Modifications-2 | Code: E0303 | STR | 600H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-07-29 | 2022-07-29 | 2022-08-16 | 2022-08-16
200883C-600-DW-1821-4006 | [D] | 200883C | 600 | DW | 1821 | 4006 |  | 46 |  | Structural Connection Details for Brownfield Structural Modification | Code: E0303 | STR | 600H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-07-04 | 2022-07-04 | 2022-07-01 | 2022-07-01
200883C-600-DW-1821-4006 | [D] | 200883C | 600 | DW | 1821 | 4006 |  | 46 |  | Structural Connection Details for Brownfield Structural Modification | Code: E0303 | STR | 600H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-07-08 | 2022-07-08 | 2022-07-20 | 2022-07-20
200883C-600-DW-1821-4006 | [D] | 200883C | 600 | DW | 1821 | 4006 |  | 46 |  | Structural Connection Details for Brownfield Structural Modification | Code: E0303 | STR | 600H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-07-29 | 2022-07-29 | 2022-08-16 | 2022-08-16
200883C-600-DW-1825-4000 | [D] | 200883C | 600 | DW | 1825 | 4000 |  | 31 |  | Yuri Phase 0 - Miscellaneous Pipe Support Details for H2 Line | Code: E0303 | STR | 600H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-07-04 | 2022-07-04 | 2022-07-01 | 2022-07-01
200883C-600-DW-1825-4000 | [D] | 200883C | 600 | DW | 1825 | 4000 |  | 31 |  | Yuri Phase 0 - Miscellaneous Pipe Support Details for H2 Line | Code: E0303 | STR | 600H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-07-08 | 2022-07-08 | 2022-07-23 | 2022-07-23
200883C-600-DW-1825-4000 | [D] | 200883C | 600 | DW | 1825 | 4000 |  | 31 |  | Yuri Phase 0 - Miscellaneous Pipe Support Details for H2 Line | Code: E0303 | STR | 600H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-600-DW-1825-4001 | [D] | 200883C | 600 | DW | 1825 | 4001 |  | 31 |  | Miscllaneous Details for Pipe/Cable Tray Supports inside existing plant-2 | Code: E0303 | STR | 600H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-07-04 | 2022-07-04 | 2022-07-01 | 2022-07-01
200883C-600-DW-1825-4001 | [D] | 200883C | 600 | DW | 1825 | 4001 |  | 31 |  | Miscllaneous Details for Pipe/Cable Tray Supports inside existing plant-2 | Code: E0303 | STR | 600H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-07-08 | 2022-07-08 | 2022-07-18 | 2022-07-18
200883C-600-DW-1825-4001 | [D] | 200883C | 600 | DW | 1825 | 4001 |  | 31 |  | Miscllaneous Details for Pipe/Cable Tray Supports inside existing plant-2 | Code: E0303 | STR | 600H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-07-29 | 2022-07-29 | 2022-07-18 | 2022-07-18
200883C-600-MR-1310-4000 | [D] | 200883C | 600 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Gate Globe Check Valve | Code: E0610 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-04 | 2022-07-04 | 2022-06-01 | 2022-06-01
200883C-600-MR-1310-4000 | [D] | 200883C | 600 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Gate Globe Check Valve | Code: E0610 | PIP | 600H2 |  |  |  |  | IFQ | 40 |  |  | MPIP | 2022-07-08 | 2022-07-08 | 2022-06-27 | 2022-06-27
200883C-600-MR-1310-4000 | [D] | 200883C | 600 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Gate Globe Check Valve | Code: E0610 | PIP | 600H2 |  |  |  |  | IFP | 70 |  |  | MPIP | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-600-MR-1310-4000 | [D] | 200883C | 600 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Gate Globe Check Valve | Code: E0610 | PIP | 600H2 |  |  |  |  | VDR1 | 80 |  |  | MPIP | 2022-10-18 | 2022-10-18 | 2022-10-18
200883C-600-MR-1310-4000 | [D] | 200883C | 600 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Gate Globe Check Valve | Code: E0610 | PIP | 600H2 |  |  |  |  | VDR2 | 90 |  |  | MPIP | 2022-11-08 | 2022-11-08 | 2022-11-08
200883C-600-MR-1310-4000 | [D] | 200883C | 600 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Gate Globe Check Valve | Code: E0610 | PIP | 600H2 |  |  |  |  | VDR3 | 100 |  |  | MPIP | 2022-11-29 | 2022-11-29 | 2022-11-29
200883C-600-MR-1320-4000 | [D] | 200883C | 600 | MR | 1320 | 4000 |  | 23 |  | Yuri Phase 0-MR for AS, CS, SS Seamless Pipes | Code: E0310 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-04 | 2022-07-04 | 2022-06-01 | 2022-06-01
200883C-600-MR-1320-4000 | [D] | 200883C | 600 | MR | 1320 | 4000 |  | 23 |  | Yuri Phase 0-MR for AS, CS, SS Seamless Pipes | Code: E0310 | PIP | 600H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-07-08 | 2022-07-08 | 2022-06-24 | 2022-06-24
200883C-600-MR-1320-4000 | [D] | 200883C | 600 | MR | 1320 | 4000 |  | 23 |  | Yuri Phase 0-MR for AS, CS, SS Seamless Pipes | Code: E0310 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-600-MR-1330-4000 | [D] | 200883C | 600 | MR | 1330 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Wrought Fittings | Code: E0310 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-04 | 2022-07-04 | 2022-06-01 | 2022-06-01
200883C-600-MR-1330-4000 | [D] | 200883C | 600 | MR | 1330 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Wrought Fittings | Code: E0310 | PIP | 600H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-07-08 | 2022-07-08 | 2022-06-27 | 2022-06-27
200883C-600-MR-1330-4000 | [D] | 200883C | 600 | MR | 1330 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Wrought Fittings | Code: E0310 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-600-MR-1340-4000 | [D] | 200883C | 600 | MR | 1340 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Fittings | Code: E0310 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-04 | 2022-07-04 | 2022-06-01 | 2022-06-01
200883C-600-MR-1340-4000 | [D] | 200883C | 600 | MR | 1340 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Fittings | Code: E0310 | PIP | 600H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-07-08 | 2022-07-08 | 2022-06-27 | 2022-06-27
200883C-600-MR-1340-4000 | [D] | 200883C | 600 | MR | 1340 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Fittings | Code: E0310 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-600-MR-1350-4000 | [D] | 200883C | 600 | MR | 1350 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS Flanges, Spectacle Blinds, Paddle & Blanks | Code: E0310 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-04 | 2022-07-04 | 2022-06-01 | 2022-06-01
200883C-600-MR-1350-4000 | [D] | 200883C | 600 | MR | 1350 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS Flanges, Spectacle Blinds, Paddle & Blanks | Code: E0310 | PIP | 600H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-07-08 | 2022-07-08 | 2022-06-27 | 2022-06-27
200883C-600-MR-1350-4000 | [D] | 200883C | 600 | MR | 1350 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS Flanges, Spectacle Blinds, Paddle & Blanks | Code: E0310 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-600-MR-1360-4000 | [D] | 200883C | 600 | MR | 1360 | 4000 |  | 23 |  | Yuri Phase 0-MR for Gaskets | Code: E0310 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-04 | 2022-07-04 | 2022-07-01 | 2022-07-01
200883C-600-MR-1360-4000 | [D] | 200883C | 600 | MR | 1360 | 4000 |  | 23 |  | Yuri Phase 0-MR for Gaskets | Code: E0310 | PIP | 600H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-07-08 | 2022-07-08 | 2022-07-01 | 2022-07-01
200883C-600-MR-1360-4000 | [D] | 200883C | 600 | MR | 1360 | 4000 |  | 23 |  | Yuri Phase 0-MR for Gaskets | Code: E0310 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-600-MR-1370-4000 | [D] | 200883C | 600 | MR | 1370 | 4000 |  | 23 |  | Yuri Phase 0-MR for Machine Bolts, Stud Bolts & Nuts | Code: E0310 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-04 | 2022-07-04 | 2022-06-01 | 2022-06-01
200883C-600-MR-1370-4000 | [D] | 200883C | 600 | MR | 1370 | 4000 |  | 23 |  | Yuri Phase 0-MR for Machine Bolts, Stud Bolts & Nuts | Code: E0310 | PIP | 600H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-07-08 | 2022-07-08 | 2022-07-01 | 2022-07-01
200883C-600-MR-1370-4000 | [D] | 200883C | 600 | MR | 1370 | 4000 |  | 23 |  | Yuri Phase 0-MR for Machine Bolts, Stud Bolts & Nuts | Code: E0310 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-600-MR-1383-4000 | [D] | 200883C | 600 | MR | 1383 | 4000 |  | 23 |  | Yuri Phase 0-MR for Supports | Code: E0310 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-04 | 2022-07-04 | 2022-07-01 | 2022-07-01
200883C-600-MR-1383-4000 | [D] | 200883C | 600 | MR | 1383 | 4000 |  | 23 |  | Yuri Phase 0-MR for Supports | Code: E0310 | PIP | 600H2 |  |  |  |  | IFQ | 70 |  |  | MPIP | 2022-07-08 | 2022-07-08 | 2022-08-05 | 2022-08-05
200883C-600-MR-1383-4000 | [D] | 200883C | 600 | MR | 1383 | 4000 |  | 23 |  | Yuri Phase 0-MR for Supports | Code: E0310 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-09-27 | 2022-09-27 | 2022-09-27
200883C-600-MR-1572-4000 | [D] | 200883C | 600 | MR | 1572 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Cable Tray And Accessories- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-11 | 2022-07-11 | 2022-07-18 | 2022-07-18
200883C-600-MR-1572-4000 | [D] | 200883C | 600 | MR | 1572 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Cable Tray And Accessories- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-07-18 | 2022-07-18 | 2022-07-18 | 2022-07-18
200883C-600-MR-1572-4000 | [D] | 200883C | 600 | MR | 1572 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Cable Tray And Accessories- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-10-25 | 2022-10-25 | 2022-07-18 | 2022-07-18
200883C-600-MR-1572-4000 | [D] | 200883C | 600 | MR | 1572 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Cable Tray And Accessories- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2022-11-22 | 2022-11-22 | 2022-07-18 | 2022-07-18
200883C-600-MR-1572-4000 | [D] | 200883C | 600 | MR | 1572 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Cable Tray And Accessories- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2022-12-20 | 2022-12-20 | 2022-07-18 | 2022-07-18
200883C-600-MR-1572-4000 | [D] | 200883C | 600 | MR | 1572 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Cable Tray And Accessories- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-01-17 | 2023-01-17 | 2022-07-18 | 2022-07-18
200883C-600-MR-1574-4000 | [D] | 200883C | 600 | MR | 1574 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Instrument Cables- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-11 | 2022-07-11 | 2022-07-23 | 2022-07-23
200883C-600-MR-1574-4000 | [D] | 200883C | 600 | MR | 1574 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Instrument Cables- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-07-18 | 2022-07-18 | 2022-07-29 | 2022-07-29
200883C-600-MR-1574-4000 | [D] | 200883C | 600 | MR | 1574 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Instrument Cables- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-10-25 | 2022-10-25 | 2022-10-25
200883C-600-MR-1574-4000 | [D] | 200883C | 600 | MR | 1574 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Instrument Cables- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2022-11-22 | 2022-11-22 | 2022-11-22
200883C-600-MR-1574-4000 | [D] | 200883C | 600 | MR | 1574 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Instrument Cables- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2022-12-20 | 2022-12-20 | 2022-12-20
200883C-600-MR-1574-4000 | [D] | 200883C | 600 | MR | 1574 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Instrument Cables- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-01-17 | 2023-01-17 | 2023-01-17
200883C-600-MR-1575-4000 | [D] | 200883C | 600 | MR | 1575 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For cable glands- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-11 | 2022-07-11 | 2022-07-23 | 2022-07-23
200883C-600-MR-1575-4000 | [D] | 200883C | 600 | MR | 1575 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For cable glands- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-07-18 | 2022-07-18 | 2022-08-05 | 2022-08-05
200883C-600-MR-1575-4000 | [D] | 200883C | 600 | MR | 1575 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For cable glands- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-10-25 | 2022-10-25 | 2022-08-05 | 2022-08-05
200883C-600-MR-1575-4000 | [D] | 200883C | 600 | MR | 1575 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For cable glands- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | VDR1 | 80 |  |  | MINS | 2022-11-22 | 2022-11-22 | 2022-08-05 | 2022-08-05
200883C-600-MR-1575-4000 | [D] | 200883C | 600 | MR | 1575 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For cable glands- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | VDR2 | 90 |  |  | MINS | 2022-12-20 | 2022-12-20 | 2022-08-05 | 2022-08-05
200883C-600-MR-1575-4000 | [D] | 200883C | 600 | MR | 1575 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For cable glands- Brown Field | Code: E0610 | INS | 600H2 |  |  |  |  | VDR3 | 100 |  |  | MINS | 2023-01-17 | 2023-01-17 | 2022-08-05 | 2022-08-05
200883C-600-MR-1621-4000 | [D] | 200883C | 600 | MR | 1621 | 4000 |  | 41 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Brownfield | Code: E0610 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-13 | 2022-07-13 | 2022-07-23 | 2022-07-23
200883C-600-MR-1621-4000 | [D] | 200883C | 600 | MR | 1621 | 4000 |  | 41 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Brownfield | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-07-20 | 2022-07-20 | 2022-07-26 | 2022-07-26
200883C-600-MR-1621-4000 | [D] | 200883C | 600 | MR | 1621 | 4000 |  | 41 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Brownfield | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-10-25 | 2022-10-25 | 2022-10-25
200883C-600-MR-1621-4000 | [D] | 200883C | 600 | MR | 1621 | 4000 |  | 41 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Brownfield | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MELE | 2022-11-22 | 2022-11-22 | 2022-11-22
200883C-600-MR-1621-4000 | [D] | 200883C | 600 | MR | 1621 | 4000 |  | 41 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Brownfield | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MELE | 2022-12-20 | 2022-12-20 | 2022-12-20
200883C-600-MR-1621-4000 | [D] | 200883C | 600 | MR | 1621 | 4000 |  | 41 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Brownfield | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MELE | 2023-01-17 | 2023-01-17 | 2023-01-17
200883C-600-MR-1623-4000 | [D] | 200883C | 600 | MR | 1623 | 4000 |  | 41 |  | Yuri Phase 0 - Cable Trays And Ladders - Brownfield | Code: E0610 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-13 | 2022-07-13 | 2022-07-23 | 2022-07-23
200883C-600-MR-1623-4000 | [D] | 200883C | 600 | MR | 1623 | 4000 |  | 41 |  | Yuri Phase 0 - Cable Trays And Ladders - Brownfield | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-07-20 | 2022-07-20 | 2022-08-06 | 2022-08-06
200883C-600-MR-1623-4000 | [D] | 200883C | 600 | MR | 1623 | 4000 |  | 41 |  | Yuri Phase 0 - Cable Trays And Ladders - Brownfield | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-10-25 | 2022-10-25 | 2022-10-25
200883C-600-MR-1623-4000 | [D] | 200883C | 600 | MR | 1623 | 4000 |  | 41 |  | Yuri Phase 0 - Cable Trays And Ladders - Brownfield | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR1 | 80 |  |  | MELE | 2022-11-22 | 2022-11-22 | 2022-11-22
200883C-600-MR-1623-4000 | [D] | 200883C | 600 | MR | 1623 | 4000 |  | 41 |  | Yuri Phase 0 - Cable Trays And Ladders - Brownfield | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR2 | 90 |  |  | MELE | 2022-12-20 | 2022-12-20 | 2022-12-20
200883C-600-MR-1623-4000 | [D] | 200883C | 600 | MR | 1623 | 4000 |  | 41 |  | Yuri Phase 0 - Cable Trays And Ladders - Brownfield | Code: E0610 | ELE | 000H2 |  |  |  |  | VDR3 | 100 |  |  | MELE | 2023-01-17 | 2023-01-17 | 2023-01-17
200883C-600-MTO-1311-4000 | [D] | 200883C | 600 | MTO | 1311 | 4000 |  | 45 |  | Yuri Phase 0-Piping Bulk MTO-1 | Code: E0204 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-25 | 2022-07-25 | 2022-07-25 | 2022-07-25
200883C-600-MTO-1311-4000 | [D] | 200883C | 600 | MTO | 1311 | 4000 |  | 45 |  | Yuri Phase 0-Piping Bulk MTO-1 | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-07-29 | 2022-07-29 | 2022-08-19
200883C-600-NM-0050-4000 | [D] | 200883C | 600 | NM | 50 | 4000 |  | 24 |  | Yuri Phase 0 - Tie-In List | Code: E0311 | PRO | 600H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-05-30 | 2022-05-30 | 2022-05-30 | 2022-05-30
200883C-600-NM-0050-4000 | [D] | 200883C | 600 | NM | 50 | 4000 |  | 24 |  | Yuri Phase 0 - Tie-In List | Code: E0311 | PRO | 600H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-06-03 | 2022-06-03 | 2022-07-01 | 2022-07-01
200883C-600-NM-0050-4000 | [D] | 200883C | 600 | NM | 50 | 4000 |  | 24 |  | Yuri Phase 0 - Tie-In List | Code: E0311 | PRO | 600H2 |  |  |  |  | IFU | 100 |  |  | MPRO | 2022-07-01 | 2022-07-01 | 2022-07-22 | 2022-07-22
200883C-600-NM-1350-4000 | [D] | 200883C | 600 | NM | 1350 | 4000 |  | 45 |  | Yuri Phase 0-Isometric drawings- YPF Tie-In | Code: E0203 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2023-01-19 | 2023-01-19 | 2022-08-15 | 2022-08-15
200883C-600-NM-1350-4000 | [D] | 200883C | 600 | NM | 1350 | 4000 |  | 45 |  | Yuri Phase 0-Isometric drawings- YPF Tie-In | Code: E0203 | PIP | 600H2 |  |  |  |  | IFC | 100 |  |  | MPIP | 2023-03-31 | 2023-03-31 | 2022-08-15
200883C-600-PID-0021-4000 | [D] | 200883C | 600 | PID | 21 | 4000 |  | 24 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Potable Water | Code: E0501 | PRO | 600H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-600-PID-0021-4000 | [D] | 200883C | 600 | PID | 21 | 4000 |  | 24 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Potable Water | Code: E0501 | PRO | 600H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-17 | 2022-06-17
200883C-600-PID-0021-4000 | [D] | 200883C | 600 | PID | 21 | 4000 |  | 24 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Potable Water | Code: E0501 | PRO | 600H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-06-25 | 2022-06-25
200883C-600-PID-0021-4000 | [D] | 200883C | 600 | PID | 21 | 4000 |  | 24 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Potable Water | Code: E0501 | PRO | 600H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-600-PID-0021-4000 | [D] | 200883C | 600 | PID | 21 | 4000 |  | 24 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Potable Water | Code: E0501 | PRO | 600H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-600-PID-0021-4001 | [D] | 200883C | 600 | PID | 21 | 4001 |  | 24 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for DM Water | Code: E0501 | PRO | 600H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-600-PID-0021-4001 | [D] | 200883C | 600 | PID | 21 | 4001 |  | 24 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for DM Water | Code: E0501 | PRO | 600H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-17 | 2022-06-17
200883C-600-PID-0021-4001 | [D] | 200883C | 600 | PID | 21 | 4001 |  | 24 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for DM Water | Code: E0501 | PRO | 600H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-06-25 | 2022-06-25
200883C-600-PID-0021-4001 | [D] | 200883C | 600 | PID | 21 | 4001 |  | 24 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for DM Water | Code: E0501 | PRO | 600H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-600-PID-0021-4001 | [D] | 200883C | 600 | PID | 21 | 4001 |  | 24 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for DM Water | Code: E0501 | PRO | 600H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-600-PID-0021-4002 | [D] | 200883C | 600 | PID | 21 | 4002 |  | 12 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Hydrogen | Code: E0501 | PRO | 600H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-600-PID-0021-4002 | [D] | 200883C | 600 | PID | 21 | 4002 |  | 12 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Hydrogen | Code: E0501 | PRO | 600H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-17 | 2022-06-17
200883C-600-PID-0021-4002 | [D] | 200883C | 600 | PID | 21 | 4002 |  | 12 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Hydrogen | Code: E0501 | PRO | 600H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-06-25 | 2022-06-25
200883C-600-PID-0021-4002 | [D] | 200883C | 600 | PID | 21 | 4002 |  | 12 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Hydrogen | Code: E0501 | PRO | 600H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-600-PID-0021-4002 | [D] | 200883C | 600 | PID | 21 | 4002 |  | 12 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Hydrogen | Code: E0501 | PRO | 600H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-600-PID-0021-4003 | [D] | 200883C | 600 | PID | 21 | 4003 |  | 12 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Instrument Air and Nitrogen | Code: E0501 | PRO | 600H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-04-03 | 2022-04-03 | 2022-04-03 | 2022-04-03
200883C-600-PID-0021-4003 | [D] | 200883C | 600 | PID | 21 | 4003 |  | 12 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Instrument Air and Nitrogen | Code: E0501 | PRO | 600H2 |  |  |  |  | IFR | 40 |  |  | MPRO | 2022-05-27 | 2022-05-27 | 2022-06-17 | 2022-06-17
200883C-600-PID-0021-4003 | [D] | 200883C | 600 | PID | 21 | 4003 |  | 12 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Instrument Air and Nitrogen | Code: E0501 | PRO | 600H2 |  |  |  |  | IFH | 60 |  |  | MPRO | 2022-07-08 | 2022-07-08 | 2022-06-25 | 2022-06-25
200883C-600-PID-0021-4003 | [D] | 200883C | 600 | PID | 21 | 4003 |  | 12 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Instrument Air and Nitrogen | Code: E0501 | PRO | 600H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-600-PID-0021-4003 | [D] | 200883C | 600 | PID | 21 | 4003 |  | 12 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Instrument Air and Nitrogen | Code: E0501 | PRO | 600H2 |  |  |  |  | IFC | 100 |  |  | MPRO | 2023-01-04 | 2023-01-04 | 2023-01-04
200883C-600-RT-1300-1000 | [D] | 200883C | 600 | RT | 1300 | 1000 |  | 40 |  | Yuri Phase 0 – Site Survey – Site Survey Report | Code: E0303 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | APIP | 2022-07-02 | 2022-07-02 | 2022-05-27 | 2022-05-27
200883C-600-RT-1300-1000 | [D] | 200883C | 600 | RT | 1300 | 1000 |  | 40 |  | Yuri Phase 0 – Site Survey – Site Survey Report | Code: E0303 | PIP | 600H2 |  |  |  |  | IFR | 70 |  |  | APIP | 2022-07-02 | 2022-07-02 | 2022-05-27 | 2022-05-27
200883C-600-RT-1300-1000 | [D] | 200883C | 600 | RT | 1300 | 1000 |  | 40 |  | Yuri Phase 0 – Site Survey – Site Survey Report | Code: E0303 | PIP | 600H2 |  |  |  |  | IFC | 100 |  |  | APIP | 2022-08-31 | 2022-08-31 | 2022-08-31
200883C-600-RT-1800-4000 | [D] | 200883C | 600 | RT | 1800 | 4000 |  | 62 |  | Structural Steel Design Report for Brownfield Structural Modifications | Code: E0301 | STR | 600H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-07-04 | 2022-07-04 | 2022-07-01 | 2022-07-01
200883C-600-RT-1800-4000 | [D] | 200883C | 600 | RT | 1800 | 4000 |  | 62 |  | Structural Steel Design Report for Brownfield Structural Modifications | Code: E0301 | STR | 600H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-07-08 | 2022-07-08 | 2022-07-20 | 2022-07-20
200883C-600-RT-1800-4000 | [D] | 200883C | 600 | RT | 1800 | 4000 |  | 62 |  | Structural Steel Design Report for Brownfield Structural Modifications | Code: E0301 | STR | 600H2 |  |  |  |  | IFD | 100 |  |  | MSTR | 2022-07-29 | 2022-07-29 | 2022-08-16 | 2022-08-16
200883C-600-RT-1800-4001 | [D] | 200883C | 600 | RT | 1800 | 4001 |  | 62 |  | Yuri Phase 0 - Structural Steel Design Report for New Structure and Cable Tray Support Inside Existing Plant | Code: E0301 | STR | 600H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-07-04 | 2022-07-04 | 2022-07-01 | 2022-07-01
200883C-600-RT-1800-4001 | [D] | 200883C | 600 | RT | 1800 | 4001 |  | 62 |  | Yuri Phase 0 - Structural Steel Design Report for New Structure and Cable Tray Support Inside Existing Plant | Code: E0301 | STR | 600H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-07-08 | 2022-07-08 | 2022-07-23 | 2022-07-23
200883C-600-RT-1800-4001 | [D] | 200883C | 600 | RT | 1800 | 4001 |  | 62 |  | Yuri Phase 0 - Structural Steel Design Report for New Structure and Cable Tray Support Inside Existing Plant | Code: E0301 | STR | 600H2 |  |  |  |  | IFD | 100 |  |  | MSTR | 2022-07-29 | 2022-07-29 | 2022-08-16 | 2022-08-16
200883C-600-SOW-1300-0001 | [D] | 200883C | 600 | SOW | 1300 | 1 |  | 40 |  | Yuri Phase 0 - Piping Survey - Scope of Work | Code: E0303 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | APIP | 2022-05-16 | 2022-05-16 | 2022-04-05 | 2022-04-05
200883C-600-SOW-1300-0001 | [D] | 200883C | 600 | SOW | 1300 | 1 |  | 40 |  | Yuri Phase 0 - Piping Survey - Scope of Work | Code: E0303 | PIP | 600H2 |  |  |  |  | IFR | 70 |  |  | APIP | 2022-07-02 | 2022-07-02 | 2022-04-19 | 2022-04-19
200883C-600-SOW-1300-0001 | [D] | 200883C | 600 | SOW | 1300 | 1 |  | 40 |  | Yuri Phase 0 - Piping Survey - Scope of Work | Code: E0303 | PIP | 600H2 |  |  |  |  | IFC | 100 |  |  | APIP | 2022-08-31 | 2022-08-31 | 2022-08-15 | 2022-08-15
200883C-600-SOW-1600-4000 | [D] | 200883C | 600 | SOW | 1600 | 4000 |  | 100 |  | Yuri Phase 0 - Scope of Work - 11KV Switchgear Panel Modifications | Code: E0303 | ELE | 600H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-06-09 | 2022-06-09 | 2022-06-09 | 2022-06-09
200883C-600-SOW-1600-4000 | [D] | 200883C | 600 | SOW | 1600 | 4000 |  | 100 |  | Yuri Phase 0 - Scope of Work - 11KV Switchgear Panel Modifications | Code: E0303 | ELE | 600H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-06-15 | 2022-06-15 | 2022-07-06 | 2022-07-06
200883C-600-SOW-1600-4000 | [D] | 200883C | 600 | SOW | 1600 | 4000 |  | 100 |  | Yuri Phase 0 - Scope of Work - 11KV Switchgear Panel Modifications | Code: E0303 | ELE | 600H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-07-27 | 2022-07-27 | 2022-08-18 | 2022-08-18
200883C-600-TBT-1310-4000 | [D] | 200883C | 600 | TBT | 1310 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Forged Gate Globe Check Valve | Code: E0204 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-30 | 2022-07-30 | 2022-08-08 | 2022-08-08
200883C-600-TBT-1310-4000 | [D] | 200883C | 600 | TBT | 1310 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Forged Gate Globe Check Valve | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1320-4000 | [D] | 200883C | 600 | TBT | 1320 | 4000 |  | 23 |  | Yuri Phase 0-TBT for AS, CS, SS Seamless Pipes | Code: E0204 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-30 | 2022-07-30 | 2022-08-08 | 2022-08-08
200883C-600-TBT-1320-4000 | [D] | 200883C | 600 | TBT | 1320 | 4000 |  | 23 |  | Yuri Phase 0-TBT for AS, CS, SS Seamless Pipes | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1340-4000 | [D] | 200883C | 600 | TBT | 1340 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Forged Fittings | Code: E0204 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-30 | 2022-07-30 | 2022-08-08 | 2022-08-08
200883C-600-TBT-1340-4000 | [D] | 200883C | 600 | TBT | 1340 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Forged Fittings | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1340-4001 | [D] | 200883C | 600 | TBT | 1340 | 4001 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Wrought Fittings | Code: E0204 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-30 | 2022-07-30 | 2022-07-30
200883C-600-TBT-1340-4001 | [D] | 200883C | 600 | TBT | 1340 | 4001 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Wrought Fittings | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1350-4000 | [D] | 200883C | 600 | TBT | 1350 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS Flanges, Spectacle Blinds, Paddle & Blanks | Code: E0204 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-30 | 2022-07-30 | 2022-08-08 | 2022-08-08
200883C-600-TBT-1350-4000 | [D] | 200883C | 600 | TBT | 1350 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS Flanges, Spectacle Blinds, Paddle & Blanks | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1360-4000 | [D] | 200883C | 600 | TBT | 1360 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Gaskets | Code: E0204 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-30 | 2022-07-30 | 2022-08-08 | 2022-08-08
200883C-600-TBT-1360-4000 | [D] | 200883C | 600 | TBT | 1360 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Gaskets | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1370-4000 | [D] | 200883C | 600 | TBT | 1370 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Machine Bolts, Stud Bolts & Nuts | Code: E0204 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-30 | 2022-07-30 | 2022-08-08 | 2022-08-08
200883C-600-TBT-1370-4000 | [D] | 200883C | 600 | TBT | 1370 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Machine Bolts, Stud Bolts & Nuts | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1383-4000 | [D] | 200883C | 600 | TBT | 1383 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Supports | Code: E0204 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-30 | 2022-07-30 | 2022-07-30
200883C-600-TBT-1383-4000 | [D] | 200883C | 600 | TBT | 1383 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Supports | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1572-4000 | [D] | 200883C | 600 | TBT | 1572 | 4000 |  | 16 |  | Yuri Phase 0 - Technical Bid Tabulation For Cable Tray And Accessories- Brown Field | Code: E0204 | INS | 600H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-18 | 2022-08-18 | 2022-07-18 | 2022-07-18
200883C-600-TBT-1572-4000 | [D] | 200883C | 600 | TBT | 1572 | 4000 |  | 16 |  | Yuri Phase 0 - Technical Bid Tabulation For Cable Tray And Accessories- Brown Field | Code: E0204 | INS | 600H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-15 | 2022-09-15 | 2022-07-18 | 2022-07-18
200883C-600-TBT-1574-4000 | [D] | 200883C | 600 | TBT | 1574 | 4000 |  | 16 |  | Yuri Phase 0 - Technical Bid Tabulation For Instrument Cables-Brown Field | Code: E0204 | INS | 600H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-18 | 2022-08-18 | 2022-08-18
200883C-600-TBT-1574-4000 | [D] | 200883C | 600 | TBT | 1574 | 4000 |  | 16 |  | Yuri Phase 0 - Technical Bid Tabulation For Instrument Cables-Brown Field | Code: E0204 | INS | 600H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-15 | 2022-09-15 | 2022-09-15
200883C-600-TBT-1575-4000 | [D] | 200883C | 600 | TBT | 1575 | 4000 |  | 16 |  | Yuri Phase 0 - Technical Bid Tabulation For cable glands- Brown Field | Code: E0204 | INS | 600H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-18 | 2022-08-18 | 2022-08-05 | 2022-08-05
200883C-600-TBT-1575-4000 | [D] | 200883C | 600 | TBT | 1575 | 4000 |  | 16 |  | Yuri Phase 0 - Technical Bid Tabulation For cable glands- Brown Field | Code: E0204 | INS | 600H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-15 | 2022-09-15 | 2022-08-05 | 2022-08-05
200883C-600-TBT-1621-4001 | [D] | 200883C | 600 | TBT | 1621 | 4001 |  | 21 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Brownfield | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-08-20 | 2022-08-20 | 2022-08-20
200883C-600-TBT-1621-4001 | [D] | 200883C | 600 | TBT | 1621 | 4001 |  | 21 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Brownfield | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-09-17 | 2022-09-17 | 2022-09-17
200883C-600-TBT-1623-4001 | [D] | 200883C | 600 | TBT | 1623 | 4001 |  | 21 |  | Yuri Phase 0 - Cable Trays And Ladders - Brownfield | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-08-20 | 2022-08-20 | 2022-08-20
200883C-600-TBT-1623-4001 | [D] | 200883C | 600 | TBT | 1623 | 4001 |  | 21 |  | Yuri Phase 0 - Cable Trays And Ladders - Brownfield | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-09-17 | 2022-09-17 | 2022-09-17
200883C-700-DW-1532-5000 | [D] | 200883C | 700 | DW | 1532 | 5000 |  | 1 |  | Yuri Phase 0 - PPM Location Layout Drawing (DELETED 3-Aug-22) | Code: E0303 | INS | 700PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-05-20 | 2022-05-20 | 2022-05-20 | 2022-05-20
200883C-700-DW-1532-5000 | [D] | 200883C | 700 | DW | 1532 | 5000 |  | 1 |  | Yuri Phase 0 - PPM Location Layout Drawing (DELETED 3-Aug-22) | Code: E0303 | INS | 700PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-06-19 | 2022-06-19 | 2022-07-29 | 2022-07-29
200883C-700-DW-1532-5000 | [D] | 200883C | 700 | DW | 1532 | 5000 |  | 1 |  | Yuri Phase 0 - PPM Location Layout Drawing (DELETED 3-Aug-22) | Code: E0303 | INS | 700PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-07-19 | 2022-07-19 | 2022-07-29 | 2022-07-29
200883C-700-DW-1532-5001 | [D] | 200883C | 700 | DW | 1532 | 5001 |  | 1 |  | Yuri Phase 0 - PPM Network Connection Diagram (DELETED 3-Aug-22) | Code: E0303 | INS | 700PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-05-18 | 2022-05-18 | 2022-05-18 | 2022-05-18
200883C-700-DW-1532-5001 | [D] | 200883C | 700 | DW | 1532 | 5001 |  | 1 |  | Yuri Phase 0 - PPM Network Connection Diagram (DELETED 3-Aug-22) | Code: E0303 | INS | 700PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-06-17 | 2022-06-17 | 2022-07-29 | 2022-07-29
200883C-700-DW-1532-5001 | [D] | 200883C | 700 | DW | 1532 | 5001 |  | 1 |  | Yuri Phase 0 - PPM Network Connection Diagram (DELETED 3-Aug-22) | Code: E0303 | INS | 700PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-07-17 | 2022-07-17 | 2022-07-29 | 2022-07-29
200883C-700-DW-1612-4000 | [D] | 200883C | 700 | DW | 1612 | 4000 |  | 21 |  | Yuri Phase 0 - Substation Building Earthing Layout | Code: E0303 | ELE | 700H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-23 | 2022-07-23 | 2022-07-25 | 2022-07-25
200883C-700-DW-1612-4000 | [D] | 200883C | 700 | DW | 1612 | 4000 |  | 21 |  | Yuri Phase 0 - Substation Building Earthing Layout | Code: E0303 | ELE | 700H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-07-30 | 2022-07-30 | 2022-07-26 | 2022-07-26
200883C-700-DW-1612-4000 | [D] | 200883C | 700 | DW | 1612 | 4000 |  | 21 |  | Yuri Phase 0 - Substation Building Earthing Layout | Code: E0303 | ELE | 700H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-700-DW-1622-4000 | [D] | 200883C | 700 | DW | 1622 | 4000 |  | 41 |  | Yuri Phase 0 - Substation Building Electrical - Instrument Cable Ladder Layouts | Code: E0303 | ELE | 700H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-13 | 2022-07-13 | 2022-07-18 | 2022-07-18
200883C-700-DW-1622-4000 | [D] | 200883C | 700 | DW | 1622 | 4000 |  | 41 |  | Yuri Phase 0 - Substation Building Electrical - Instrument Cable Ladder Layouts | Code: E0303 | ELE | 700H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-07-20 | 2022-07-20 | 2022-07-20
200883C-700-DW-1622-4000 | [D] | 200883C | 700 | DW | 1622 | 4000 |  | 41 |  | Yuri Phase 0 - Substation Building Electrical - Instrument Cable Ladder Layouts | Code: E0303 | ELE | 700H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-08-17 | 2022-08-17 | 2022-08-17
200883C-700-DW-1625-4000 | [D] | 200883C | 700 | DW | 1625 | 4000 |  | 122 |  | Yuri Phase 0 - Substation Building Equipment Layout | Code: E0303 | ELE | 700H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-08 | 2022-07-08 | 2022-07-08 | 2022-07-08
200883C-700-DW-1625-4000 | [D] | 200883C | 700 | DW | 1625 | 4000 |  | 122 |  | Yuri Phase 0 - Substation Building Equipment Layout | Code: E0303 | ELE | 700H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-07-15 | 2022-07-15 | 2022-07-20 | 2022-07-20
200883C-700-DW-1625-4000 | [D] | 200883C | 700 | DW | 1625 | 4000 |  | 122 |  | Yuri Phase 0 - Substation Building Equipment Layout | Code: E0303 | ELE | 700H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-08-12 | 2022-08-12 | 2022-08-12
200883C-700-JSS-1641-4000 | [D] | 200883C | 700 | JSS | 1641 | 4000 |  | 0 |  | Yuri Phase 0 - Specification for Zig Zag Earthing Transformer | Code: E0301 | ELE | 700H2 |  |  |  |  | STA | 10 |  |  | MELE |  | 2022-08-16 | 2022-08-15 | 2022-08-15
200883C-700-JSS-1641-4000 | [D] | 200883C | 700 | JSS | 1641 | 4000 |  | 0 |  | Yuri Phase 0 - Specification for Zig Zag Earthing Transformer | Code: E0301 | ELE | 700H2 |  |  |  |  | IFR | 70 |  |  | MELE |  | 2022-08-23 | 2022-08-15 | 2022-08-15
200883C-700-JSS-1641-4000 | [D] | 200883C | 700 | JSS | 1641 | 4000 |  | 0 |  | Yuri Phase 0 - Specification for Zig Zag Earthing Transformer | Code: E0301 | ELE | 700H2 |  |  |  |  | IFD | 100 |  |  | MELE |  | 2022-09-20 | 2022-08-15 | 2022-08-15
200883C-700-JSS-1680-1000 | [D] | 200883C | 700 | JSS | 1680 | 1000 |  | 40 |  | Yuri Phase 0 - Specification for Pre-Fabricated Substation Building | Code: E0304 | ELE | 700H2 |  |  |  |  | STA | 10 |  |  | AELE | 2022-04-26 | 2022-04-26 | 2022-04-26 | 2022-04-26
200883C-700-JSS-1680-1000 | [D] | 200883C | 700 | JSS | 1680 | 1000 |  | 40 |  | Yuri Phase 0 - Specification for Pre-Fabricated Substation Building | Code: E0304 | ELE | 700H2 |  |  |  |  | IFD | 70 |  |  | AELE | 2022-05-16 | 2022-05-16 | 2022-07-20 | 2022-07-20
200883C-700-JSS-1680-1000 | [D] | 200883C | 700 | JSS | 1680 | 1000 |  | 40 |  | Yuri Phase 0 - Specification for Pre-Fabricated Substation Building | Code: E0304 | ELE | 700H2 |  |  |  |  | IFC | 100 |  |  | AELE | 2022-08-31 | 2022-08-31 | 2022-08-31
200883C-700-MR-1680-1000 | [D] | 200883C | 700 | MR | 1680 | 1000 |  | 160 |  | Yuri Phase 0 - Pre-Fabricated Substation Building | Code: E0301 | ELE | 700H2 |  |  |  |  | STA | 10 |  |  | AELE | 2022-07-26 | 2022-07-26 | 2022-08-13 | 2022-08-13
200883C-700-MR-1680-1000 | [D] | 200883C | 700 | MR | 1680 | 1000 |  | 160 |  | Yuri Phase 0 - Pre-Fabricated Substation Building | Code: E0301 | ELE | 700H2 |  |  |  |  | IFR | 70 |  |  | AELE | 2022-07-26 | 2022-07-26 | 2022-08-15 | 2022-08-15
200883C-700-MR-1680-1000 | [D] | 200883C | 700 | MR | 1680 | 1000 |  | 160 |  | Yuri Phase 0 - Pre-Fabricated Substation Building | Code: E0301 | ELE | 700H2 |  |  |  |  | IFD | 100 |  |  | AELE | 2022-08-31 | 2022-08-31 | 2022-09-06
200883C-700-SP-1500-5000 | [D] | 200883C | 700 | SP | 1500 | 5000 |  | 1 |  | Yuri Phase 0 - PPM Technical Data Sheet (DELETED 3-Aug-22) | Code: E0303 | INS | 700PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-06-11 | 2022-06-11 | 2022-06-11 | 2022-06-11
200883C-700-SP-1500-5000 | [D] | 200883C | 700 | SP | 1500 | 5000 |  | 1 |  | Yuri Phase 0 - PPM Technical Data Sheet (DELETED 3-Aug-22) | Code: E0303 | INS | 700PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-07-11 | 2022-07-11 | 2022-07-29 | 2022-07-29
200883C-700-SP-1500-5000 | [D] | 200883C | 700 | SP | 1500 | 5000 |  | 1 |  | Yuri Phase 0 - PPM Technical Data Sheet (DELETED 3-Aug-22) | Code: E0303 | INS | 700PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-08-10 | 2022-08-10 | 2022-07-29 | 2022-07-29
200883C-700-SP-1641-4000 | [D] | 200883C | 700 | SP | 1641 | 4000 |  | 0 |  | Yuri Phase 0 - Datasheet for Zig Zag Transformers - H2 plant | Code: E0301 | ELE | 700H2 |  |  |  |  | STA | 10 |  |  | MELE |  | 2022-08-16 | 2022-08-15 | 2022-08-15
200883C-700-SP-1641-4000 | [D] | 200883C | 700 | SP | 1641 | 4000 |  | 0 |  | Yuri Phase 0 - Datasheet for Zig Zag Transformers - H2 plant | Code: E0301 | ELE | 700H2 |  |  |  |  | IFR | 70 |  |  | MELE |  | 2022-08-23 | 2022-08-19 | 2022-08-19
200883C-700-SP-1641-4000 | [D] | 200883C | 700 | SP | 1641 | 4000 |  | 0 |  | Yuri Phase 0 - Datasheet for Zig Zag Transformers - H2 plant | Code: E0301 | ELE | 700H2 |  |  |  |  | IFD | 100 |  |  | MELE |  | 2022-09-20 | 2022-09-20
200883C-700-SP-1673-4000 | [D] | 200883C | 700 | SP | 1673 | 4000 |  | 0 |  | Yuri Phase 0 - Data Sheet - VRLA Battery | Code: E0301 | ELE | 700H2 |  |  |  |  | STA | 10 |  |  | MELE |  | 2022-08-16 | 2022-08-15 | 2022-08-15
200883C-700-SP-1673-4000 | [D] | 200883C | 700 | SP | 1673 | 4000 |  | 0 |  | Yuri Phase 0 - Data Sheet - VRLA Battery | Code: E0301 | ELE | 700H2 |  |  |  |  | IFR | 70 |  |  | MELE |  | 2022-08-23 | 2022-08-15 | 2022-08-15
200883C-700-SP-1673-4000 | [D] | 200883C | 700 | SP | 1673 | 4000 |  | 0 |  | Yuri Phase 0 - Data Sheet - VRLA Battery | Code: E0301 | ELE | 700H2 |  |  |  |  | IFD | 100 |  |  | MELE |  | 2022-09-20 | 2022-08-15 | 2022-08-15
200883C-700-TBT-1620-1000 | [D] | 200883C | 700 | TBT | 1620 | 1000 |  | 40 |  | Yuri Phase 0 - Technical Bid Tabulation - Pre-Fabricated Substation Building | Code: E0303 | ELE | 700H2 |  |  |  |  | STA | 10 |  |  | AELE | 2022-06-30 | 2022-06-30 | 2022-09-16
200883C-700-TBT-1620-1000 | [D] | 200883C | 700 | TBT | 1620 | 1000 |  | 40 |  | Yuri Phase 0 - Technical Bid Tabulation - Pre-Fabricated Substation Building | Code: E0303 | ELE | 700H2 |  |  |  |  | IFR | 70 |  |  | AELE | 2022-06-30 | 2022-06-30 | 2022-09-30
200883C-700-TBT-1620-1000 | [D] | 200883C | 700 | TBT | 1620 | 1000 |  | 40 |  | Yuri Phase 0 - Technical Bid Tabulation - Pre-Fabricated Substation Building | Code: E0303 | ELE | 700H2 |  |  |  |  | IFC | 100 |  |  | AELE | 2022-07-20 | 2022-07-20 | 2022-10-07

## AOC
Overdue
DELIVERABLE REFERENCE | CAT | DLV REF. P1: CONTRACT CODE | DLV REF. P2: UNIT CODE | DLV REF. P3: DOC/DLV TYPE | DLV REF. P4: ENGINEERING CODE | DLV REF. P5: SERIAL NUMBER | CLIENT REFERENCE | WEIGHT | MANUFACTURING WEIGHT | TITLE | MILESTONE CHAIN | DBS | WBS | FREE CRITERIA 1 | FREE CRITERIA 2 | FREE CRITERIA 3 | FREE CRITERIA 4 | MSCODE | CUMULATIVE | MANUFACTURING CUMULATIVE | PBS | OBS | INITIAL PLAN DATE | REVISED PLAN DATE | FORECAST DATE | Reason for delay
200883C-000-CN-1901-1000 | [D] | 200883C | 0 | CN | 1901 | 1000 |  | 20 |  | Yuri Phase 0 - Safety and Risk Calculations | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-08-01 | 2022-08-01 | 2022-08-22
200883C-000-JSD-6300-1000 | [D] | 200883C | 0 | JSD | 6300 | 1000 |  | 80 |  | Yuri Phase 0 - General Specification for General Equipment and Piping Welding - Fabrication and Inspection | Code: E0303 | MEC | 000H2 |  |  |  |  | STA | 10 |  |  | AMEC | 2022-07-08 | 2022-07-08 | 2022-07-08
200883C-000-RT-1900-1000 | [D] | 200883C | 0 | RT | 1900 | 1000 |  | 42 |  | Yuri Phase 0 - Hazardous Area Classification Report | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-06-28 | 2022-06-28 | 2022-08-22
200883C-000-RT-1900-1002 | [D] | 200883C | 0 | RT | 1900 | 1002 |  | 60 |  | Yuri Phase 0 - HAZOP Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-08-17 | 2022-08-17 | 2022-08-17
200883C-000-RT-1900-1003 | [D] | 200883C | 0 | RT | 1900 | 1003 |  | 40 |  | Yuri Phase 0 - HSE Risk Register | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-08-16 | 2022-08-16 | 2022-08-16
200883C-000-RT-1900-1004 | [D] | 200883C | 0 | RT | 1900 | 1004 |  | 40 |  | Yuri Phase 0 - HAZID Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-000-RT-1900-1004 | [D] | 200883C | 0 | RT | 1900 | 1004 |  | 40 |  | Yuri Phase 0 - HAZID Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-08-24 | 2022-08-24 | 2022-08-24
200883C-000-RT-1900-1006 | [D] | 200883C | 0 | RT | 1900 | 1006 |  | 30 |  | Yuri Phase 0 - Human Factors Review Report | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-000-RT-1900-1009 | [D] | 200883C | 0 | RT | 1900 | 1009 |  | 40 |  | Yuri Phase 0 - Terms of Reference - HAZID Study | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-08-31 | 2022-08-31 | 2022-07-18
200883C-500-JSS-1700-1000 | [D] | 200883C | 500 | JSS | 1700 | 1000 |  | 103 |  | Yuri Phase 0 - Specification for Vented Enclosure | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | ASTR | 2022-07-19 | 2022-07-19 | 2022-08-22
3WLAH
DELIVERABLE REFERENCE | CAT | DLV REF. P1: CONTRACT CODE | DLV REF. P2: UNIT CODE | DLV REF. P3: DOC/DLV TYPE | DLV REF. P4: ENGINEERING CODE | DLV REF. P5: SERIAL NUMBER | CLIENT REFERENCE | WEIGHT | MANUFACTURING WEIGHT | TITLE | MILESTONE CHAIN | DBS | WBS | FREE CRITERIA 1 | FREE CRITERIA 2 | FREE CRITERIA 3 | FREE CRITERIA 4 | MSCODE | CUMULATIVE | MANUFACTURING CUMULATIVE | PBS | OBS | INITIAL PLAN DATE | REVISED PLAN DATE | FORECAST DATE
200883C-000-CN-1901-1000 | [D] | 200883C | 0 | CN | 1901 | 1000 |  | 20 |  | Yuri Phase 0 - Safety and Risk Calculations | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-08-19 | 2022-08-19 | 2022-09-09
200883C-000-JSD-1900-1000 | [D] | 200883C | 0 | JSD | 1900 | 1000 |  | 20 |  | Yuri Phase 0 - Safety Philosophy | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-08-15 | 2022-08-15 | 2022-08-29
200883C-000-JSD-6300-1000 | [D] | 200883C | 0 | JSD | 6300 | 1000 |  | 80 |  | Yuri Phase 0 - General Specification for General Equipment and Piping Welding - Fabrication and Inspection | Code: E0303 | MEC | 000H2 |  |  |  |  | IFR | 70 |  |  | AMEC | 2022-08-31 | 2022-08-31 | 2022-08-31
200883C-000-NM-1900-1001 | [D] | 200883C | 0 | NM | 1900 | 1001 |  | 30 |  | Yuri Phase 0 - Safety Critical Element Register | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-08-23 | 2022-08-23 | 2022-08-29
200883C-000-NM-1900-1001 | [D] | 200883C | 0 | NM | 1900 | 1001 |  | 30 |  | Yuri Phase 0 - Safety Critical Element Register | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-09-12 | 2022-09-12 | 2022-09-16
200883C-000-RT-1900-1000 | [D] | 200883C | 0 | RT | 1900 | 1000 |  | 42 |  | Yuri Phase 0 - Hazardous Area Classification Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-07-18 | 2022-07-18 | 2022-08-29
200883C-000-RT-1900-1001 | [D] | 200883C | 0 | RT | 1900 | 1001 |  | 60 |  | Yuri Phase 0 - LOPA Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | STA | 10 |  |  | ASAF | 2022-06-28 | 2022-06-28 | 2022-09-12
200883C-000-RT-1900-1001 | [D] | 200883C | 0 | RT | 1900 | 1001 |  | 60 |  | Yuri Phase 0 - LOPA Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-07-18 | 2022-07-18 | 2022-09-13
200883C-000-RT-1900-1002 | [D] | 200883C | 0 | RT | 1900 | 1002 |  | 60 |  | Yuri Phase 0 - HAZOP Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-08-30 | 2022-08-30 | 2022-08-30
200883C-000-RT-1900-1003 | [D] | 200883C | 0 | RT | 1900 | 1003 |  | 40 |  | Yuri Phase 0 - HSE Risk Register | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-09-05 | 2022-09-05 | 2022-09-05
200883C-000-RT-1900-1004 | [D] | 200883C | 0 | RT | 1900 | 1004 |  | 40 |  | Yuri Phase 0 - HAZID Workshop Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-10-12 | 2022-10-12 | 2022-09-09
200883C-000-RT-1900-1006 | [D] | 200883C | 0 | RT | 1900 | 1006 |  | 30 |  | Yuri Phase 0 - Human Factors Review Report | Code: E0303 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | ASAF | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-000-RT-1900-1011 | [D] | 200883C | 0 | RT | 1900 | 1011 |  | 40 |  | Yuri Phase 0 - Terms of Reference - LOPA Study | Code: E0303 | SAF | 000H2 |  |  |  |  | IFC | 100 |  |  | ASAF | 2022-10-31 | 2022-10-31 | 2022-09-02
200883C-500-JSS-1700-1000 | [D] | 200883C | 500 | JSS | 1700 | 1000 |  | 103 |  | Yuri Phase 0 - Specification for Vented Enclosure | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | ASTR | 2022-08-08 | 2022-08-08 | 2022-09-09

## MOC
Overdue
DELIVERABLE REFERENCE | CAT | DLV REF. P1: CONTRACT CODE | DLV REF. P2: UNIT CODE | DLV REF. P3: DOC/DLV TYPE | DLV REF. P4: ENGINEERING CODE | DLV REF. P5: SERIAL NUMBER | CLIENT REFERENCE | WEIGHT | MANUFACTURING WEIGHT | TITLE | MILESTONE CHAIN | DBS | WBS | FREE CRITERIA 1 | FREE CRITERIA 2 | FREE CRITERIA 3 | FREE CRITERIA 4 | MSCODE | CUMULATIVE | MANUFACTURING CUMULATIVE | PBS | OBS | INITIAL PLAN DATE | REVISED PLAN DATE | FORECAST DATE | Reason for delay
200883C-000-DW-1920-4000 | [D] | 200883C | 0 | DW | 1920 | 4000 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 1 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-08-08 | 2022-08-08 | 2022-08-08 | Post HAC schedule from AOC
200883C-000-DW-1920-4001 | [D] | 200883C | 0 | DW | 1920 | 4001 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 2 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-08-08 | 2022-08-08 | 2022-08-08 | Post HAC schedule from AOC
200883C-000-DW-1920-4002 | [D] | 200883C | 0 | DW | 1920 | 4002 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 3 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-08-08 | 2022-08-08 | 2022-08-08 | Post HAC schedule from AOC
200883C-000-DW-1920-4003 | [D] | 200883C | 0 | DW | 1920 | 4003 |  | 36 |  | Yuri Phase 0 - Hazardous Area Classification Drawing - Sheet 4 | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-08-08 | 2022-08-08 | 2022-08-08 | Post HAC schedule from AOC
200883C-000-JSD-1300-4006 | [D] | 200883C | 0 | JSD | 1300 | 4006 |  | 12 |  | Yuri Phase 0-Insulation Specification | Code: E0301 | PIP | 000H2 |  |  |  |  | IFR | 70 |  |  | MPIP | 2022-08-26 | 2022-08-26 | 2022-08-26
200883C-000-JSS-1620-4000 | [D] | 200883C | 0 | JSS | 1620 | 4000 |  | 21 |  | Yuri Phase 0 - General Electrical Installation Requirements | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-08 | 2022-07-08 | 2022-08-22
200883C-000-JSS-1900-4000 | [D] | 200883C | 0 | JSS | 1900 | 4000 |  | 44 |  | Yuri Phase 0 - Fire and Gas Detection Specification | Code: E0301 | SAF | 000H2 |  |  |  |  | IFR | 70 |  |  | MSAF | 2022-07-15 | 2022-07-15 | 2022-07-20 | To be issued
200883C-000-JSS-1900-4000 | [D] | 200883C | 0 | JSS | 1900 | 4000 |  | 44 |  | Yuri Phase 0 - Fire and Gas Detection Specification | Code: E0301 | SAF | 000H2 |  |  |  |  | IFD | 100 |  |  | MSAF | 2022-08-12 | 2022-08-12 | 2022-08-12 | To be issued post IFR comments
200883C-000-JSS-1940-4000 | [D] | 200883C | 0 | JSS | 1940 | 4000 |  | 65 |  | Yuri Phase 0 - Safety Equipment Specification | Code: E0301 | SAF | 000H2 |  |  |  |  | IFD | 100 |  |  | MSAF | 2022-07-28 | 2022-07-28 | 2022-07-28 | Reissued for Reviwe on 27-8-22
200883C-000-MR-1545-4000 | [D] | 200883C | 0 | MR | 1545 | 4000 |  | 48 |  | Yuri Phase 0 - Material Requisition and Datasheet For Safety Relief Valves | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-08-12 | 2022-08-12 | 2022-08-12
200883C-000-MR-1547-4000 | [D] | 200883C | 0 | MR | 1547 | 4000 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Magnetic Flow Meter | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-000-MR-1552-4001 | [D] | 200883C | 0 | MR | 1552 | 4001 |  | 38 |  | Yuri Phase 0 - Material Requisition and Datasheet For Radar Level transmitter | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-06-27 | 2022-06-27 | 2022-06-27
200883C-000-MR-1566-4000 | [D] | 200883C | 0 | MR | 1566 | 4000 |  | 70 |  | Yuri Phase 0 - Material Requisition and Datasheet For FandG Detectors | Code: E0610 | INS | 000H2 |  |  |  |  | IFQ | 40 |  |  | MINS | 2022-08-22 | 2022-08-22 | 2022-08-22
200883C-000-MR-1652-4000 | [D] | 200883C | 0 | MR | 1652 | 4000 |  | 81 |  | Yuri Phase 0 - HV Switchgear | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-000-MR-1654-4000 | [D] | 200883C | 0 | MR | 1654 | 4000 |  | 81 |  | Yuri Phase 0 - Material Requisition for LV Switchgear | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-08-23 | 2022-08-23 | 2022-08-23
200883C-000-NM-1551-4000 | [D] | 200883C | 0 | NM | 1551 | 4000 |  | 63 |  | Yuri Phase 0 - Instrument and FandG Index | Code: E0311 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-000-NM-1551-4000 | [D] | 200883C | 0 | NM | 1551 | 4000 |  | 63 |  | Yuri Phase 0 - Instrument and FandG Index | Code: E0311 | INS | 000H2 |  |  |  |  | IFU | 100 |  |  | MINS | 2022-08-26 | 2022-08-26 | 2022-08-26
200883C-000-NM-1654-4000 | [D] | 200883C | 0 | NM | 1654 | 4000 |  | 81 |  | Yuri Phase 0 - LV Switchgear Schedule | Code: E0303 | ELE | 000H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-07-13 | 2022-07-13 | 2022-07-13
200883C-000-NM-1950-4000 | [D] | 200883C | 0 | NM | 1950 | 4000 |  | 29 |  | Yuri Phase 0 - Fire & Gas Cause & Effect Chart | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-000-TAS-0000-1005 | [T] | 200883C | 0 | TAS | 0 | 1005 |  | 957 |  | Yuri Phase 0-SB lines Modeling | Code: T0100 | PIP | 000H2 |  |  |  |  | M3 | 30 |  |  | MPIP | 2022-08-21 | 2022-08-21 | 2022-08-21
200883C-000-TBT-1543-4000 | [D] | 200883C | 0 | TBT | 1543 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For On - Off Valves | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-12 | 2022-08-12 | 2022-08-12
200883C-000-TBT-1552-4000 | [D] | 200883C | 0 | TBT | 1552 | 4000 |  | 26 |  | Yuri Phase 0 - Technical Bid Tabulation For Magnetic Level Gauge | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-12 | 2022-08-12 | 2022-08-12
200883C-000-TBT-1552-4001 | [D] | 200883C | 0 | TBT | 1552 | 4001 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Radar Level transmitter | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-28 | 2022-07-28 | 2022-07-28
200883C-000-TBT-1552-4001 | [D] | 200883C | 0 | TBT | 1552 | 4001 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Radar Level transmitter | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-08-25 | 2022-08-25 | 2022-08-25
200883C-000-TBT-1553-4000 | [D] | 200883C | 0 | TBT | 1553 | 4000 |  | 57 |  | Yuri Phase 0 - Technical Bid Tabulation For Electronic Transmitters (Pressure , Flow, level , temperature) | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-12 | 2022-08-12 | 2022-08-12
200883C-000-TBT-1554-4000 | [D] | 200883C | 0 | TBT | 1554 | 4000 |  | 38 |  | Yuri Phase 0 - Technical Bid Tabulation For Temperature Elements and Gauges | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-13 | 2022-08-13 | 2022-08-13
200883C-000-TBT-1584-4000 | [D] | 200883C | 0 | TBT | 1584 | 4000 |  | 89 |  | Yuri Phase 0 - Technical Bid Tabulation For Hydrogen Quality and Metering System | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-07-18 | 2022-07-18 | 2022-07-18
200883C-000-TBT-1584-4000 | [D] | 200883C | 0 | TBT | 1584 | 4000 |  | 89 |  | Yuri Phase 0 - Technical Bid Tabulation For Hydrogen Quality and Metering System | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-08-15 | 2022-08-15 | 2022-08-15
200883C-000-TBT-1652-4000 | [D] | 200883C | 0 | TBT | 1652 | 4000 |  | 41 |  | Yuri Phase 0 - HV Switchgear | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-08-03 | 2022-08-03 | 2022-08-03
200883C-000-TBT-1671-4000 | [D] | 200883C | 0 | TBT | 1671 | 4000 |  | 41 |  | Yuri Phase 0 - AC UPS System | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-21 | 2022-07-21 | 2022-07-21
200883C-000-TBT-1671-4000 | [D] | 200883C | 0 | TBT | 1671 | 4000 |  | 41 |  | Yuri Phase 0 - AC UPS System | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-08-18 | 2022-08-18 | 2022-08-18
200883C-000-TBT-1672-4000 | [D] | 200883C | 0 | TBT | 1672 | 4000 |  | 41 |  | Yuri Phase 0 - DC UPS System | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-07-21 | 2022-07-21 | 2022-07-21
200883C-000-TBT-1672-4000 | [D] | 200883C | 0 | TBT | 1672 | 4000 |  | 41 |  | Yuri Phase 0 - DC UPS System | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-08-18 | 2022-08-18 | 2022-08-18
200883C-500-CN-0008-4002 | [D] | 200883C | 500 | CN | 8 | 4002 |  | 94 |  | Yuri Phase 0 - Process calculations- Critical | Code: E0201 | PRO | 500H2 |  |  |  |  | IFI | 100 |  |  | MPRO | 2022-06-17 | 2022-06-17 | 2022-06-17
200883C-500-DW-1425-2003 | [D] | 200883C | 500 | DW | 1425 | 2003 |  | 25 |  | Yuri Phase 0 - Roadside drainage structure details (2) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-07-27 | 2022-07-27 | 2022-07-27 | Pending MFG's details for consistency purpose
200883C-500-DW-1425-2004 | [D] | 200883C | 500 | DW | 1425 | 2004 |  | 25 |  | Yuri Phase 0 - Roadside drainage structure details (3) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-07-27 | 2022-07-27 | 2022-07-27 | Resever, may not require
200883C-500-DW-1624-4001 | [D] | 200883C | 500 | DW | 1624 | 4001 |  | 21 |  | Yuri Phase 0 - Cable Rack Layout Drawing - Key Plan | Code: E0303 | ELE | 500H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-08-15 | 2022-08-15 | 2022-08-15
200883C-500-DW-1821-4016 | [D] | 200883C | 500 | DW | 1821 | 4016 |  | 0 |  | Piperack Module - PR4- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-08-23 | 2022-08-23 | Piperack PR4 module, is under hold due to non availability of PERIC skids data. Drawings are issued for IDC
200883C-500-DW-1821-4017 | [D] | 200883C | 500 | DW | 1821 | 4017 |  | 0 |  | Piperack Module - PR4- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-08-23 | 2022-08-23 | Piperack PR4 module, is under hold due to non availability of PERIC skids data. Drawings are issued for IDC
200883C-500-DW-1821-4018 | [D] | 200883C | 500 | DW | 1821 | 4018 |  | 0 |  | Piperack Module - PR4- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-08-23 | 2022-08-23 | Piperack PR4 module, is under hold due to non availability of PERIC skids data.
200883C-500-DW-1821-4019 | [D] | 200883C | 500 | DW | 1821 | 4019 |  | 0 |  | Piperack Module - PR4- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-08-23 | 2022-08-23 | Piperack PR4 module, is under hold due to non availability of PERIC skids data.
200883C-500-DW-1821-4020 | [D] | 200883C | 500 | DW | 1821 | 4020 |  | 0 |  | Piperack Module - PR4- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-08-23 | 2022-08-23 | Piperack PR4 module, is under hold due to non availability of PERIC skids data.
200883C-500-DW-2025-2000 | [D] | 200883C | 500 | DW | 2025 | 2000 |  | 0 |  | Yuri Phase 0 - H2 Ventilated Enclosure Architectural Conceptual Plans and Elevations | Code: E0302 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV |  | 2022-08-19 | 2022-08-19 | Will IDC by 31-Aug.
200883C-500-JSC-1450-2000 | [D] | 200883C | 500 | JSC | 1450 | 2000 |  | 75 |  | Yuri Phase 0 - Specification for Plant Roads and Pavements - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-07-01 | 2022-07-01 | 2022-07-01 | Target to issue 31-Aug
200883C-500-JSD-1400-2000 | [D] | 200883C | 500 | JSD | 1400 | 2000 |  | 99 |  | Yuri Phase 0 - Basis Of Design For Civil Works - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFD | 100 |  |  | BCIV | 2022-06-28 | 2022-06-28 | 2022-06-28 | Pending Company's comments on Drainage Philosophy (sent to review since 17-AUG)
200883C-500-MR-1900-4000 | [D] | 200883C | 500 | MR | 1900 | 4000 |  | 45 |  | MR for Safety Equipment | Code: E0610 | MEC | 500H2 |  |  |  |  | IFQ | 40 |  |  | MMEC | 2022-07-07 | 2022-07-07 | 2022-07-07
200883C-500-PDS-1545-4000 | [D] | 200883C | 500 | PDS | 1545 | 4000 |  | 24 |  | Yuri Phase 0 - Safety relief valve Process datasheet | Code: E0301 | PRO | 500H2 |  |  |  |  | IFR | 70 |  |  | MPRO | 2022-06-03 | 2022-06-03 | 2022-06-03
200883C-500-PDS-1545-4000 | [D] | 200883C | 500 | PDS | 1545 | 4000 |  | 24 |  | Yuri Phase 0 - Safety relief valve Process datasheet | Code: E0301 | PRO | 500H2 |  |  |  |  | IFD | 100 |  |  | MPRO | 2022-07-29 | 2022-07-29 | 2022-07-29
200883C-500-RT-0800-4000 | [D] | 200883C | 500 | RT | 800 | 4000 |  | 113 |  | Presure Vessel Registration | Code: E0201 | MEC | 500H2 |  |  |  |  | IFI | 100 |  |  | MMEC | 2022-06-25 | 2022-06-25 | 2022-06-25
200883C-500-RT-1800-4010 | [D] | 200883C | 500 | RT | 1800 | 4010 |  | 0 |  | Structural Steel Design Report-Module PR4- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-08-23 | 2022-08-23 | Piperack PR4 module, is under hold due to non availability of PERIC skids data.
200883C-500-RT-1800-4011 | [D] | 200883C | 500 | RT | 1800 | 4011 |  | 0 |  | Structural Steel Design Report-Module PR4- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-08-23 | 2022-08-23 | Piperack PR4 module, is under hold due to non availability of PERIC skids data.
200883C-500-TBT-0811-4000 | [D] | 200883C | 500 | TBT | 811 | 4000 |  | 46 |  | TBT for Vessels (Instrument Air storage vessel) | Code: E0204 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-07-30 | 2022-07-30 | 2022-07-30
200883C-500-TBT-0910-4000 | [D] | 200883C | 500 | TBT | 910 | 4000 |  | 90 |  | TBT for Centrifugal Pumps (Cooling Water, Chilled Water Circulation, Potable Water) | Code: E0204 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-08-04 | 2022-08-04 | 2022-08-04
200883C-500-TBT-1900-4000 | [D] | 200883C | 500 | TBT | 1900 | 4000 |  | 45 |  | TBT for Safety Equipment | Code: E0204 | MEC | 500H2 |  |  |  |  | STA | 10 |  |  | MMEC | 2022-08-07 | 2022-08-07 | 2022-08-07
200883C-600-DW-1741-2003 | [D] | 200883C | 600 | DW | 1741 | 2003 |  | 31 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (4) | Code: E0303 | CIV | 600H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-08-04 | 2022-08-04 | 2022-08-04 | To be cancelled
200883C-600-DW-1741-2003 | [D] | 200883C | 600 | DW | 1741 | 2003 |  | 31 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (4) | Code: E0303 | CIV | 600H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-08-22 | 2022-08-22 | 2022-08-22 | To be cancelled
200883C-600-DW-1825-4000 | [D] | 200883C | 600 | DW | 1825 | 4000 |  | 31 |  | Yuri Phase 0 - Miscellaneous Pipe Support Details for H2 Line | Code: E0303 | STR | 600H2 |  |  |  |  | IFC | 100 |  |  | MSTR | 2022-07-29 | 2022-07-29 | 2022-07-29 | Under hold for Pipe route confirmation from AOC/MFG
200883C-600-MTO-1311-4000 | [D] | 200883C | 600 | MTO | 1311 | 4000 |  | 45 |  | Yuri Phase 0-Piping Bulk MTO-1 | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-07-29 | 2022-07-29 | 2022-08-19
200883C-600-NM-1350-4000 | [D] | 200883C | 600 | NM | 1350 | 4000 |  | 45 |  | Yuri Phase 0-Isometric drawings- YPF Tie-In | Code: E0203 | PIP | 600H2 |  |  |  |  | IFC | 100 |  |  | MPIP | 2023-03-31 | 2023-03-31 | 2022-08-15
200883C-600-TBT-1340-4001 | [D] | 200883C | 600 | TBT | 1340 | 4001 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Wrought Fittings | Code: E0204 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-30 | 2022-07-30 | 2022-07-30
200883C-600-TBT-1383-4000 | [D] | 200883C | 600 | TBT | 1383 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Supports | Code: E0204 | PIP | 600H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-07-30 | 2022-07-30 | 2022-07-30
200883C-600-TBT-1574-4000 | [D] | 200883C | 600 | TBT | 1574 | 4000 |  | 16 |  | Yuri Phase 0 - Technical Bid Tabulation For Instrument Cables-Brown Field | Code: E0204 | INS | 600H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-18 | 2022-08-18 | 2022-08-18
200883C-600-TBT-1621-4001 | [D] | 200883C | 600 | TBT | 1621 | 4001 |  | 21 |  | Yuri Phase 0 - HV and LV Power And Control Cables - Brownfield | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-08-20 | 2022-08-20 | 2022-08-20
200883C-600-TBT-1623-4001 | [D] | 200883C | 600 | TBT | 1623 | 4001 |  | 21 |  | Yuri Phase 0 - Cable Trays And Ladders - Brownfield | Code: E0204 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-08-20 | 2022-08-20 | 2022-08-20
200883C-700-DW-1622-4000 | [D] | 200883C | 700 | DW | 1622 | 4000 |  | 41 |  | Yuri Phase 0 - Substation Building Electrical - Instrument Cable Ladder Layouts | Code: E0303 | ELE | 700H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-07-20 | 2022-07-20 | 2022-07-20
200883C-700-DW-1622-4000 | [D] | 200883C | 700 | DW | 1622 | 4000 |  | 41 |  | Yuri Phase 0 - Substation Building Electrical - Instrument Cable Ladder Layouts | Code: E0303 | ELE | 700H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-08-17 | 2022-08-17 | 2022-08-17
200883C-700-DW-1625-4000 | [D] | 200883C | 700 | DW | 1625 | 4000 |  | 122 |  | Yuri Phase 0 - Substation Building Equipment Layout | Code: E0303 | ELE | 700H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-08-12 | 2022-08-12 | 2022-08-12
3WLAH
DELIVERABLE REFERENCE | CAT | DLV REF. P1: CONTRACT CODE | DLV REF. P2: UNIT CODE | DLV REF. P3: DOC/DLV TYPE | DLV REF. P4: ENGINEERING CODE | DLV REF. P5: SERIAL NUMBER | CLIENT REFERENCE | WEIGHT | MANUFACTURING WEIGHT | TITLE | MILESTONE CHAIN | DBS | WBS | FREE CRITERIA 1 | FREE CRITERIA 2 | FREE CRITERIA 3 | FREE CRITERIA 4 | MSCODE | CUMULATIVE | MANUFACTURING CUMULATIVE | PBS | OBS | INITIAL PLAN DATE | REVISED PLAN DATE | FORECAST DATE | Column1
200883C-000-DW-1552-4000 | [D] | 200883C | 0 | DW | 1552 | 4000 |  | 41 |  | Yuri Phase 0 - Instrument Level Sketches | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-000-DW-1576-4000 | [D] | 200883C | 0 | DW | 1576 | 4000 |  | 95 |  | Yuri Phase 0 - Pneumatic and Process Hook-Up Drawings | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-000-DW-1576-4001 | [D] | 200883C | 0 | DW | 1576 | 4001 |  | 48 |  | Yuri Phase 0 - Instrument Supports Mounting Details | Code: E0303 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-09-07 | 2022-09-07 | 2022-09-07
200883C-000-DW-1576-4001 | [D] | 200883C | 0 | DW | 1576 | 4001 |  | 48 |  | Yuri Phase 0 - Instrument Supports Mounting Details | Code: E0303 | INS | 000H2 |  |  |  |  | IFR | 70 |  |  | MINS | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-000-MR-1310-4000 | [D] | 200883C | 0 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Gate Globe Check Needle Valve | Code: E0610 | PIP | 000H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-06 | 2022-09-06 | 2022-09-06
200883C-000-MR-1310-4000 | [D] | 200883C | 0 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Gate Globe Check Needle Valve | Code: E0610 | PIP | 000H2 |  |  |  |  | IFQ | 40 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-000-MR-1574-4000 | [D] | 200883C | 0 | MR | 1574 | 4000 |  | 32 |  | Yuri Phase 0 - Material Requisition and Datasheet For Instrument Cables | Code: E0610 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-000-MR-1584-4000 | [D] | 200883C | 0 | MR | 1584 | 4000 |  | 133 |  | Yuri Phase 0 - Material Requisition and Datasheet For Hydrogen Quality and Metering System | Code: E0610 | INS | 000H2 |  |  |  |  | IFP | 70 |  |  | MINS | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-000-MR-1610-4000 | [D] | 200883C | 0 | MR | 1610 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Earthing | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-000-MR-1620-4000 | [D] | 200883C | 0 | MR | 1620 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Power | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-000-MR-1630-4000 | [D] | 200883C | 0 | MR | 1630 | 4000 |  | 41 |  | Yuri Phase 0 - Electrical Bulk Materials - Lighting | Code: E0610 | ELE | 000H2 |  |  |  |  | IFQ | 40 |  |  | MELE | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-000-MR-1641-4000 | [D] | 200883C | 0 | MR | 1641 | 4000 |  | 81 |  | Yuri Phase 0 - Transformers | Code: E0610 | ELE | 000H2 |  |  |  |  | IFP | 70 |  |  | MELE | 2022-09-16 | 2022-09-16 | 2022-09-16
200883C-000-MTO-1619-4000 | [D] | 200883C | 0 | MTO | 1619 | 4000 |  | 41 |  | Yuri Phase 0 - Earthing Material Take-Off | Code: E0306 | ELE | 000H2 |  |  |  |  | IFP1 | 70 |  |  | MELE | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-000-NM-1511-4000 | [D] | 200883C | 0 | NM | 1511 | 4000 |  | 32 |  | Yuri Phase 0 - ICS Hardwired I - O List | Code: E0311 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-000-NM-1511-4002 | [D] | 200883C | 0 | NM | 1511 | 4002 |  | 32 |  | Yuri Phase 0 - FandG Hardwired I - O List | Code: E0311 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-000-NM-1630-4000 | [D] | 200883C | 0 | NM | 1630 | 4000 |  | 81 |  | Yuri Phase 0 - Distribution Board Schedule | Code: E0303 | ELE | 000H2 |  |  |  |  | STA | 10 |  |  | MELE | 2022-09-08 | 2022-09-08 | 2022-09-08
200883C-000-NM-1630-4000 | [D] | 200883C | 0 | NM | 1630 | 4000 |  | 81 |  | Yuri Phase 0 - Distribution Board Schedule | Code: E0303 | ELE | 000H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-09-15 | 2022-09-15 | 2022-09-15
200883C-000-RT-1900-4000 | [D] | 200883C | 0 | RT | 1900 | 4000 |  | 44 |  | Yuri Phase 0 - Fire Water System Hydraulic Report | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-08-29 | 2022-08-29 | 2022-08-29 | To be issued
200883C-000-SOW-1600-4000 | [D] | 200883C | 0 | SOW | 1600 | 4000 |  | 41 |  | Yuri Phase 0 - Scope of Work for Site Electrical Installation | Code: E0301 | ELE | 000H2 |  |  |  |  | IFD | 100 |  |  | MELE | 2022-07-13 | 2022-07-13 | 2022-08-31
200883C-000-SP-1940-4000 | [D] | 200883C | 0 | SP | 1940 | 4000 |  | 36 |  | Yuri Phase 0 - Data Sheets For Safety Equipment | Code: E0401 | SAF | 000H2 |  |  |  |  | IFR | 50 |  |  | MSAF | 2022-09-02 | 2022-09-02 | 2022-09-02
200883C-000-STC-1490-2000 | [D] | 200883C | 0 | STC | 1490 | 2000 |  | 25 |  | Yuri Phase 0 - Civil Works Standard Drawings | Code: E0303 | CIV | 000H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-07-22 | 2022-07-22 | 2022-08-29
200883C-000-TAS-0000-1008 | [T] | 200883C | 0 | TAS | 0 | 1008 |  | 183 |  | 3D Modelling | Code: T0100 | ELE | 000H2 |  |  |  |  | M3 | 30 |  |  | MELE | 2022-09-07 | 2022-09-07 | 2022-09-07
200883C-000-TAS-0000-1009 | [T] | 200883C | 0 | TAS | 0 | 1009 |  | 142 |  | Mechanical Package Review | Code: T0100 | ELE | 000H2 |  |  |  |  | M3 | 30 |  |  | MELE | 2022-09-07 | 2022-09-07 | 2022-09-07
200883C-000-TBT-1533-4000 | [D] | 200883C | 0 | TBT | 1533 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Pressure Gauges | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-09 | 2022-09-09 | 2022-09-09
200883C-000-TBT-1541-4000 | [D] | 200883C | 0 | TBT | 1541 | 4000 |  | 38 |  | Yuri Phase 0 - Technical Bid Tabulation For Control Valves | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-09-05 | 2022-09-05 | 2022-09-05
200883C-000-TBT-1543-4000 | [D] | 200883C | 0 | TBT | 1543 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For On - Off Valves | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-09 | 2022-09-09 | 2022-09-09
200883C-000-TBT-1545-4000 | [D] | 200883C | 0 | TBT | 1545 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Safety Relief Valves | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-000-TBT-1546-4000 | [D] | 200883C | 0 | TBT | 1546 | 4000 |  | 32 |  | Yuri Phase 0 - Technical Bid Tabulation For Flow Element | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-000-TBT-1547-4000 | [D] | 200883C | 0 | TBT | 1547 | 4000 |  | 19 |  | Yuri Phase 0 - Technical Bid Tabulation For Magnetic Flow Meter | Code: E0204 | INS | 000H2 |  |  |  |  | STA | 10 |  |  | MINS | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-000-TBT-1552-4000 | [D] | 200883C | 0 | TBT | 1552 | 4000 |  | 26 |  | Yuri Phase 0 - Technical Bid Tabulation For Magnetic Level Gauge | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-09 | 2022-09-09 | 2022-09-09
200883C-000-TBT-1553-4000 | [D] | 200883C | 0 | TBT | 1553 | 4000 |  | 57 |  | Yuri Phase 0 - Technical Bid Tabulation For Electronic Transmitters (Pressure , Flow, level , temperature) | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-09 | 2022-09-09 | 2022-09-09
200883C-000-TBT-1554-4000 | [D] | 200883C | 0 | TBT | 1554 | 4000 |  | 38 |  | Yuri Phase 0 - Technical Bid Tabulation For Temperature Elements and Gauges | Code: E0204 | INS | 000H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-10 | 2022-09-10 | 2022-09-10
200883C-000-TBT-1641-4000 | [D] | 200883C | 0 | TBT | 1641 | 4000 |  | 41 |  | Yuri Phase 0 - Transformers | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-08-09 | 2022-08-09 | 2022-09-09
200883C-000-TBT-1654-4000 | [D] | 200883C | 0 | TBT | 1654 | 4000 |  | 41 |  | Yuri Phase 0 - LV Switchgear | Code: E0204 | ELE | 000H2 |  |  |  |  | IFP | 100 |  |  | MELE | 2022-08-09 | 2022-08-09 | 2022-09-09
200883C-500-CN-1733-2000 | [D] | 200883C | 500 | CN | 1733 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Vendor Assembled Skids and Equipment Foundations - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-09-02 | 2022-09-02 | 2022-09-02
200883C-500-CN-1733-2000 | [D] | 200883C | 500 | CN | 1733 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Vendor Assembled Skids and Equipment Foundations - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-08 | 2022-09-08 | 2022-09-08
200883C-500-CN-1735-2000 | [D] | 200883C | 500 | CN | 1735 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Battery Limit Platform - H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-09-15 | 2022-09-15 | 2022-09-15
200883C-500-DW-0051-4000 | [D] | 200883C | 500 | DW | 51 | 4000 |  | 45 |  | Yuri Phase 0-Equipment arrangement drawing | Code: E0401 | PIP | 500H2 |  |  |  |  | IFR | 50 |  |  | MPIP | 2022-08-29 | 2022-08-29 | 2022-08-29
200883C-500-DW-0052-4000 | [D] | 200883C | 500 | DW | 52 | 4000 |  | 23 |  | Yuri Phase 0-Utility Station And Safety Shower Layout | Code: E0401 | PIP | 500H2 |  |  |  |  | IFR | 50 |  |  | MPIP | 2022-08-30 | 2022-08-30 | 2022-08-30
200883C-500-DW-1425-2001 | [D] | 200883C | 500 | DW | 1425 | 2001 |  | 25 |  | Yuri Phase 0 - Road and car park marking plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-08-29 | 2022-08-29 | 2022-08-29 | Under IDC. Target to issue IFR 2-SEPT
200883C-500-DW-1454-2001 | [D] | 200883C | 500 | DW | 1454 | 2001 |  | 50 |  | Yuri Phase 0 - Hydraulic Systems Details Drawing - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-08-29 | 2022-08-29 | 2022-08-29 | Pending Company's comments on Drainage Philosophy (sent to review since 17-AUG)
200883C-500-DW-1454-2002 | [D] | 200883C | 500 | DW | 1454 | 2002 |  | 25 |  | Yuri Phase 0 - Drainage Schedule - Table - Drainage Profile (1) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-01 | 2022-09-01 | 2022-09-01
200883C-500-DW-1454-2003 | [D] | 200883C | 500 | DW | 1454 | 2003 |  | 25 |  | Yuri Phase 0 - Drainage Schedule - Table - Drainage Profile (2) - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-01 | 2022-09-01 | 2022-09-01
200883C-500-DW-1454-2004 | [D] | 200883C | 500 | DW | 1454 | 2004 |  | 50 |  | Yuri Phase 0 - Drainage Details - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-01 | 2022-09-01 | 2022-09-01
200883C-500-DW-1622-4000 | [D] | 200883C | 500 | DW | 1622 | 4000 |  | 21 |  | Yuri Phase 0 - Electrical Lighting Layout Drawing - Key Plan | Code: E0303 | ELE | 500H2 |  |  |  |  | IFR | 70 |  |  | MELE | 2022-09-01 | 2022-09-01 | 2022-09-01
200883C-500-DW-1624-4001 | [D] | 200883C | 500 | DW | 1624 | 4001 |  | 21 |  | Yuri Phase 0 - Cable Rack Layout Drawing - Key Plan | Code: E0303 | ELE | 500H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-DW-1701-2000 | [D] | 200883C | 500 | DW | 1701 | 2000 |  | 99 |  | Yuri Phase 0 - Overall Foundation Layout Plan - H2 Plant | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-08-30 | 2022-08-30 | 2022-08-30 | Based on original schedule, this document should be issued on 20-SEPT
200883C-500-DW-1742-2000 | [D] | 200883C | 500 | DW | 1742 | 2000 |  | 38 |  | Yuri Phase 0 - Battery Limit Platform Foundation Plans and Details | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-09-15 | 2022-09-15 | 2022-09-15
200883C-500-DW-1743-2000 | [D] | 200883C | 500 | DW | 1743 | 2000 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (1) | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-09-02 | 2022-09-02 | 2022-09-02
200883C-500-DW-1743-2000 | [D] | 200883C | 500 | DW | 1743 | 2000 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (1) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-08 | 2022-09-08 | 2022-09-08
200883C-500-DW-1743-2001 | [D] | 200883C | 500 | DW | 1743 | 2001 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (2) | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-09-02 | 2022-09-02 | 2022-09-02
200883C-500-DW-1743-2001 | [D] | 200883C | 500 | DW | 1743 | 2001 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (2) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-08 | 2022-09-08 | 2022-09-08
200883C-500-DW-1743-2002 | [D] | 200883C | 500 | DW | 1743 | 2002 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (3) | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-09-02 | 2022-09-02 | 2022-09-02
200883C-500-DW-1743-2002 | [D] | 200883C | 500 | DW | 1743 | 2002 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (3) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-08 | 2022-09-08 | 2022-09-08
200883C-500-DW-1743-2003 | [D] | 200883C | 500 | DW | 1743 | 2003 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (4) | Code: E0303 | CIV | 500H2 |  |  |  |  | STA | 10 |  |  | BCIV | 2022-09-02 | 2022-09-02 | 2022-09-02
200883C-500-DW-1743-2003 | [D] | 200883C | 500 | DW | 1743 | 2003 |  | 25 |  | Yuri Phase 0 - Equipment Skid Foundation Plans and Details (4) | Code: E0303 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-09-08 | 2022-09-08 | 2022-09-08
200883C-500-DW-1821-4006 | [D] | 200883C | 500 | DW | 1821 | 4006 |  | 0 |  | Piperack Module - PR2- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-DW-1821-4007 | [D] | 200883C | 500 | DW | 1821 | 4007 |  | 0 |  | Piperack Module - PR2- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-DW-1821-4008 | [D] | 200883C | 500 | DW | 1821 | 4008 |  | 0 |  | Piperack Module - PR2- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-DW-1821-4009 | [D] | 200883C | 500 | DW | 1821 | 4009 |  | 0 |  | Piperack Module - PR2- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-DW-1821-4010 | [D] | 200883C | 500 | DW | 1821 | 4010 |  | 0 |  | Piperack Module - PR2- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-DW-1821-4011 | [D] | 200883C | 500 | DW | 1821 | 4011 |  | 0 |  | Piperack Module - PR3- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16 | Piperack PR3 module, planning is changed as per discussion on 25.08.2022 plot plan review meeting. Revised information is awaited from Piping
200883C-500-DW-1821-4011 | [D] | 200883C | 500 | DW | 1821 | 4011 |  | 0 |  | Piperack Module - PR3- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-30 | 2022-09-30 | Piperack PR3 module, planning is changed as per discussion on 25.08.2022 plot plan review meeting. Revised information is awaited from Piping
200883C-500-DW-1821-4012 | [D] | 200883C | 500 | DW | 1821 | 4012 |  | 0 |  | Piperack Module - PR3- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16 | Piperack PR3 module, planning is changed as per discussion on 25.08.2022 plot plan review meeting. Revised information is awaited from Piping
200883C-500-DW-1821-4012 | [D] | 200883C | 500 | DW | 1821 | 4012 |  | 0 |  | Piperack Module - PR3- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-30 | 2022-09-30 | Piperack PR3 module, planning is changed as per discussion on 25.08.2022 plot plan review meeting. Revised information is awaited from Piping
200883C-500-DW-1821-4013 | [D] | 200883C | 500 | DW | 1821 | 4013 |  | 0 |  | Piperack Module - PR3- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16 | Piperack PR3 module, planning is changed as per discussion on 25.08.2022 plot plan review meeting. Revised information is awaited from Piping
200883C-500-DW-1821-4013 | [D] | 200883C | 500 | DW | 1821 | 4013 |  | 0 |  | Piperack Module - PR3- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-30 | 2022-09-30 | Piperack PR3 module, planning is changed as per discussion on 25.08.2022 plot plan review meeting. Revised information is awaited from Piping
200883C-500-DW-1821-4014 | [D] | 200883C | 500 | DW | 1821 | 4014 |  | 0 |  | Piperack Module - PR3- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16 | Piperack PR3 module, planning is changed as per discussion on 25.08.2022 plot plan review meeting. Revised information is awaited from Piping
200883C-500-DW-1821-4014 | [D] | 200883C | 500 | DW | 1821 | 4014 |  | 0 |  | Piperack Module - PR3- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-30 | 2022-09-30 | Piperack PR3 module, planning is changed as per discussion on 25.08.2022 plot plan review meeting. Revised information is awaited from Piping
200883C-500-DW-1821-4015 | [D] | 200883C | 500 | DW | 1821 | 4015 |  | 0 |  | Piperack Module - PR3- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16 | Piperack PR3 module, planning is changed as per discussion on 25.08.2022 plot plan review meeting. Revised information is awaited from Piping
200883C-500-DW-1821-4015 | [D] | 200883C | 500 | DW | 1821 | 4015 |  | 0 |  | Piperack Module - PR3- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-30 | 2022-09-30 | Piperack PR3 module, planning is changed as per discussion on 25.08.2022 plot plan review meeting. Revised information is awaited from Piping
200883C-500-DW-1821-4016 | [D] | 200883C | 500 | DW | 1821 | 4016 |  | 0 |  | Piperack Module - PR4- Base Plate Plan and Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-10-07 | 2022-10-07 | Piperack PR4 module, is under hold due to non availability of PERIC skids data.
200883C-500-DW-1821-4017 | [D] | 200883C | 500 | DW | 1821 | 4017 |  | 0 |  | Piperack Module - PR4- Structural Plans | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-10-07 | 2022-10-07 | Piperack PR4 module, is under hold due to non availability of PERIC skids data.
200883C-500-DW-1821-4018 | [D] | 200883C | 500 | DW | 1821 | 4018 |  | 0 |  | Piperack Module - PR4- Structural Elevation | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-10-07 | 2022-10-07 | Piperack PR4 module, is under hold due to non availability of PERIC skids data.
200883C-500-DW-1821-4019 | [D] | 200883C | 500 | DW | 1821 | 4019 |  | 0 |  | Piperack Module - PR4- Connection Details | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-10-07 | 2022-10-07 | Piperack PR4 module, is under hold due to non availability of PERIC skids data.
200883C-500-DW-1821-4020 | [D] | 200883C | 500 | DW | 1821 | 4020 |  | 0 |  | Piperack Module - PR4- Concept Drawing for Lifting Arrangement | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-10-07 | 2022-10-07 | Piperack PR4 module, is under hold due to non availability of PERIC skids data.
200883C-500-DW-1825-4000 | [D] | 200883C | 500 | DW | 1825 | 4000 |  | 77 |  | Structural Layout for Skid-1 | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-08-29 | 2022-08-29 | 2022-08-29 | Pump data pending from vendors
200883C-500-DW-1825-4001 | [D] | 200883C | 500 | DW | 1825 | 4001 |  | 77 |  | Structural Detailst for Skid-1 | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-08-29 | 2022-08-29 | 2022-08-29 | Pump data pending from vendors
200883C-500-DW-2025-2000 | [D] | 200883C | 500 | DW | 2025 | 2000 |  | 0 |  | Yuri Phase 0 - H2 Ventilated Enclosure Architectural Conceptual Plans and Elevations | Code: E0302 | CIV | 500H2 |  |  |  |  | IFI | 70 |  |  | BCIV |  | 2022-08-31 | 2022-08-31 | To be issued IFI after issue IFR.
200883C-500-MR-1310-4000 | [D] | 200883C | 500 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Cast Gate Globe Check Valve | Code: E0610 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-06 | 2022-09-06 | 2022-09-06
200883C-500-MR-1310-4000 | [D] | 200883C | 500 | MR | 1310 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Cast Gate Globe Check Valve | Code: E0610 | PIP | 500H2 |  |  |  |  | IFQ | 40 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1310-4001 | [D] | 200883C | 500 | MR | 1310 | 4001 |  | 23 |  | Yuri Phase 0-MR for Ball Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-06 | 2022-09-06 | 2022-09-06
200883C-500-MR-1310-4001 | [D] | 200883C | 500 | MR | 1310 | 4001 |  | 23 |  | Yuri Phase 0-MR for Ball Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | IFQ | 40 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1310-4002 | [D] | 200883C | 500 | MR | 1310 | 4002 |  | 23 |  | Yuri Phase 0-MR for Butterfly Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-06 | 2022-09-06 | 2022-09-06
200883C-500-MR-1310-4002 | [D] | 200883C | 500 | MR | 1310 | 4002 |  | 23 |  | Yuri Phase 0-MR for Butterfly Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | IFQ | 40 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1310-4003 | [D] | 200883C | 500 | MR | 1310 | 4003 |  | 23 |  | Yuri Phase 0-MR for Dual Plate Check Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-06 | 2022-09-06 | 2022-09-06
200883C-500-MR-1310-4003 | [D] | 200883C | 500 | MR | 1310 | 4003 |  | 23 |  | Yuri Phase 0-MR for Dual Plate Check Valves | Code: E0610 | PIP | 500H2 |  |  |  |  | IFQ | 40 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1320-4000 | [D] | 200883C | 500 | MR | 1320 | 4000 |  | 23 |  | Yuri Phase 0-MR for LTCS,CS Seamless Pipes | Code: E0310 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1320-4001 | [D] | 200883C | 500 | MR | 1320 | 4001 |  | 23 |  | Yuri Phase 0-MR for LTCS,CS Welded ,Galvanized Pipes | Code: E0310 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1324-4000 | [D] | 200883C | 500 | MR | 1324 | 4000 |  | 23 |  | Yuri Phase 0-MR for SS Seamless/ Welded Pipes | Code: E0310 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1330-4000 | [D] | 200883C | 500 | MR | 1330 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Wrought Fittings | Code: E0310 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MR-1340-4000 | [D] | 200883C | 500 | MR | 1340 | 4000 |  | 23 |  | Yuri Phase 0-MR for CS / SS Forged Fittings | Code: E0310 | PIP | 500H2 |  |  |  |  | STA | 10 |  |  | MPIP | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-MTO-1311-4003 | [D] | 200883C | 500 | MTO | 1311 | 4003 |  | 338 |  | Yuri Phase 0-Piping Bulk MTO-1 | Code: E0204 | PIP | 500H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-09-06 | 2022-09-06 | 2022-09-06
200883C-500-MTO-1410-2001 | [D] | 200883C | 500 | MTO | 1410 | 2001 |  | 50 |  | Yuri Phase 0 - Road - Pathway - graded track and car park MTO- H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-08-29 | 2022-08-29 | 2022-08-29 | Issued 26-AUG
200883C-500-MTO-1410-2002 | [D] | 200883C | 500 | MTO | 1410 | 2002 |  | 50 |  | Yuri Phase 0 - Stormwater Drainage MTO- H2 Plant | Code: E0301 | CIV | 500H2 |  |  |  |  | IFR | 70 |  |  | BCIV | 2022-08-29 | 2022-08-29 | 2022-08-29 | Pending Company's comments on Drainage Philosophy (sent to review since 17-AUG)
200883C-500-NM-0005-4000 | [D] | 200883C | 500 | NM | 5 | 4000 |  | 24 |  | Yuri Phase 0 - Overall Effluent List | Code: E0311 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-NM-0006-4000 | [D] | 200883C | 500 | NM | 6 | 4000 |  | 24 |  | Yuri Phase 0 - Overall Relief Load Summary | Code: E0311 | PRO | 500H2 |  |  |  |  | STA | 10 |  |  | MPRO | 2022-09-13 | 2022-09-13 | 2022-09-13
200883C-500-PID-0021-4000 | [D] | 200883C | 500 | PID | 21 | 4000 |  | 71 |  | Yuri Phase 0 - PID OSBL Battery Limit (Process and Utility) | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4001 | [D] | 200883C | 500 | PID | 21 | 4001 |  | 71 |  | Yuri Phase 0 - PID Electrolyser Stacks | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4002 | [D] | 200883C | 500 | PID | 21 | 4002 |  | 71 |  | Yuri Phase 0 - PID Gas Liquid Treater Skid A | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4003 | [D] | 200883C | 500 | PID | 21 | 4003 |  | 71 |  | Yuri Phase 0 - PID Gas Liquid Treater Skid B | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4004 | [D] | 200883C | 500 | PID | 21 | 4004 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Purification Package | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4005 | [D] | 200883C | 500 | PID | 21 | 4005 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Buffer tank & Compressor | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4006 | [D] | 200883C | 500 | PID | 21 | 4006 |  | 71 |  | Yuri Phase 0 - PID Hydrogen Product Metering Package | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4007 | [D] | 200883C | 500 | PID | 21 | 4007 |  | 71 |  | Yuri Phase 0 - PID Chilled Water System | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4008 | [D] | 200883C | 500 | PID | 21 | 4008 |  | 71 |  | Yuri Phase 0 - PID Chilled Water Refrigeration Package | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4009 | [D] | 200883C | 500 | PID | 21 | 4009 |  | 47 |  | Yuri Phase 0 - PID Cooing water system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4010 | [D] | 200883C | 500 | PID | 21 | 4010 |  | 71 |  | Yuri Phase 0 - PID Rectifier cooling water system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4011 | [D] | 200883C | 500 | PID | 21 | 4011 |  | 71 |  | Yuri Phase 0 - PID DM Water and Lye System | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4012 | [D] | 200883C | 500 | PID | 21 | 4012 |  | 71 |  | Yuri Phase 0 - PID Instrument Air Receiver | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4013 | [D] | 200883C | 500 | PID | 21 | 4013 |  | 71 |  | Yuri Phase 0 - PID Nitrogen distribution system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4014 | [D] | 200883C | 500 | PID | 21 | 4014 |  | 71 |  | Yuri Phase 0 - PID Potable Water distribution system | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0021-4019 | [D] | 200883C | 500 | PID | 21 | 4019 |  | 24 |  | Yuri Phase 0 - PID Air Cooler System | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0090-4000 | [D] | 200883C | 500 | PID | 90 | 4000 |  | 47 |  | Yuri Phase 0 - PID Drawing Index | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0090-4001 | [D] | 200883C | 500 | PID | 90 | 4001 |  | 71 |  | Yuri Phase 0 - PID Piping Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0090-4002 | [D] | 200883C | 500 | PID | 90 | 4002 |  | 71 |  | Yuri Phase 0 - PID Piping Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-PID-0090-4003 | [D] | 200883C | 500 | PID | 90 | 4003 |  | 71 |  | Yuri Phase 0 - PID Instrument Legend | Code: E0501 | PRO | 500H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-500-RT-1800-4000 | [D] | 200883C | 500 | RT | 1800 | 4000 |  | 62 |  | Structural Steel Design Report for Skid-1 | Code: E0301 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-08-30 | 2022-08-30 | 2022-08-30 | Pump data pending from vendors
200883C-500-RT-1800-4000 | [D] | 200883C | 500 | RT | 1800 | 4000 |  | 62 |  | Structural Steel Design Report for Skid-1 | Code: E0301 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-09-06 | 2022-09-06 | 2022-09-06 | Pump data pending from vendors
200883C-500-RT-1800-4002 | [D] | 200883C | 500 | RT | 1800 | 4002 |  | 62 |  | Structural Steel Design Report for Pipe Supports, Battery Limit Platform | Code: E0301 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR | 2022-09-08 | 2022-09-08 | 2022-09-08
200883C-500-RT-1800-4002 | [D] | 200883C | 500 | RT | 1800 | 4002 |  | 62 |  | Structural Steel Design Report for Pipe Supports, Battery Limit Platform | Code: E0301 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR | 2022-09-14 | 2022-09-14 | 2022-09-14
200883C-500-RT-1800-4006 | [D] | 200883C | 500 | RT | 1800 | 4006 |  | 0 |  | Structural Steel Design Report-Module PR2- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-RT-1800-4007 | [D] | 200883C | 500 | RT | 1800 | 4007 |  | 0 |  | Structural Steel Design Report-Module PR2- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16
200883C-500-RT-1800-4008 | [D] | 200883C | 500 | RT | 1800 | 4008 |  | 0 |  | Structural Steel Design Report-Module PR3- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16 | Piperack PR3 module, planning is changed as per discussion on 25.08.2022 plot plan review meeting. Revised information is awaited from Piping
200883C-500-RT-1800-4008 | [D] | 200883C | 500 | RT | 1800 | 4008 |  | 0 |  | Structural Steel Design Report-Module PR3- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-30 | 2022-09-30 | Piperack PR3 module, planning is changed as per discussion on 25.08.2022 plot plan review meeting. Revised information is awaited from Piping
200883C-500-RT-1800-4009 | [D] | 200883C | 500 | RT | 1800 | 4009 |  | 0 |  | Structural Steel Design Report-Module PR3- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | STA | 10 |  |  | MSTR |  | 2022-09-16 | 2022-09-16 | Piperack PR3 module, planning is changed as per discussion on 25.08.2022 plot plan review meeting. Revised information is awaited from Piping
200883C-500-RT-1800-4009 | [D] | 200883C | 500 | RT | 1800 | 4009 |  | 0 |  | Structural Steel Design Report-Module PR3- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-09-30 | 2022-09-30 | Piperack PR3 module, planning is changed as per discussion on 25.08.2022 plot plan review meeting. Revised information is awaited from Piping
200883C-500-RT-1800-4010 | [D] | 200883C | 500 | RT | 1800 | 4010 |  | 0 |  | Structural Steel Design Report-Module PR4- Inplace Design, Transportation Analysis and Lifting Analysis | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-10-07 | 2022-10-07 | Piperack PR4 module, is under hold due to non availability of PERIC skids data.
200883C-500-RT-1800-4011 | [D] | 200883C | 500 | RT | 1800 | 4011 |  | 0 |  | Structural Steel Design Report-Module PR4- Module Weight and COG Calculation | Code: E0303 | STR | 500H2 |  |  |  |  | IFR | 70 |  |  | MSTR |  | 2022-10-07 | 2022-10-07 | Piperack PR4 module, is under hold due to non availability of PERIC skids data.
200883C-500-TBT-0710-4000 | [D] | 200883C | 500 | TBT | 710 | 4000 |  | 203 |  | TBT for Air Cooled Heat Exchanger | Code: E0204 | MEC | 500H2 |  |  |  |  | IFP | 100 |  |  | MMEC | 2022-08-31 | 2022-08-31 | 2022-08-31
200883C-500-TBT-0811-4000 | [D] | 200883C | 500 | TBT | 811 | 4000 |  | 46 |  | TBT for Vessels (Instrument Air storage vessel) | Code: E0204 | MEC | 500H2 |  |  |  |  | IFP | 100 |  |  | MMEC | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-500-TBT-0910-4000 | [D] | 200883C | 500 | TBT | 910 | 4000 |  | 90 |  | TBT for Centrifugal Pumps (Cooling Water, Chilled Water Circulation, Potable Water) | Code: E0204 | MEC | 500H2 |  |  |  |  | IFP | 100 |  |  | MMEC | 2022-09-01 | 2022-09-01 | 2022-09-01
200883C-500-TBT-1900-4000 | [D] | 200883C | 500 | TBT | 1900 | 4000 |  | 45 |  | TBT for Safety Equipment | Code: E0204 | MEC | 500H2 |  |  |  |  | IFP | 100 |  |  | MMEC | 2022-09-04 | 2022-09-04 | 2022-09-04
200883C-500-TBT-4150-4000 | [D] | 200883C | 500 | TBT | 4150 | 4000 |  | 202 |  | TBT for Refrigeration package | Code: E0204 | MEC | 500H2 |  |  |  |  | IFP | 100 |  |  | MMEC | 2022-08-31 | 2022-08-31 | 2022-08-31
200883C-600-CN-1735-2000 | [D] | 200883C | 600 | CN | 1735 | 2000 |  | 50 |  | Yuri Phase 0 - Calculation For Brownfield Pipe Support / Cable Tray Support Foundation | Code: E0301 | CIV | 600H2 |  |  |  |  | IFD | 100 |  |  | BCIV | 2022-08-05 | 2022-08-05 | 2022-09-13 | To be issued IFD by 1-SEP
200883C-600-DW-1624-4001 | [D] | 200883C | 600 | DW | 1624 | 4001 |  | 21 |  | Yuri Phase 0 - YARA Plant Cable Routing Layout (Brown Field scope) | Code: E0303 | ELE | 600H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-08-04 | 2022-08-04 | 2022-09-14
200883C-600-DW-1741-2000 | [D] | 200883C | 600 | DW | 1741 | 2000 |  | 38 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (1) | Code: E0303 | CIV | 600H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-08-22 | 2022-08-22 | 2022-09-13 | To be issued IFC by 1-SEP
200883C-600-DW-1741-2001 | [D] | 200883C | 600 | DW | 1741 | 2001 |  | 38 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (2) | Code: E0303 | CIV | 600H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-08-22 | 2022-08-22 | 2022-09-13 | To be issued IFC by 1-SEP
200883C-600-DW-1741-2002 | [D] | 200883C | 600 | DW | 1741 | 2002 |  | 31 |  | Yuri Phase 0 - Pipe/Cable Tray Supports inside existing plant Foundation Details (3) | Code: E0303 | CIV | 600H2 |  |  |  |  | IFC | 100 |  |  | BCIV | 2022-08-22 | 2022-08-22 | 2022-09-13 | To be issued IFC by 1-SEP
200883C-600-PID-0021-4000 | [D] | 200883C | 600 | PID | 21 | 4000 |  | 24 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Potable Water | Code: E0501 | PRO | 600H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-600-PID-0021-4001 | [D] | 200883C | 600 | PID | 21 | 4001 |  | 24 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for DM Water | Code: E0501 | PRO | 600H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-600-PID-0021-4002 | [D] | 200883C | 600 | PID | 21 | 4002 |  | 12 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Hydrogen | Code: E0501 | PRO | 600H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-600-PID-0021-4003 | [D] | 200883C | 600 | PID | 21 | 4003 |  | 12 |  | Yuri Phase 0 - Tie-In (Brownfields) PIDs for Instrument Air and Nitrogen | Code: E0501 | PRO | 600H2 |  |  |  |  | IFD | 80 |  |  | MPRO | 2022-09-12 | 2022-09-12 | 2022-09-12
200883C-600-TBT-1310-4000 | [D] | 200883C | 600 | TBT | 1310 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Forged Gate Globe Check Valve | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1320-4000 | [D] | 200883C | 600 | TBT | 1320 | 4000 |  | 23 |  | Yuri Phase 0-TBT for AS, CS, SS Seamless Pipes | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1340-4000 | [D] | 200883C | 600 | TBT | 1340 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Forged Fittings | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1340-4001 | [D] | 200883C | 600 | TBT | 1340 | 4001 |  | 23 |  | Yuri Phase 0-TBT for CS / SS Wrought Fittings | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1350-4000 | [D] | 200883C | 600 | TBT | 1350 | 4000 |  | 23 |  | Yuri Phase 0-TBT for CS Flanges, Spectacle Blinds, Paddle & Blanks | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1360-4000 | [D] | 200883C | 600 | TBT | 1360 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Gaskets | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1370-4000 | [D] | 200883C | 600 | TBT | 1370 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Machine Bolts, Stud Bolts & Nuts | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1383-4000 | [D] | 200883C | 600 | TBT | 1383 | 4000 |  | 23 |  | Yuri Phase 0-TBT for Supports | Code: E0204 | PIP | 600H2 |  |  |  |  | IFP | 100 |  |  | MPIP | 2022-08-27 | 2022-08-27 | 2022-08-27
200883C-600-TBT-1574-4000 | [D] | 200883C | 600 | TBT | 1574 | 4000 |  | 16 |  | Yuri Phase 0 - Technical Bid Tabulation For Instrument Cables-Brown Field | Code: E0204 | INS | 600H2 |  |  |  |  | IFP | 100 |  |  | MINS | 2022-09-15 | 2022-09-15 | 2022-09-15
200883C-700-DW-1612-4000 | [D] | 200883C | 700 | DW | 1612 | 4000 |  | 21 |  | Yuri Phase 0 - Substation Building Earthing Layout | Code: E0303 | ELE | 700H2 |  |  |  |  | IFC | 100 |  |  | MELE | 2022-08-27 | 2022-08-27 | 2022-08-27

## MFG
Overdue
DELIVERABLE REFERENCE | CAT | DLV REF. P1: CONTRACT CODE | DLV REF. P2: UNIT CODE | DLV REF. P3: DOC/DLV TYPE | DLV REF. P4: ENGINEERING CODE | DLV REF. P5: SERIAL NUMBER | CLIENT REFERENCE | WEIGHT | MANUFACTURING WEIGHT | TITLE | MILESTONE CHAIN | DBS | WBS | FREE CRITERIA 1 | FREE CRITERIA 2 | FREE CRITERIA 3 | FREE CRITERIA 4 | MSCODE | CUMULATIVE | MANUFACTURING CUMULATIVE | PBS | OBS | INITIAL PLAN DATE | REVISED PLAN DATE | FORECAST DATE | Status | Submission Date | Forecast Date2 | Reason for delay
200883C-000-NM-1500-5001 | [D] | 200883C | 0 | NM | 1500 | 5001 |  | 80 |  | Yuri Phase 0 - Modbus Mapping Address NCU (Network Control Unit) | Code: E0303 | INS | 000PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-07-19 | 2022-07-19 | 2022-07-19 | In Progress |  | 2022-09-12
200883C-000-NM-1500-5001 | [D] | 200883C | 0 | NM | 1500 | 5001 |  | 80 |  | Yuri Phase 0 - Modbus Mapping Address NCU (Network Control Unit) | Code: E0303 | INS | 000PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-08-18 | 2022-08-18 | 2022-08-18 | In Progress |  | 2022-09-12
200883C-000-NM-1500-5002 | [D] | 200883C | 0 | NM | 1500 | 5002 |  | 80 |  | Yuri Phase 0 - Master Signals List | Code: E0303 | INS | 000PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-07-20 | 2022-07-20 | 2022-08-22 | In Progress |  | 2022-09-12
200883C-000-RT-1400-5001 | [D] | 200883C | 0 | RT | 1400 | 5001 |  | 30 |  | Yuri Phase 0 - Atmospheric Corrosion Assessment | Code: E0303 | CIV | 000PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-30 | In Progress | 2022-06-20 | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-000-RT-1600-5000 | [D] | 200883C | 0 | RT | 1600 | 5000 |  | 120 |  | Yuri Phase 0 - Arc Fault Studies | Code: E0303 | ELE | 000PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-08-14 | 2022-08-14 | 2022-08-14 | Not Started |  | 2022-09-30 | Pending Technip Approval
200883C-400-DW-1423-5000 | [D] | 200883C | 400 | DW | 1423 | 5000 |  | 20 |  | Yuri Phase 0 - Drainage - culvert layout plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-15 | 2022-07-15 | 2022-07-15 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1423-5000 | [D] | 200883C | 400 | DW | 1423 | 5000 |  | 20 |  | Yuri Phase 0 - Drainage - culvert layout plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-14 | 2022-08-14 | 2022-08-14 | In Progress | 2022-08-26 | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1423-5003 | [D] | 200883C | 400 | DW | 1423 | 5003 |  | 40 |  | Yuri Phase 0 - Bulk Earthworks Cut and Fill Plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-15 | 2022-07-15 | 2022-07-15 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1423-5003 | [D] | 200883C | 400 | DW | 1423 | 5003 |  | 40 |  | Yuri Phase 0 - Bulk Earthworks Cut and Fill Plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-14 | 2022-08-14 | 2022-08-14 | In Progress | 2022-08-26 | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1423-5004 | [D] | 200883C | 400 | DW | 1423 | 5004 |  | 48 |  | Yuri Phase 0 - Bulk earthworks grading plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-15 | 2022-07-15 | 2022-07-15 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1423-5004 | [D] | 200883C | 400 | DW | 1423 | 5004 |  | 48 |  | Yuri Phase 0 - Bulk earthworks grading plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-14 | 2022-08-14 | 2022-08-14 | In Progress | 2022-08-26 | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1423-5005 | [D] | 200883C | 400 | DW | 1423 | 5005 |  | 48 |  | Yuri Phase 0 - Typical bulk earthwork cross sections - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-06-30 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1423-5005 | [D] | 200883C | 400 | DW | 1423 | 5005 |  | 48 |  | Yuri Phase 0 - Typical bulk earthwork cross sections - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-30 | In Progress | 2022-08-26 | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1423-5006 | [D] | 200883C | 400 | DW | 1423 | 5006 |  | 20 |  | Yuri Phase 0 - Cut and Fill Bulk Earthworks Overview - PV plant | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-15 | 2022-07-15 | 2022-07-15 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1423-5006 | [D] | 200883C | 400 | DW | 1423 | 5006 |  | 20 |  | Yuri Phase 0 - Cut and Fill Bulk Earthworks Overview - PV plant | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-14 | 2022-08-14 | 2022-08-14 | In Progress | 2022-08-26 | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1423-5007 | [D] | 200883C | 400 | DW | 1423 | 5007 |  | 40 |  | Yuri Phase 0 - Cut And Fill Bulk Earthworks - Array Xx - PV plant | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-15 | 2022-07-15 | 2022-07-15 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1423-5007 | [D] | 200883C | 400 | DW | 1423 | 5007 |  | 40 |  | Yuri Phase 0 - Cut And Fill Bulk Earthworks - Array Xx - PV plant | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-14 | 2022-08-14 | 2022-08-14 | In Progress | 2022-08-26 | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1424-5000 | [D] | 200883C | 400 | DW | 1424 | 5000 |  | 40 |  | Yuri Phase 0 - Fencing Plan Sheet | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-15 | 2022-07-15 | 2022-07-15 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1424-5000 | [D] | 200883C | 400 | DW | 1424 | 5000 |  | 40 |  | Yuri Phase 0 - Fencing Plan Sheet | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-14 | 2022-08-14 | 2022-08-14 | In Progress | 2022-08-26 | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1424-5002 | [D] | 200883C | 400 | DW | 1424 | 5002 |  | 16 |  | Yuri Phase 0 - Gate Details Sheet - PV | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-08-16 | 2022-08-16 | 2022-08-16 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1425-5001 | [D] | 200883C | 400 | DW | 1425 | 5001 |  | 40 |  | Yuri Phase 0 - Road Culvert layout - PV | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-07-11 | 2022-07-11 | 2022-07-11 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1425-5001 | [D] | 200883C | 400 | DW | 1425 | 5001 |  | 40 |  | Yuri Phase 0 - Road Culvert layout - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-08-10 | 2022-08-10 | 2022-08-10 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1425-5002 | [D] | 200883C | 400 | DW | 1425 | 5002 |  | 32 |  | Yuri Phase 0 - Roadside drainage structure design plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-06-30 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1425-5002 | [D] | 200883C | 400 | DW | 1425 | 5002 |  | 32 |  | Yuri Phase 0 - Roadside drainage structure design plan - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-30 | In Progress | 2022-08-26 | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1425-5003 | [D] | 200883C | 400 | DW | 1425 | 5003 |  | 40 |  | Yuri Phase 0 - Roadside drainage structure detail - PV | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-26 | 2022-06-26 | 2022-06-26 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1425-5003 | [D] | 200883C | 400 | DW | 1425 | 5003 |  | 40 |  | Yuri Phase 0 - Roadside drainage structure detail - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-26 | 2022-07-26 | 2022-07-26 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1425-5003 | [D] | 200883C | 400 | DW | 1425 | 5003 |  | 40 |  | Yuri Phase 0 - Roadside drainage structure detail - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-25 | 2022-08-25 | 2022-08-25 | In Progress | 2022-08-26 | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1425-5005 | [D] | 200883C | 400 | DW | 1425 | 5005 |  | 40 |  | Yuri Phase 0 - Road Longitudinal Section | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-07-25 | 2022-07-25 | 2022-07-25 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1425-5005 | [D] | 200883C | 400 | DW | 1425 | 5005 |  | 40 |  | Yuri Phase 0 - Road Longitudinal Section | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-08-24 | 2022-08-24 | 2022-08-24 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1425-5006 | [D] | 200883C | 400 | DW | 1425 | 5006 |  | 40 |  | Yuri Phase 0 - Road Cross Sections | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-06-30 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1425-5006 | [D] | 200883C | 400 | DW | 1425 | 5006 |  | 40 |  | Yuri Phase 0 - Road Cross Sections | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-30 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1454-5001 | [D] | 200883C | 400 | DW | 1454 | 5001 |  | 40 |  | Yuri Phase 0 - Trench Sections | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-13 | 2022-07-13 | 2022-09-09 | In Progress |  | 2022-09-09 | In Progress
200883C-400-DW-1454-5001 | [D] | 200883C | 400 | DW | 1454 | 5001 |  | 40 |  | Yuri Phase 0 - Trench Sections | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-12 | 2022-08-12 | 2022-08-12 | In Progress |  | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1454-5002 | [D] | 200883C | 400 | DW | 1454 | 5002 |  | 40 |  | Yuri Phase 0 - DC Trench Route PV Array Xx | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-14 | 2022-08-14 | 2022-08-14 | In Progress | 2022-06-15 | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1454-5003 | [D] | 200883C | 400 | DW | 1454 | 5003 |  | 40 |  | Yuri Phase 0 - DC Trench Route PV Array Xx - Section | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-06-30 | Completed |  |  | Completed
200883C-400-DW-1454-5003 | [D] | 200883C | 400 | DW | 1454 | 5003 |  | 40 |  | Yuri Phase 0 - DC Trench Route PV Array Xx - Section | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-30 | Completed | 2022-06-22 |  | Completed
200883C-400-DW-1522-5001 | [D] | 200883C | 400 | DW | 1522 | 5001 |  | 40 |  | Yuri Phase 0 - PCS-Xx Comms Connections | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-07-19 | 2022-07-19 | 2022-08-19 | In Progress |  | 2022-09-12
200883C-400-DW-1572-5000 | [D] | 200883C | 400 | DW | 1572 | 5000 |  | 40 |  | Yuri Phase 0 - PCS-Xx Cable Connections | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-07-19 | 2022-07-19 | 2022-07-19 | In Progress |  | 2022-09-12
200883C-400-DW-1572-5000 | [D] | 200883C | 400 | DW | 1572 | 5000 |  | 40 |  | Yuri Phase 0 - PCS-Xx Cable Connections | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-08-18 | 2022-08-18 | 2022-08-18 | Not Started |  | 2022-09-02
200883C-400-DW-1622-5002 | [D] | 200883C | 400 | DW | 1622 | 5002 |  | 40 |  | Yuri Phase 0 - Site Array Layout And Labelling - PV | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-06-30 | Completed | 2022-08-26 |  | Completed
200883C-400-DW-1652-5000 | [D] | 200883C | 400 | DW | 1652 | 5000 |  | 24 |  | Yuri Phase 0 - SLD Xx - Xx string COMBINER BOX - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-17 | 2022-07-17 | 2022-07-17 | In Progress |  | 2022-10-14 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1652-5001 | [D] | 200883C | 400 | DW | 1652 | 5001 |  | 128 |  | Yuri Phase 0 - EMS SLD - Architecture | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-15 | 2022-06-15 | 2022-06-15 | Completed |  |  | Completed
200883C-400-DW-1652-5001 | [D] | 200883C | 400 | DW | 1652 | 5001 |  | 128 |  | Yuri Phase 0 - EMS SLD - Architecture | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-15 | 2022-07-15 | 2022-07-15 | In Progress |  | 2022-10-14 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1662-5000 | [D] | 200883C | 400 | DW | 1662 | 5000 |  | 40 |  | Yuri Phase 0 - Inverter HV Switchgear Schematic Control Diagrams - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-17 | 2022-06-17 | 2022-06-17 | Completed |  |  | Completed
200883C-400-DW-1662-5000 | [D] | 200883C | 400 | DW | 1662 | 5000 |  | 40 |  | Yuri Phase 0 - Inverter HV Switchgear Schematic Control Diagrams - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-17 | 2022-07-17 | 2022-07-17 | In Progress |  | 2022-10-14 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1662-5001 | [D] | 200883C | 400 | DW | 1662 | 5001 |  | 80 |  | Yuri Phase 0 - EMS Schematics | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-06 | 2022-07-06 | 2022-07-06 | In Progress |  | 2022-09-16 | Ongoing design and development. Some information required from Engie
200883C-400-DW-1662-5001 | [D] | 200883C | 400 | DW | 1662 | 5001 |  | 80 |  | Yuri Phase 0 - EMS Schematics | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-05 | 2022-08-05 | 2022-08-05 | In Progress |  | 2022-10-14 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1664-5001 | [D] | 200883C | 400 | DW | 1664 | 5001 |  | 40 |  | Yuri Phase 0 - Panel Wiring Drawings - EMS | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-07-27 | 2022-07-27 | 2022-07-27 | In Progress |  | 2022-09-16 | Ongoing design and development. Some information required from Engie
200883C-400-DW-1664-5001 | [D] | 200883C | 400 | DW | 1664 | 5001 |  | 40 |  | Yuri Phase 0 - Panel Wiring Drawings - EMS | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-08-26 | 2022-08-26 | 2022-08-26 | In Progress |  | 2022-09-16 | Ongoing design and development. Some information required from Engie
200883C-400-DW-1665-5000 | [D] | 200883C | 400 | DW | 1665 | 5000 |  | 16 |  | Yuri Phase 0 - Electrical General Arrangement Module Interconnection Details - 2 Sheets | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-15 | 2022-07-15 | 2022-07-15 | In Progress |  | 2022-10-14 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1665-5001 | [D] | 200883C | 400 | DW | 1665 | 5001 |  | 16 |  | Yuri Phase 0 - Termination Drawings | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-09 | 2022-06-09 | 2022-06-09 | In Progress |  |  | Ongoing design and development.
200883C-400-DW-1665-5001 | [D] | 200883C | 400 | DW | 1665 | 5001 |  | 16 |  | Yuri Phase 0 - Termination Drawings | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-09 | 2022-07-09 | 2022-07-09 | In Progress |  | 2022-10-14 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1722-5000 | [D] | 200883C | 400 | DW | 1722 | 5000 |  | 40 |  | Yuri Phase 0 - Platform Levels and Details Specifications - Foundations and Footings - PV Inverters | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-07-08 | 2022-07-08 | 2022-07-08 | Completed |  |  | Completed
200883C-400-DW-1722-5000 | [D] | 200883C | 400 | DW | 1722 | 5000 |  | 40 |  | Yuri Phase 0 - Platform Levels and Details Specifications - Foundations and Footings - PV Inverters | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-07 | 2022-08-07 | 2022-08-07 | In Progress |  | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1722-5001 | [D] | 200883C | 400 | DW | 1722 | 5001 |  | 16 |  | Yuri Phase 0 - Typical Table Arrangments - PV structures | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-30 | In Progress | 2022-06-10 | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-DW-1824-5000 | [D] | 200883C | 400 | DW | 1824 | 5000 |  | 40 |  | Yuri Phase 0 - Platform Levels - PV area | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-06-30 | 2022-06-30 | 2022-06-30 | Completed |  |  | Completed
200883C-400-DW-1824-5000 | [D] | 200883C | 400 | DW | 1824 | 5000 |  | 40 |  | Yuri Phase 0 - Platform Levels - PV area | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-07-30 | 2022-07-30 | 2022-07-30 | In Progress | 2022-06-17 | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-JSD-1400-5000 | [D] | 200883C | 400 | JSD | 1400 | 5000 |  | 40 |  | Yuri Phase 0 - Basis Of Design For Civil Works - PV Plant | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-05-18 | 2022-05-18 | 2022-05-18 | Completed |  |  | Completed
200883C-400-JSD-1400-5000 | [D] | 200883C | 400 | JSD | 1400 | 5000 |  | 40 |  | Yuri Phase 0 - Basis Of Design For Civil Works - PV Plant | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-06-17 | 2022-06-17 | 2022-06-17 | In Progress | 2022-06-23 | 2022-10-17 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-JSS-1510-5000 | [D] | 200883C | 400 | JSS | 1510 | 5000 |  | 168 |  | Yuri Phase 0 - Functional Design Specifications | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-06-22 | 2022-06-22 | 2022-06-22 | In Progress |  | 2022-09-12
200883C-400-JSS-1510-5000 | [D] | 200883C | 400 | JSS | 1510 | 5000 |  | 168 |  | Yuri Phase 0 - Functional Design Specifications | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-07-22 | 2022-07-22 | 2022-07-22 |  |  | 2022-09-02
200883C-400-JSS-1640-5000 | [D] | 200883C | 400 | JSS | 1640 | 5000 |  | 40 |  | Yuri Phase 0 - Specification for Transformers - Inverters | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-29 | 2022-06-29 | 2022-06-29 | In Progress |  | 2022-09-16 | Finalisation of design ongoing.
200883C-400-JSS-1640-5000 | [D] | 200883C | 400 | JSS | 1640 | 5000 |  | 40 |  | Yuri Phase 0 - Specification for Transformers - Inverters | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-29 | 2022-07-29 | 2022-07-29 | In Progress |  | 2022-09-16 | Finalisation of design ongoing.
200883C-400-JSS-1673-5001 | [D] | 200883C | 400 | JSS | 1673 | 5001 |  | 40 |  | Yuri Phase 0 - Battery Management System Description | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-19 | 2022-07-19 | 2022-07-19 | Completed |  |  | Completed
200883C-400-JSS-1673-5001 | [D] | 200883C | 400 | JSS | 1673 | 5001 |  | 40 |  | Yuri Phase 0 - Battery Management System Description | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-18 | 2022-08-18 | 2022-08-18 | In Progress |  | 2022-10-14 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-NM-1500-5000 | [D] | 200883C | 400 | NM | 1500 | 5000 |  | 80 |  | Yuri Phase 0 - MV Station Com Panel I - O Signals List | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-07-19 | 2022-07-19 | 2022-07-19 | In Progress |  | 2022-09-12
200883C-400-NM-1500-5000 | [D] | 200883C | 400 | NM | 1500 | 5000 |  | 80 |  | Yuri Phase 0 - MV Station Com Panel I - O Signals List | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-08-18 | 2022-08-18 | 2022-08-18 | In Progress |  | 2022-09-12
200883C-400-NM-1535-5000 | [D] | 200883C | 400 | NM | 1535 | 5000 |  | 80 |  | Yuri Phase 0 – EMS Alarm List | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFINS | 2022-07-19 | 2022-07-19 | 2022-07-19 | In Progress |  | 2022-09-12
200883C-400-NM-1535-5000 | [D] | 200883C | 400 | NM | 1535 | 5000 |  | 80 |  | Yuri Phase 0 – EMS Alarm List | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-08-18 | 2022-08-18 | 2022-08-18 | In Progress |  | 2022-09-12
200883C-400-NM-1572-5000 | [D] | 200883C | 400 | NM | 1572 | 5000 |  | 80 |  | Yuri Phase 0 - Met Station Signal List | Code: E0303 | INS | 400PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-07-20 | 2022-07-20 | 2022-07-20 | In Progress |  | 2022-09-12
200883C-400-NM-1572-5000 | [D] | 200883C | 400 | NM | 1572 | 5000 |  | 80 |  | Yuri Phase 0 - Met Station Signal List | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-08-19 | 2022-08-19 | 2022-08-19 | In Progress |  | 2022-09-09
200883C-400-NM-1600-5000 | [D] | 200883C | 400 | NM | 1600 | 5000 |  | 40 |  | Yuri Phase 0 - Hourly Generation Data | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-06-30 | 2022-06-30 | 2022-06-30 | In Progress |  | 2022-09-16 | Ongoing design and development.
200883C-400-NM-1600-5000 | [D] | 200883C | 400 | NM | 1600 | 5000 |  | 40 |  | Yuri Phase 0 - Hourly Generation Data | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-07-30 | In Progress |  | 2022-09-16 | Ongoing design and development.
200883C-400-NM-1623-5000 | [D] | 200883C | 400 | NM | 1623 | 5000 |  | 80 |  | Yuri Phase 0 - DC Cable Schedules - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-17 | 2022-06-17 | 2022-06-17 | Completed |  | 2022-09-01 | Completed
200883C-400-NM-1623-5000 | [D] | 200883C | 400 | NM | 1623 | 5000 |  | 80 |  | Yuri Phase 0 - DC Cable Schedules - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-17 | 2022-07-17 | 2022-07-17 | In Progress |  | 2022-10-14 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-NM-5000 | [D] | 200883C | 400 | NM |  | 5000 |  | 40 |  | Yuri Phase 0 - PV Array Xx - Set out Points | Code: E0303 | MEC | 400PV |  |  |  |  | STA | 10 |  |  | MFMEC | 2022-07-10 | 2022-07-10 | 2022-08-15 | In Progress |  | 2022-09-16
200883C-400-RT-1400-5000 | [D] | 200883C | 400 | RT | 1400 | 5000 |  | 80 |  | Yuri Phase 0 - Civil and Structural Report - PV Area | Code: E0303 | CIV | 400PV |  |  |  |  | STA | 10 |  |  | MFCIV | 2022-07-19 | 2022-07-19 | 2022-07-19 | Completed |  |  | Completed
200883C-400-RT-1400-5000 | [D] | 200883C | 400 | RT | 1400 | 5000 |  | 80 |  | Yuri Phase 0 - Civil and Structural Report - PV Area | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-08-18 | 2022-08-18 | 2022-08-18 | In Progress |  | 2022-09-23 | In Progress
200883C-400-RT-1600-5000 | [D] | 200883C | 400 | RT | 1600 | 5000 |  | 320 |  | Yuri Phase 0 - Power System Studies (loadflow - short circuit - transient stability) | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-07-15 | 2022-07-15 | 2022-07-15 | In Progress |  | 2022-09-30 | Ongoing design and development.
200883C-400-RT-1600-5000 | [D] | 200883C | 400 | RT | 1600 | 5000 |  | 320 |  | Yuri Phase 0 - Power System Studies (loadflow - short circuit - transient stability) | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-08-14 | 2022-08-14 | 2022-08-14 | In Progress |  | 2022-09-30 | Ongoing design and development.
200883C-400-RT-1600-5002 | [D] | 200883C | 400 | RT | 1600 | 5002 |  | 40 |  | Yuri Phase 0 - Energy Yield Analysis | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-29 | 2022-06-29 | 2022-06-29 | In Progress |  | 2022-09-16 | Ongoing design and development.
200883C-400-RT-1600-5002 | [D] | 200883C | 400 | RT | 1600 | 5002 |  | 40 |  | Yuri Phase 0 - Energy Yield Analysis | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-29 | 2022-07-29 | 2022-07-29 | In Progress |  | 2022-10-14 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-RT-1600-5003 | [D] | 200883C | 400 | RT | 1600 | 5003 |  | 40 |  | Yuri Phase 0 - Shading Analysis | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-06-29 | 2022-06-29 | 2022-06-29 | In Progress |  | 2022-09-16 | Ongoing design and development.
200883C-400-RT-1600-5003 | [D] | 200883C | 400 | RT | 1600 | 5003 |  | 40 |  | Yuri Phase 0 - Shading Analysis | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-29 | 2022-07-29 | 2022-07-29 | In Progress |  | 2022-10-14 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-RT-1600-5005 | [D] | 200883C | 400 | RT | 1600 | 5005 |  | 40 |  | Yuri Phase 0 - Cable Design Report - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-15 | 2022-07-15 | 2022-07-15 | In Progress |  | 2022-09-30
200883C-400-RT-1600-5005 | [D] | 200883C | 400 | RT | 1600 | 5005 |  | 40 |  | Yuri Phase 0 - Cable Design Report - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-14 | 2022-08-14 | 2022-08-14 | In Progress |  | 2022-10-14 | IFC/Detailed Design to be submitted after NTP received.
200883C-400-RT-1600-5006 | [D] | 200883C | 400 | RT | 1600 | 5006 |  | 40 |  | Yuri Phase 0 - Insulation Coordination Report - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-07-30 | On Hold |  | 2022-09-30 | Pending Approval from Technip for Variation
200883C-400-RT-1600-5007 | [D] | 200883C | 400 | RT | 1600 | 5007 |  | 80 |  | Yuri Phase 0 - Electrical Design Report - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-21 | 2022-07-21 | 2022-07-21 | In Progress |  | 2022-11-01
200883C-400-RT-1600-5007 | [D] | 200883C | 400 | RT | 1600 | 5007 |  | 80 |  | Yuri Phase 0 - Electrical Design Report - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-20 | 2022-08-20 | 2022-08-20 | In Progress |  | 2022-10-14 | IFC/Detailed Design to be submitted after NTP received.
3WLAH
DELIVERABLE REFERENCE | CAT | DLV REF. P1: CONTRACT CODE | DLV REF. P2: UNIT CODE | DLV REF. P3: DOC/DLV TYPE | DLV REF. P4: ENGINEERING CODE | DLV REF. P5: SERIAL NUMBER | CLIENT REFERENCE | WEIGHT | MANUFACTURING WEIGHT | TITLE | MILESTONE CHAIN | DBS | WBS | FREE CRITERIA 1 | FREE CRITERIA 2 | FREE CRITERIA 3 | FREE CRITERIA 4 | MSCODE | CUMULATIVE | MANUFACTURING CUMULATIVE | PBS | OBS | INITIAL PLAN DATE | REVISED PLAN DATE | FORECAST DATE | Column1
200883C-000-JSS-1574-5000 | [D] | 200883C | 0 | JSS | 1574 | 5000 |  | 40 |  | Yuri Phase 0 - FO Cable Datasheet | Code: E0303 | INS | 000PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-06-15 | 2022-06-15 | 2022-08-29 | Completed
200883C-000-JSS-1574-5000 | [D] | 200883C | 0 | JSS | 1574 | 5000 |  | 40 |  | Yuri Phase 0 - FO Cable Datasheet | Code: E0303 | INS | 000PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-07-15 | 2022-07-15 | 2022-09-08 | Completed
200883C-000-NM-1500-5000 | [D] | 200883C | 0 | NM | 1500 | 5000 |  | 40 |  | Yuri Phase 0 - Inverter Station Das Panel I - O Signals List (Battery and PV) | Code: E0303 | INS | 000PV |  |  |  |  | IFR | 70 |  |  | MFINS | 2022-05-26 | 2022-05-26 | 2022-08-29 | Completed
200883C-000-NM-1500-5002 | [D] | 200883C | 0 | NM | 1500 | 5002 |  | 80 |  | Yuri Phase 0 - Master Signals List | Code: E0303 | INS | 000PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-08-19 | 2022-08-19 | 2022-09-16 | In Progress
200883C-000-RT-1600-5000 | [D] | 200883C | 0 | RT | 1600 | 5000 |  | 120 |  | Yuri Phase 0 - Arc Fault Studies | Code: E0303 | ELE | 000PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-09-13 | 2022-09-13 | 2022-09-13 | Not Started
200883C-400-DW-0410-5000 | [D] | 200883C | 400 | DW | 410 | 5000 |  | 200 |  | Yuri Phase 0 - Site Plan - GA (Including Facilities) Overall Site Layout - Array - 6 sheets | Code: E0303 | MEC | 400PV |  |  |  |  | IFC | 100 |  |  | MFMEC | 2022-07-10 | 2022-07-10 | 2022-08-31 | Completed
200883C-400-DW-1424-5002 | [D] | 200883C | 400 | DW | 1424 | 5002 |  | 16 |  | Yuri Phase 0 - Gate Details Sheet - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFR | 70 |  |  | MFCIV | 2022-09-15 | 2022-09-15 | 2022-09-15 | Completed
200883C-400-DW-1425-5001 | [D] | 200883C | 400 | DW | 1425 | 5001 |  | 40 |  | Yuri Phase 0 - Road Culvert layout - PV | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-09-09 | 2022-09-09 | 2022-09-09 | Completed
200883C-400-DW-1425-5006 | [D] | 200883C | 400 | DW | 1425 | 5006 |  | 40 |  | Yuri Phase 0 - Road Cross Sections | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-29 | 2022-08-29 | 2022-08-29 | Completed
200883C-400-DW-1454-5003 | [D] | 200883C | 400 | DW | 1454 | 5003 |  | 40 |  | Yuri Phase 0 - DC Trench Route PV Array Xx - Section | Code: E0303 | CIV | 400PV |  |  |  |  | IFC | 100 |  |  | MFCIV | 2022-08-29 | 2022-08-29 | 2022-08-29 | Completed
200883C-400-DW-1522-5001 | [D] | 200883C | 400 | DW | 1522 | 5001 |  | 40 |  | Yuri Phase 0 - PCS-Xx Comms Connections | Code: E0303 | INS | 400PV |  |  |  |  | IFC | 100 |  |  | MFINS | 2022-08-18 | 2022-08-18 | 2022-08-31 | In Progress
200883C-400-DW-1612-5001 | [D] | 200883C | 400 | DW | 1612 | 5001 |  | 16 |  | Yuri Phase 0 - LV Protective Earthing Connections General Arrangments-02 | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-08-30 | Completed
200883C-400-DW-1612-5002 | [D] | 200883C | 400 | DW | 1612 | 5002 |  | 16 |  | Yuri Phase 0 - LV Protective Earthing Between Structures - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-08-30 | Completed
200883C-400-DW-1612-5003 | [D] | 200883C | 400 | DW | 1612 | 5003 |  | 50 |  | Yuri Phase 0 - Array Xx LV Earthing - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-08-29 | Completed
200883C-400-DW-1622-5001 | [D] | 200883C | 400 | DW | 1622 | 5001 |  | 32 |  | Yuri Phase 0 - Major Electrical Equipment Labelling - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-08-29 | Completed
200883C-400-DW-1622-5002 | [D] | 200883C | 400 | DW | 1622 | 5002 |  | 40 |  | Yuri Phase 0 - Site Array Layout And Labelling - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-08-31 | Completed
200883C-400-DW-1624-5000 | [D] | 200883C | 400 | DW | 1624 | 5000 |  | 40 |  | Yuri Phase 0 - Electrical General Arrangement Cable Extender Arrangements - 3 Sheets | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-07-30 | 2022-07-30 | 2022-08-30 | Completed
200883C-400-DW-1624-5001 | [D] | 200883C | 400 | DW | 1624 | 5001 |  | 40 |  | Yuri Phase 0 - DC Sub-Array Feeder Cables - PV | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-08-29 | Completed
200883C-400-DW-1625-5002 | [D] | 200883C | 400 | DW | 1625 | 5002 |  | 1 |  | Yuri Phase 0 - DAS General Arrangement | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE |  | 2022-09-02 | 2022-09-02
200883C-400-DW-1625-5003 | [D] | 200883C | 400 | DW | 1625 | 5003 |  | 1 |  | Yuri Phase 0 - DAS Internal Layout | Code: E0303 | INS | 400PV |  |  |  |  | STA | 10 |  |  | MFELE |  | 2022-09-02 | 2022-09-02
200883C-400-JSS-1640-5000 | [D] | 200883C | 400 | JSS | 1640 | 5000 |  | 40 |  | Yuri Phase 0 - Specification for Transformers - Inverters | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-28 | 2022-08-28 | 2022-08-28 | Completed
200883C-400-JSS-1673-5000 | [D] | 200883C | 400 | JSS | 1673 | 5000 |  | 40 |  | Yuri Phase 0 - Specification for BESS | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-08-29 | In Progress
200883C-400-NM-1600-5000 | [D] | 200883C | 400 | NM | 1600 | 5000 |  | 40 |  | Yuri Phase 0 - Hourly Generation Data | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-08-29 | In Progress
200883C-400-NM-5000 | [D] | 200883C | 400 | NM |  | 5000 |  | 40 |  | Yuri Phase 0 - PV Array Xx - Set out Points | Code: E0303 | MEC | 400PV |  |  |  |  | IFR | 70 |  |  | MFMEC | 2022-08-09 | 2022-08-09 | 2022-09-01 | In Progress
200883C-400-RT-1600-5000 | [D] | 200883C | 400 | RT | 1600 | 5000 |  | 320 |  | Yuri Phase 0 - Power System Studies (loadflow - short circuit - transient stability) | Code: E0303 | ELE | 400PV |  |  |  |  | IFC | 100 |  |  | MFELE | 2022-09-13 | 2022-09-13 | 2022-09-13 | In Progress
200883C-400-RT-1600-5001 | [D] | 200883C | 400 | RT | 1600 | 5001 |  | 120 |  | Yuri Phase 0 - Harmonic Analysis | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-08-31 | 2022-08-31 | 2022-08-31 | In Progress
200883C-400-RT-1600-5004 | [D] | 200883C | 400 | RT | 1600 | 5004 |  | 40 |  | Yuri Phase 0 - Earthing And Lightning Report - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | STA | 10 |  |  | MFELE | 2022-08-30 | 2022-08-30 | 2022-08-30 | In Progress
200883C-400-RT-1600-5006 | [D] | 200883C | 400 | RT | 1600 | 5006 |  | 40 |  | Yuri Phase 0 - Insulation Coordination Report - PV area | Code: E0303 | ELE | 400PV |  |  |  |  | IFR | 70 |  |  | MFELE | 2022-08-29 | 2022-08-29 | 2022-08-29 | On Hold
200883C-400-RT-5000 | [D] | 200883C | 400 | RT |  | 5000 |  | 80 |  | Yuri Phase 0 - Certified Plant Certificates - Reports | Code: E0303 | MEC | 400PV |  |  |  |  | STA | 10 |  |  | MFMEC | 2022-08-31 | 2022-08-31 | 2022-08-31