## Division of Responsibility(DoR)
Division of Responsibility - Unincorarated JV (SEPD and Monford)
Section | Description | SEPD | Monford | Consortium Resource | Meeting Minutes 20-04-23
| Participating Interest | 51% | 49%
A | ENGINEERING
A1 | SOLAR FARM DESIGN
| Concept, detail and IFC design - Solar Farm | X
| Concept, detail and IFC design - SCADA System |  | X
A2 | DOCUMENTATION
A2.1 | INSTALLATION AND COMMISSIONING DOCUMENTS
| Installation documentation for respective scope | X | X
| Commissioning documents for respective scope | X | X
A2.2 | MANUALS FOR COMMERCIAL OPERATION
| Operation and maintenance manuals on digital media | X | X
| Operation and maintenance manuals as hard copy | X | X
B | SUPPLY OF SOLAR FARM PLANT AND SPARE PARTS
B1 | SOLAR FARM KEY EQUIPMENT
B1.1 | PV PANEL
| PV Panel supply | X
| MC4 Connector supply | X
B1.2 | FIXED MOUNTING STRUCTURE
| Upper Structure | X
| Pile | X
B1.3 | POWER CONVERSION SYSTEM
| Inverter | X
| Inverter transformer | X
| Low voltage cabinet | X
| RMU | X
| Communication cabinet | X
B2 | SOLAR FARM BALANCE OF SYSTEMS
B2.1 | DC Balance of System
| DC combiner box - including disconnects, over current protection, busbar | X
| DC cable and MC4 connector - PV panel to combiner box | X
| DC main cables - DC combiner box to inverters | X
B2.2 | MEDIUM VOLTAGE SYSTEM
| MV cable | X
B2.3 | METEOROLOGICAL STATION
| Met station | X
B2.4 | PLANT EARTHING
| Earthing conductor | X
| Earthing cable | X
B2.5 | CONTROL SYSTEM
| SCADA software and hardware |  | X
| Plant power controllor (PPC) |  | X
| Plant control cables |  | X
| Integration with various subsystem like |  | X
| Communications cable |  | X
| Optical fiber |  | X
| Power quality meter |  | X
| Cyber Security - Hardware & Software |  | X
| Revenue measuring system |  | X
| DC system |  | X
B2.6 | SECURITY SYSTEM - CCTV
| Camera |  | X
| Monitor system |  | X
B2.7 | PERMANENT SITE AMENITIES
| Buildings | X
| Water suply and storage | X
B2.8 | HARMONIC FILTER
Harmonic study
| Harmonic filter if required | X
C | CONSTRUCTION
C1 | CIVIL
| Clearing and grubbing |  | X
| Permanent security fencing |  | X
| Roadworks |  | X
| MV pads and foundation |  | X
| Drainage |  | X
| Earthworks |  | X
| Erosion and sediment control |  | X
C2 | MECHANICAL
| Piling |  | X
| Mounting structure installation |  | X
| PV panel installation |  | X
C3 | ELECTRICAL
| Trench and backfill |  | X
| PV panel connection |  | X
| DC harness and termination |  | X
| DC main cabling and termination |  | X
| MV cabling and termination |  | X
| Communication cabling and termination |  | X
| FO cabling and termination |  | X
| PCS installation |  | X
| SCADA installation |  | X
| CCTV installation |  | X
| Site Amenities installation |  | X
D | TRANSPORTATION OF ITEMS SUPPLIED
D1 | MATERIAL AND SERVICES FOR LOGISTICS
| Packing and marking of equipment as per Customer QA requirements | X
| Arranging of shipping line/freight forwarder and export related clearances | X
| Notification to buyer of time and place of delivery of equipment | X
| Loading and transportation of equipment as per IEC safety standard till place of delivery | X
| Transport insurance from place of manufacturing to place of delivery | X
| Preparation of origin country documents required for destination customs clearance as per requirements of end customer | X
| Import clearance of goods | X
| Import taxes and duties as applicable | X
D2 | SITE TRANSPORT
| Transport route preparation (if required) | X
| Transport permit assistance | X
| Loading of equipment/containers on truck from customs | X
| Transportation of equipment/containers from port of destination to site | X
| Transport insurance from port of destination to project site | X
| Unloading of equipment/containers at project site |  | X
| Storage and Handling of the supplied equipments |  | X
E | TAXES, DUTIES, PERMITS AND INSURANCE
E1 | TAXES AND DUTIES (for respective scope)
| GST tax and local taxes | X | X
| Other taxes / duties (if required) | X | X
E2 | PERMITS
| Construction permitting, approvals, stamps, etcetera |  | X
| Building permit |  | X
| Water permit |  | X
| Environmental permit |  | X
| Permitting procedures |  | X
| R0, R1 and R2 testing and approvals from AMEO & Transmission Network Service Provider (TNSP) | X
E3 | INSURANCE
| Professional indemnity insurance | X | X
| General liability and product liability insurance + marine & logistics insurance if required | X | X
| Workers' compensation and employer's liability insurance for respective scope | X | X
F | CONSTRUCTION MANAGEMENT
F1 | CONSTRUCTION MANAGEMENT FOR SOLAR FARM
| Site / construction management |  | X
| Construction supervisors |  | X
F2 | TEMPORARY INSTALLATION AND ARRANGEMENTS
F2.1 | ROADS AND WORKING AREA
| Temporary access road to site (if required) |  | X
| Temporary roads at site (if required) |  | X
| Preparing of working areas |  | X
| Designating storage area |  | X
| Preparation of temporary storage enclosure if needed |  | X
F2.2 | UTILITIES
| Site office & Labour Colony if any |  | X
| Internet connection to site during construction |  | X
| Electricity consumption during construction |  | X
| Water consumption during construction |  | X
| Illumination during construction |  | X
| Workers social facility |  | X
| Construction equipment and tools |  | X
| Fuel supply for construction equipment usage |  | X
F2.3 | SECURITY
| Security of supplied equipment |  | X
| Temporary fencing during construction (if required) |  | X
| Security for personnel transport between site and accommodation |  | X
F3 | HEALTH SAFETY AND ENVIRONMENT
| Fire protection during construction and commissioning work on the site |  | X
| Medical evacuation plans of seriously injured persons |  | X
| Chemical storage |  | X
| Hygiene and safe canteen and food preparation (when on-site canteen) |  | X
| Work permitting at site |  | X
| Locking and tagging procedures |  | X
| Waste material handling |  | X
F4 | QUALITY CONTROL AND ASSURANCE
F4.1 | MATERIAL QUALITY
| Manufacturing Quality assurance plan for respective scope | X | X
| In process quality inspection and Factory acceptance test | X | X
F4.2 | SITE CONSTRUCTION QUALITY
| Site Quality plan |  | X
| Supervision and acceptance of job work |  | X
G | COMMISSIONING
G1 | COMMISSIONING FOR SOLAR FARM
| Pre-commissioning |  | X | Both the teams should jointly support eachother in commissioning smoothly
| Integrated commissioning | X | X | Both the teams should jointly support eachother in commissioning smoothly