## ITC
Inspection Test Checklist (ITC) : Fence Gate Installation
Project | Yuri EPC
Client | Engie
Project Number | 1096-01
Document Number | 1096-01-MFG-QLT-ITC-CIV-0035 Fence Gate Installation
Area Inspected
Lot Number
Date
SIGN-OFF
Item,# | Item Title |  | Compliance (Yes/No/N/A) | Date Complete | Sub-contractor representative: (If applicable) | Monford Group Representative | Optional Witness | Comments
1 | MATERIALS CONFORMITY
1.1 | Tthe material used is in accordance with spec and with AS1725.1 |  | Yes/No/N/A
2 | Fence location
2.1 | The layout of the fence is clearly marked in accordance with the drawings |  | Yes/No/N/A
2.2 | Post Marking Out: The distance between fence posts according to Specs. |  | Yes/No/N/A
3 | Installation
3.1 | Installation – Tensile Wire & Bracing Strut Bottom, Middle and Top wire secured and tensioned correctly. Bracing Strut clamp installed at reinforcement post as per specs below top twist mesh. Bracing strut installed at Reinforcement panel, ends and corners. Chain link wire will be hung on the strainers and tensioned. Clamp Installed. |  | Yes/No/N/A
3.2 | Installation – Twist Mesh & Barbed Wire Twist mesh is fastened and tensioned correctly with clips and wiring. Barbed wire been fastened and properly tensioned and fixed to the fence posts with clips, clamps and fitting elements. Twist wire (Diamond mesh) is properly tensioned and fixed to the fence posts with steel wire and fitting elements. Barbed wire are installed in accordance with AS and secure with wire. |  | Yes/No/N/A
3.3 | Gates sizing to be correct as per approved design |  | Yes/No/N/A
3.4 | All welds shall be painted with two coats of approved zinc rich paint |  | Yes/No/N/A
3.5 | Height of gate in line with height of fence, Confirmation required. |  | Yes/No/N/A
3.6 | Galvanized steel post caps fitted |  | Yes/No/N/A
3.7 | Gate latches, stops, keepers & hinges fitted |  | Yes/No/N/A
3.8 | Locking mechanism fitted to Gate |  | Yes/No/N/A
3.9 | Earthing Cable installed at correct location |  | Yes/No/N/A
3.1 | Compression lug is secured according to specs. |  | Yes/No/N/A
3.11 | Clean posts on completion |  | Yes/No/N/A
3.12 | Chains have been provided to prevent gates from swinging |  | Yes/No/N/A
General Notes / Remedial Actions
|  | Name |  |  | Title |  | Signature |  | Date
COMPILED BY
ACCEPTED BY MONFORD GROUP