## Risk Assessment Scope
Project Name | Yuri Project Phase 0
Project Number | 1096-01
Project Manager | Brian Rafferty
Client | Engie
Start Date
CRAW Date | 2022-09-02
CRAW Facilitator
Scope of Works
Risk Workshop (CRAW) Attendees
Name | Company | Position
Tayah Thornton | Monford | HSEQ Manager
Brian Rafferty | Monford | Project Manager

## Risk Matrix
Risk Matrix
Risk assessment is the process of assessing all of the safety and environmental risks associated with each of the hazards identified during the hazard identification process. All safety and environmental aspects are identified and addressed through this risk assessment process. Each aspect is assessed based on the criteria set out in steps 1, 2 and 3 below and the inherent risk and significance level is determined.
In assessing the risks, four essential steps are taken using the following criteria:
STEP 1:
Determine the severity of the potential consequences using the consequence severity table below.
STEP 2:
Determine the probability or likelihood of an incident occurring using the likelihood table below.
STEP 2:
STEP 3:
Assess the risk using the risk assessment matrix below.
HIERARCHY OF CONTROLS
| STEP 4: | The hierarchy of controls shall be used at all times when implementing controls to eliminate a hazard or reduce the risk of a hazard that causes loss to Monford. A number of controls described in the hierarchy of controls may be required to control the risk(s) to a tolerable level.
Determine the level of investigation required using the risk matrix table below.
Risk assessment involves examining and evaluating the likelihood and severity (or consequence) of the potential outcomes to prioritise risks for control.

## General Risks
1096-01 Yuri
Activity |  |  | Consequences | Risk | Assessment (before controls) |  |  | Controls | Hierarchy of Control | Assessment (Residual Risk)
Task | Hazard | Critical Risk Icon |  |  | Likelihood | Consequence | Rank |  |  | Likelihood | Consequence | Rank
Project Start Up
Recruitment and selection of project personnel and subcontractors / suppliers | Incorrect / unsuitable selection of personnel for job and works Persons under the influence of drugs and alcohol Persons not suited to the Project environment People unfit for the task |  | Possibility of employees sustaining injury due to poor health, performance or unfamiliarity with Project environmental conditions, unfamiliarity with scope of works approved work methodologies. | Safety | Possible | Major | 2 | Work Methodologies for high risk activities developed by competent and experienced personnel to suit scope of works (Engineering, Project Management, HSE and Works Supervisors) Implementation of Monfords safety systems Subcontractor Work Methodologies to be submitted and pre-approved by the Monford prior to subcontractor mobilisation to site OHS-P-022 Fitness for Work Policy Safety Management Plan PRO-F-008 Subcontractor Pre-Award Evaluation PRO-F-005 Supplier self audit questionnaire | Administration | Unlikely | Major | 12
SWMS and methodologies | Not all hazards captured and assessed Inadequate or incorrect controls nominated |  | Not capturing all hazards and correct controls to be implemented for scope of works in SWMS Developed (draft) risk assessments not complying with Monford standards and requirements | Safety | Possible | Major | 4 | Work Methodologies developed by competent and experienced personnel (Engineering, Project Management, HSE and Works Supervisors) Work Methodologies developed to suit scope of works and in accordance with site requirements. Subcontractor Work Methodologies to be submitted and pre-approved by Monford Project Management prior to subcontractor mobilisation to site SWMS development by subcontractor group and supervisor for specific scope of works Risk Management Training package rolled out to all site personnel Site specific inductions SWMS to be developed by experienced and competent personnel Monford supervisors to approve s SWMS prior to works commencing Safety Management Plan CRAW Risk Management Plan Environment Management Plan Hazard Identification and Risk Management Procedure | Administration | Unlikely | Major | 12
Pre-mobilisation training | Inexperienced workers Incompetent staff Unqualified Personnel |  | Non-competent personnel. Construction schedule delays Unable to mobilise personnel to site. | Safety | Possible | Minor | 15 | All personnel to be approved through the Monford Mobilisation Process to be suitably trained and competent All site personnel to complete Monford General Induction and site specific induction prior to commencing work | Administration | Rare | Minor | 23
Hot Weather conditions for work | Extreme heat causing heat stress - dehydration - acclimatising to conditions |  | Extreme Weather conditions | Safety | Possible | Major | 8 | Daily weather forecast to be included in Site Pre-start meeting information Monford site induction and orientation program to include Heat Stress awareness Scheduled training on heat stress and management through the weekly toolbox training program Water bottle and potable cool drinking water to be provided onsite Monitoring and encouragement to maintain adequate fluids regularly communicated at daily pre-start meetings Hard hat, shade brims and sunscreen provided for use onsite Emergency Response Management Plan | Administration | Unlikely | Major | 12
Bush fire in region of site or camp | Western Australian climate Accidental ignition from hot works Accidental ignition by lightning strike |  | Loss of Production Danger to site / camp based personnel Damage to Camp / Site facilities Personal injury / death | Environmental | Possible | Major | 8 | Fire extinguisher - 6 monthly tag / tested & maintained in register Signage Area to be clear of all combustible materials wherever possible before hot works commence Hot works spotter if required Hot works permitting system to be established Emergency Response Management Plan | Administration | Unlikely | Major | 12
Cyclone and flooding | Not prepared for cyclone and flooding Cyclonic weather events Flooding onsite Slips trips and falls Road flooding Lightning strikes High winds |  | Loss of Production Danger to site / camp based personnel Airborne items Loss of onsite services Damage to onsite facilities Personal injury / death | Environmental | Unlikely | Major | 12 | Monford induction and orientation program to address project cyclone management plan Check BOM for weather forecasts prior to travel Contact local authorities for updated report on road conditions (roads open / closed, flooded, etc.) Site alerts / notices posted on notice boards Drive to site rules Drive to road conditions The Registered Manager (RM) for the project will be responsible for the decision as to when to evacuate the camp site in the event of a cyclone or other extreme weather event threatening the site Emergency Response Management Plan | Administration | Rare | Major | 16
Project Mobilisation
Managing the risk of COVID-19 Pandemic impacting the Project | Potential transmission of COVID-19 amongst personnel on site |  | Personnel travelling to site from a government determined hotspot Shared amenities at site compound, whole of site prestart meetings, group inductions, & management meetings Transmission of COVID-19 from infected person to site personnel |  | Possible | Major | 2 | • Monford project COVID 19 Mgmt plan established and communicated. • COVID 19 declaration forms to completed & approved prior to site access • RTW interviews with individuals verifying no symptoms of covid 19 • workers / Visitor inducted in COVID-19 segregation on arrival, temperature test to be conducted if any suspisions, and mask use if requested to do so • Monford to clean/sanitize site compound amenities including all hard surfaces •ongoing update and comms of covid 19 mgmt performed by Monford • site compound social distancing/segregation established / maintained. |  | Possible | Moderate | 13
Safety Equipment and supplies | No / Insufficient PPE available Incorrect PPE available |  | Injury Delay to schedule Inability to complete task safely | Safety | Likely | Moderate | 9 | • PPE requirements communicated to all internal and external personnel for site works • Construction site supervisor to ensure all personnel wear the required PPE on site • Sufficient stock for site required PPE available • PPE clothing as per Monford standard to be worn as a minimum to enter site • Employee Relations & Information Handbook • Clothing - AS 2919-1987 • Gloves - AS 2161-1978 • Glasses tinted / clear - AS/NZS 1337.1:2010
Plant and equipment compliance | Sub-standard equipment being mobilised to site Personal getting injured from equipment failure Hydrocarbon leaks Foreign flora being brought to site Delays in production |  | Plant and equipment not compliant to standards and requirements Potential injury to personnel Equipment Damage Project delay | Safety / Environment | Possible | Moderate | 13 | Pre-mobilisation inspections and completion of site approval documentation for all plant and equipment Removal of mud, soil and other debris carrying foreign weeds prior to transportation to site Subcontractors and suppliers to be provided with standards and requirements (Subcontractor Starter Pack) Plant and equipment compliant to Legislation and Australian Standards On-line Plant Assessor system to be used for risk assessment of all plant and equipment Current quarterly tagging of tools and equipment completed prior to transport to site Scheduled maintenance of plant and equipment in accordance with manufacturer or supplier specifications Safety Management Plan PL-F-003 Plant Inspection and service sheet | Engineering | Unlikely | Moderate | 17
Project team readiness | Rushed and taking short cuts. Unfamiliar with new site environment and site rules Not confident in tasks Remote area |  | • Potential Injury to Personnel • Lack of quality in works being completed. • Project Delays | Safety | Likely | Moderate | 9 | • Project planning, scheduling, and communication • Comprehensive Induction process • Employee Relations & Information Handbook • Site General or Short-term induction
Driving to site / journey management | Employees driving to site / on site have potential to be involved in collisions caused by possible fatigue, inattention poor road conditions, weather conditions, getting lost or striking fauna Missing driver incident |  | Non-compliance - Project specific management plans, rules and procedures Non-competent and inexperienced drivers Fitness for work issues - alcohol and other drugs Employee lost or injured on route to site Risk of employee being injured or sick | Safety / Community | Possible | Major | 8 | Journey management and map to site Licenced and competent drivers Fatigue management. Pre-start check of vehicles prior to departure Mobilise through the Monford Mobilisation Process Minimise driving at night Abide by all signage and speed limits. Working hours, including travel restricted to a maximum of 12 hours, door to door For any employee due onsite who does not arrive within an expected timeframe, Monford will initiate a plan to locate the missing person. OHS-PL-002 Journey Management Plan OHS-F-009 Journey management form OHS-F-083 Individual Fatigue Self Assessment shall be used for DIDO personnel | Administration | Unlikely | Major | 12
Site induction and orientation | New employees may be unfamiliar with site conditions and work procedures |  | Project specific management plans not followed | Safety | Possible | Moderate | 13 | All personal to complete Monford induction at earliest possible time upon arrival to site and prior to commencing any work All workers awaiting induction shall be escorted onsite at all times by a fully inducted employee Buddy system to be implemented for new employees OHS-PL-007 Health and Safety Management Plan HR-POL-022 Induction Policy OHS-F-011 Induction Checklist | Administration | Unlikely | Moderate | 17
Flora and fauna onsite | Flora / fauna contact - resting in unused plant equipment and/or materials Snake bites, bee, spider, wasp stings and insect bites. |  | Inadequate inspection of work area before commencing task | Environmental | Possible | Moderate | 13 | Pre-inspection of plant and equipment prior to handling and use Flora / fauna management and protection training for project personnel as a toolbox training topic Trained snake handlers and St. John snake bite kits available onsite with first aid kits Insect repellent provided and face nets used if required Insect sting treatment available in onsite first aid kits Nominated and trained first aiders. ambulance and trained medic on site. Report all injured or stranded wildlife to site HSE Advisor. OHS-PL-003 Environmental Management Plan ENV-R-001 Environmetal Aspects and Impact Register | Administration | Unlikely | Moderate | 17
Cultural heritage site breach | Employees accidentally entering areas of cultural heritage |  | Inadequate delineation Inadequate site management | Community | Possible | Major | 8 | Delineate and fence off all cultural heritage sites identified onsite A signed Ground Disturbance Permit (GDP) must be approved prior to any works being carried out If indigenous artefacts are identified cease works and notify the site HSE Advisors and Monford Project Manager. Cultural Heritage requirements to be communicated in the induction . Performance Standards Safety Management Plan Environmental Management Plan ENV-R-001 Environmetal Aspects and Impact Register | Engineering | Unlikely | Major | 12
Site Establishment
Interface with other contractors onsite | Employees from other contractors entering work areas Access requirements for other contractors and Client to be maintained where required |  | Inadequate site management Inadequate site delineation | Safety | Possible | Major | 8 | Weekly subcontractor supervisor interface meetings coordinated by Monford Site alerts / notices to notify of any change in conditions. Work in accordance with barricading and signage procedures. Daily pre-start meetings with contractor interface issues communicated to all site personnel Hard Barricading, signage and information tags to separate construction site areas from general access by other contractors and operators Clear delineation of entry points to work areas Area entry call up requirements and signage for radio channel requirements Safety Management Plan OHS-P-002 Communication and Consultation | Engineering | Unlikely | Major | 12
Interface with community (neighbours & general public) | Interaction and complaints |  | Causes: - Lack of communication with Neighbours - Failure to communicate ER plans where there is a potential for impact to Neighbours - Operations and construction Event: Lack of community engagement leads to community issues or complaints not handled on time resulting in serious complaints with reputational impact Consequence: - Public and staff injury - Legal issues | Community | Possible | Moderate | 13 | Procedural: - Perimeter fencing and secure entry gates to control access to the construction site. - Dedicated pedestrian walkways established as part of the site Vehicle Movement Plan. - Traffic Management plan to identify any suitable 'lead in' warning signage for traffic movements into and out of the Construction site. - Induction process covers visitors entering site. - Visitors/ clients are to be under site escort by a fully inducted project representative at all times whilst on site. - Consultation & communication program (e.g. traffic mgmt for deliveries to the site). - PC Signage with emergency contact details displayed in prominent positions. - Construction Site Warning Signage displayed. - Landowner gates to be locked at all times ‐ communicated at induction. - Where there is the potential for neighbours / other stakeholders to be impacted by emergency situations, ensure that they are briefed on the project specific emergency response procedures. - Regulated work periods: Mon to Fri -6:30 to 18:30, Sat 8 - 18:00, Sun 8 - 18:00. - Complaints handling process established for project. - Toolbox talks to reinforce procedures for responding to approaches from members of the public. - Engineers and Supervisors to provide information to suppliers etc in relation to the restrictions on site deliveries. Active: - Regular communication with community Passive: - N/A | Administration | Unlikely | Minor | 21
Establish lay down and site boundaries | Interaction with other contractors |  | Inadequate traffic management plan / design | Safety | Unlikely | Major | 12 | Weekly subcontractor interface meetings coordinated by Monford Site alerts / notices to notify of any change in conditions Daily pre-start meetings to include any contractor interface issues communicated to all site personnel Permit to work procedure Site traffic management plan Clear delineation of entry points to work areas Area entry call up requirements and signage for radio channel requirements Traffic Management plan Safety Management Plan | Engineering | Rare | Major | 16
Unauthorised site entry | Unauthorised personnel entering the construction area |  | Inadequate delineation and site security | Safety | Possible | Major | 8 | Hard Barricading, signage and information tags to separate construction site areas from general access by other contractors and operators All personnel to report to the Monford site office Dedicated entry and exit points for barricaded areas with call up contact signage at these points if required All visitors to complete visitor inductions, sign visitors book and be escorted at all times by fully inducted person Workers to sign onto SWMS when entering worksite and advise area supervisor Traffic Management plan Safety Management Plan Monford Induction Program | Engineering | Unlikely | Major | 12
Project Deliveries & Lifting Operations onsite
Deliveries to site | Plant / freight vehicles not escorted to site, collision, property damage Interface issues with other contractors Inadequate area for goods delivery |  | Inadequate delineation and site security Inadequate planning for future deliveries Out of hours arrivals | Safety | Unlikely | Major | 12 | Monford induction and orientation program Barricading, signage and area / site radio call ups Prepare laydown area and delivery route before all trucks arrive on site Clear signage information for all vehicles arriving onsite - to wait for escort Traffic management plan (TMP) Traffic control plans (TCP) Spotter training via toolbox meetings and spotter prompt sheet Spotters for reversing plant, or as required for traffic control Designated companies to be informed and issued with delivery driver information pack Communication with Monford on delivery schedule - expected time of arrivals Licensed and competent operators Safety Management Plan BAC sign in and short term induction required for drivers Logistics to do visual inspections of all loads upon arrival to site | Engineering | Rare | Major | 16
Loading of trucks / materials | Incompetent drivers / operators for loading activities Unlevelled ground Poor planning during loading, making unloading difficult |  | Unauthorised personnel Inexperienced operators Poor ground conditions Poor planning | Safety | Possible | Major | 8 | Competent and trained operators to complete loading Haulage companies are responsible for ensuring loads are placed on trailers in a way to ensure unloading can take place in a safe manner onsite, any loads deemed unsafe to unload will be rejected on site and sent back to their depot for re-arrangement of load Designated companies to be informed and issued with delivery driver information pack. BAC sign in and short term induction required for drivers Safety Management Plan | Administration | Unlikely | Major | 12
Unloading of trucks / materials | Incompetent drivers / operators for unloading activities Unauthorised site entry - interaction with traffic - unapproved vehicles, plant and dangerous goods Unlevelled ground |  | Unauthorised personnel Inexperienced operators Poor ground conditions | Safety | Possible | Major | 8 | Site mobilisation process and Monford site specific induction Abide by all signage and speed limits, WA road rules Haulage company driver's responsibilities finishes at un-tying loads, from which point competent and trained operators are to complete unloading Designated companies to be informed and issued with delivery driver information pack BAC sign in and short term induction required for drivers. Safety Management Plan | Administration | Unlikely | Major | 12
Falling or movement of load during unloading activities | Items falling from a height when strapping removed Employees using unsafe practices to unload materials |  | Goods loaded on trailer incorrectly Goods moved during transport Incorrect work practices | Safety | Possible | Major | 8 | Inspection of loads on arrival to site for movement during transport Truck drivers to undo restraints and vacate area (over centre binders shall not be used onsite). Driver to move out of lift zone and remain in designated area once restraints are removed and rigger starts task. VOC’d operators to unload plant and equipment Inspection of lifting equipment prior to lift Riggers / Doggers to control lift and use appropriate load restraints that can be accessed from the ground Spotters to be used at all times while unloading / loading Correct capacity (SWL) equipment selected for the task Safe access and egress to delivery truck / trailer (side gates to be in place for edge protection - no standing / working on the back of trucks without adequate edge protection) Safety Management Plan | Engineering | Unlikely | Major | 12
Use of crane and/or forklift for loading / unloading goods, equipment, buildings, sea-containers | Non-compliant lifting gear or equipment used for lifts. Load exceeding SWL of crane (80% over lifting capacity or loads over 20T) Faulty or damaged lifting equipment. |  | Inadequate inspections Out of date lifting equipment in use Non qualified VOC'd operators | Safety | Unlikely | Major | 12 | Inspect crane on arrival to site. Registration and inspection paperwork shall be provided for the crane. Mobile Equipment Checklist and report to be completed and approved before use. Weed and Seed Inspection Report to be completed before mobilising to site. Weed Hygiene Certificate required prior to operating. All equipment to be inspected and tagged quarterly Correct crane / forklift size for lifts Daily pre-start checks and log book entries Site supervision, SWMS Planning of un-loading tasks Designated unloading area's only to be used VOC operators and verified by challenge testing Barricading to have dedicated entry and exit points Crane lift study / plan conducted (if over 20T or above 80% SWL) Inspection of lifting equipment prior to lift and all lifting gear to be in current test and tag(RGBY) and lifting register to be maintained Safety Management Plan | Administration | Rare | Major | 16
| Unsuitable ground conditions |  | Inadequate lift planning Inexperienced crane operators | Safety | Possible | Major | 8 | Inspect crane on arrival to site. Registration and inspection paperwork shall be provided for the crane. Mobile Equipment Checklist and report to be completed and approved before use. Ground compaction to be assessed for safe use of outriggers Designated unloading area's only to be used Crane lift study / plan conducted (if over 20T or above 80% SWL) Correct capacity crane / forklift for tasks OHS-PL-007 Health and Safety Management Plan OHS-F-025 Lift evaluation form OHS-P-005 Cranage and Lifting | Administration | Unlikely | Major | 12
Telehandler operations | Overturning or collapse of boom |  | Inexperienced operator Poor ground conditions Poor Maintenance regime | Safety | Unlikely | Major | 12 | Prepared level ground areas to be used for lifting operations Barricading, signage and spotters in place SWMS Qualified and VOC'd operators and dogmen / riggers Lifting equipment inspected and tagged prior to mobilisation to site and quarterly onsite Correct capacity Telehandler selected for task and taking into account reach, elevation and weight Daily pre-start checks of plant and equipment by qualified personnel Plant & rigging register to be maintained onsite (certified) Safety Management Plan | Administration | Rare | Major | 16
Dogger / rigger activities during lifting operations | Poor Communications between operator and rigger / dogger Unauthorised personal entering lifting zone Personnel walking underneath suspended loads |  | Inadequate barricading and signage around lifting zone Poor pre-lift planning between dogger and operator | Safety | Possible | Major | 8 | Dogger / rigger to be in clear view of operators at all times All movements to be communicated between operator and dogger / rigger via hand signals or two-way radio communications as appropriate Minimum ratio of one dogger / rigger to be used to one crane operator Dogger / Rigger to complete SWMS, including: surroundings; emergency escape routes crush zones and pinch points & line of fire hazards Work crews to ensure that area is not accessed by unauthorised personnel. Permission must be requested from the rigger to enter the immediate lift zone. No personnel to be under a suspended load at any time Barricading to have signposted entry and exit points VOC operators and verified by challenge testing | Administration | Unlikely | Major | 12
Manual handling | Back or muscles strains |  | Poor technique used during lifting Employees lifting objects above capability Poor planning in team lifts | Safety | Possible | Moderate | 13 | Mechanical lifting aids used wherever possible Team lifts where required Rigorous pre-placement medicals and management of pre-existing conditions. Manual handling training via Monford induction and toolbox meetings Safety Management Plan | Engineering | Unlikely | Moderate | 17
Site Preparation and Earthworks
Establish permanent survey and set out contracted works | Faulty / non-calibrated equipment - incorrect AS-Built data |  | Poor asset management and record keeping | Safety / Community | Possible | Minor | 18 | Site mobilisation process Pre-start checks of equipment by qualified and competent surveyors Calibrated survey equipment is used Viewpoint is used to maintain all details of the survey equipment | Administration | Unlikely | Minor | 21
Weed and seed management | Vehicle and plant hygiene - introduction of noxious weeds |  | Vehicles and plant not being adequately cleaned prior to being transported to site | Environmental | Possible | Moderate | 13 | Removal of mud, soil and other debris carrying foreign weeds prior to mobilisation to site Weed Hygiene Certificate required prior to operating. Pre-mobilisation mechanical inspections and completion of site approval documentation for all plant and equipment Security inspections prior to site entry Work site inspections to monitor environment (i.e. identify and action noxious weeds identified on site) Management of soil resources, (i.e. segregation of top soils and sub soils) Environmental Management Plan | Administration | Unlikely | Moderate | 17
Earthworks, plant and equipment compliance and operation | Interaction with traffic & pedestrians Accidents involving plant Contact with services or equipment |  | Incompetent and inexperienced drivers or operators Unapproved vehicles and plant | Safety | Possible | Major | 8 | Site mobilisation process and induction to ensure all operators are fully competent to preform tasks. VOC, high risk license is required for all operators. Operators to be fully aware of the procedure for operating the item of plant or equipment. Monford to ensure all plant and equipment suitable, fully serviced and in good working order. Monford to ensure work areas is fully secure and no unauthorised entry is possible On-line Plant Assessor system to be used for risk assessment of all plant and equipment. Spotters for reversing plant, or where required for traffic control. Segregate plant and pedestrians. Make positive visual contact with the operator prior to approaching TMP set up and complied with on site. All vehicles fitted with beacon and reversing alarms. All mobile plant to be fitted with ROPS and FOPS (safety in design). Speed limits adhered too. BAC testing daily prior to commencement of work. Safety Management Plan CRAW document | Engineering | Unlikely | Major | 12
Earthworks, plant and equipment | Environmental risk of leaks and broken fluid lines |  | Unapproved vehicles and plant Inadequate maintenance records | Environmental | Possible | Moderate | 13 | Monford to ensure all plant and equipment is suitable, fully serviced and in good working order. Monford to maintain all service records on Sharepoint Subcontractors to provide all current maintenance and services records for plant and equipment on site. Spill kits to be available on site to deal with spills. No use of mobile phones on site. Traffic management plan to be developed. Designate haul routes Make positive contact with Operator before encroaching within 50m of the machine. Use of 2 way tetra radios. | Administration | Unlikely | Moderate | 17
Compaction of earthworks | Incorrect compaction density resulting in ongoing quality issues |  | Inadequate workmanship Inadequate quality fill material Inadequate testing compliance | Safety / Environment | Possible | Moderate | 13 | Supervision to ensure correct placement of material Compaction records to be recorded in accordance with QA requirements Max. 300mm layer lifts. Conduct initial tests on compaction of material, to develop method spec. All ITP's must be signed off. Daily Inspections must be conducted each day by a competent person. Quality Management Plan Safety Management Plan Q-F-015 Inspection and test plan template | Engineering | Unlikely | Moderate | 17
Earthworks exclusion zone | Unauthorised work area entry |  | Inadequate delineation and barricading | Safety | Possible | Major | 8 | 50m exclusion zone from extended boom or buckets Hard barricade / signage. Excavator bucket lock pin to be used at all times All excavators to be operating with spotter in place Toolbox topic; beware the shadow Excavation permit to include work area exclusion requirements. Safety Management Plan | Administration | Unlikely | Major | 12
Open trenches onsite | Personnel / plant - equipment falling / slipping into open trenches due to unstable ground conditions Fauna entering / falling into trenches |  | Excavated trenches not barricaded correctly Edge of trenches not suitable or finished to prevent loose material falling in | Safety | Possible | Moderate | 13 | Safe access and egress to trenches (4:1 ratio ramps) Excavations > 1.5 meters to be benched or shored Barricading to fully enclose excavations Barricade shall be one 1m away from edge of excavation Information tags on barricades Barricade around trafficable areas to have night / strobe lights. Daily recorded inspection required on excavations >1.5 by the subject matter expert (Engineer). Area's of open trenches must be communicated to all relevant persons at Daily Prestart Meeting. Safety Management Plan | Engineering | Unlikely | Moderate | 17
Service Installation
Installation of in-ground services / service pits / conduits on site | Existing services not identified, specifically electrical, sewerage and water services and communication services Working in trenches Back and muscle strains from lifting |  | Permit requirements / procedural breaches | Safety | Possible | Major | 8 | Location of existing underground services prior to commencement - As Built - Dial Before You Dig - Site Plans Where underground services are known to exist erect signage to mark location of. Survey to mark / highlight with line marking paint all identified services Pot-holing and hand digging in vicinity of or suspected location of services Spotter to be in place and excavate by hand within 300mm of existing services Barricading around work area. Workers to use mechanical aid for any heavy or hard to lift piping materials Survey of all services installed in trenches prior to any backfilling beginning Ground Disturbance Permit required for all ground penetrations Safety Management Plan | Administration | Unlikely | Major | 12
Installation of building concrete supports | Back and muscles strains from employees trying to move / adjust concrete supports Vehicle / Pedestrian / Crane interaction |  | Employees not using mechanical aids for lifting Poor site delineation | Health | Possible | Catastrophic | 4 | Mechanical lifting aids used wherever possible - Crane and / or IT Loader Team lifts where required Hard barricade / signage All personnel to be approved through the Monford Project Mobilisation Process , suitable trained and competent Safety Management Plan | Engineering | Unlikely | Catastrophic | 7
Building Installation
Delivery of buildings and placement onto footings with crane | Incorrect loading of trucks (shifting of buildings) |  | Load incorrectly secured before transport Drivers not driving to road conditions | Safety | Possible | Major | 8 | Notification of any building damage load shifting during transit to be provided to Monford unloading assessment checklist to be completed by Supervision Safety Management Standards Safety Management Plan | Administration | Unlikely | Major | 12
| Incorrect positioning of truck or crane Load exceeding SWL of crane (80% over lifting capacity or loads over 20T) Unsuitable ground conditions |  | Poor pre-lifting plan Inadequate inspections Out of date lifting equipment in use Non qualified VOC'd operators Inexperienced crane operators | Safety | Possible | Major | 8 | Inspect crane on arrival to site. Registration and inspection paperwork shall be provided for the crane. Mobile Equipment Checklist and report to be completed and approved before use. Weed and Seed Inspection Report to be completed before mobilising to site. Weed Hygiene Certificate required prior to operating. All equipment to be inspected and tagged quarterly Correct crane / forklift size for lifts Daily pre-start checks and log book entries Site supervision, SWMS Planning of un-loading tasks Designated unloading area's only to be used Crane Targeted Inspections (HSE-TP-100-003) VOC operators and verified by challenge testing Barricading to have dedicated entry and exit points Crane lift study / plan conducted (if over 20T or above 80% SWL) Inspection of lifting equipment prior to lift OHS-P-005 Cranage and Lifting Safety Management Plan OHS-F-025 Lift evaluation form | Administration | Unlikely | Major | 12
| Stored energy |  | During transport | Safety | Possible | Major | 8 | Only truck driver to release binders after visual inspection and completion of unloading checklist Truck to be switched off and in gear with handbrake engaged Safety Management Plan | Administration | Unlikely | Major | 12
| Working at heights (access & egress to truck) |  | Poor work practices by employees Procedure breaches Risk of falling | Safety | Possible | Major | 8 | No working at height when unloading trucks No access to back of trucks without tray side protection Truck driver to be escorted and wait in crib room or designated area during loading / unloading, or wait inside cab Pre-slung / palletised loads where possible to remove the need for acess to the tray of vehicles / trailers Safety Management Plan | Administration | Unlikely | Major | 12
| Incorrect Building installation |  | Poor planning, lack of survey | Environmental / Community | Possible | Minor | 18 | Surveyor to have set out location for building to be installed Supervisor to review after building is located in position and surveyor to double check all corners Q-PL-001- Quality Plan ITP's | Administration | Unlikely | Minor | 21
Escavation works for dome shelter foundations including concrete pours | Equipment / worker / wildlife fall into excavation Delivery chute: strike personnel as it moves-injury. Manual handling - weight, balance, effort, loss of control, spillage, wasted concrete Chemical burns from contact with the skin |  | Injury to personnel / wildlife Plant / equipment damage Delivery chute: strike personnel as it moves-injury to personnel loss of control spillage wasted concrete chemical burns from contact with the skin |  | Unlikely | Major | 12 | Trenches demarcated if left open including use of barricading where identified Trenches backfilled as cable is laid Excavation edges demarcated Signage displayed around excavation edges Benching used to minimise fall height Pre-Start communications mobile plant fit for purpose / suitable for task. SWMS for activities Supervision UHF radio comms Positive communications maintained between operators Spotters for vehicle movements Vehicle and plant operators licensed, ticketed and verified competent mandatory & other PPE used as identified SWMS refers to Emergency Response Procedure and Emergency Plan established and communicated to all workers Clear away unnecessary materials from the area Pre activity work area inspection and approval for start Provide a well-defined, clear and smooth path for the barrows consider an adequate tip-off point. Assign the task to personnel of adequate strength and agility. Do not overload barrows. mandatory & other PPE used as identified Keep control of the chute at all times. Communicate with the driver. Driver to clean out chute at concrete plant not on site. | Engineering | Unlikely | Minor | 21
Connection of services to installed transportable offices & buildings | Damage / disruption to existing services |  | Poor workmanship Incorrect location of service pits | Community | Unlikely | Moderate | 17 | Survey to mark out services prior to installation Certified licensed electrician to complete all connections Certified licensed plumber to complete all connections All personnel to be approved through the Monford Project Mobilisation Process, be suitably trained and competent Quality Management Plan ITP's | Administration | Rare | Moderate | 20
Set up buildings for Complexing | Working at heights Weight of items on roof Incorrect use off PPE Untrained personnel |  | Unsecure scaffolding or work platform used Wind blowing unsecure items Working too close to edge - falls Dropped objects | Safety | Possible | Major | 8 | All work at heights equipment to be inspected prior to use, and tagged to indicate compliance Safe Work Method Statement for work at heights Drop Zone barricading, signage and information tags Workers to be hooked up to approved anchor point with fall restraint at all times where edge protection not in place Monford's Working at Heights procedure to be followed Training & Competency of workers to be confirmed Scaffolding erected by trained qualified and VOC'd personnel only Scaff-tag system to be used Daily visual inspections of scaff-tags by Supervisors Housekeeping on scaffold, tool bags, lanyards and buckets to be used - no loose items Work at Heights Permit required for all work at heights activities. Safety Management Plan | Engineering | Unlikely | Major | 12
Use of ladders / platform ladders | Unsafe access / egress to work areas - falls from ladders |  | Unstable ground conditions | Safety | Possible | Moderate | 13 | Ladders to be secured at top location point and extend 1m past landing / exit point Use mobile platform ladders on level ground only Platform ladders to have drop-down bar on working landing 3 points of contact to be used at all times All ladders used on site to be industrial rated - quarterly inspection - test / tag Working at heights permit and procedures to be followed OHS-F-010 - HSE Workplace Inspection Safety Management Plan | Administration | Unlikely | Moderate | 17
Working at heights activities | Falls |  | Exposed drop zones Poor employee behaviour Fall from height | Safety | Possible | Major | 8 | All work at heights equipment to be inspected prior to use, and tagged to indicate quarterly compliance requirements Working at heights permit SWP for all work at heights activities Work at heights training with current training status tracked on InTuition (valid for 2 years) Drop zone barricading and signage to be installed Working at heights rescue plan and rescue drills Edge protection installed where required Working at Heights permit and procedures to be followed Safety Management Plan | Engineering | Unlikely | Major | 12
Complexing buildings | Dropped objects Pinch Points |  | Poor housekeeping Line of fire injuries | Safety | Possible | Major | 8 | Buckets / containers for hand tools and materials Use of tool bags and lanyards as required SWMS Barricading and / or signage Spotter to be clear of drop zone at all time, and must ensure that entry is restricted at all times. Working at heights SWP Work at Heights Permit required for all work at heights activities. Working at Heights permit and procedures to be followed. Correct PPE for task OHS-PL-007 - Health and Safety Management Plan | Engineering | Unlikely | Major | 12
Building Commissioning
Electrical works - low voltage | Electricity Electric shock Electrocution Electrical burns |  | Incorrect isolation procedure used Untrained personnel and unauthorised Incorrect installation Contact with live wiring / damage to cabling Incorrect RCD's installation and usage Incorrect testing and commissioning procedure | Safety | Unlikely | Catastrophic | 7 | All electrical works to only be conducted by licenced / authorised electricians Electrical supervision to be licenced / authorised electrician Isolation of plant and equipment SWP for use of low voltage electrical equipment Use of industrial RCD's Use of physical locking isolation with personal lock 'Danger' tags Isolation / lock out training Electrical equipment quarterly (current) tested and tagged Insulated lead stands and hooks First Aiders (1:10 ratio) - name / contact details posted Electrical safety awareness and requirements training via toolbox meetings Safety Management Plan | Isolation | Rare | Catastrophic | 11
Electrical Equipment | Damaged equipment, Electric shock Electrocution |  | Electrical equipment not site compliant or to legislative requirements Poor management of equipment Incorrect procurement Damage to equipment due to poor workmanship | Safety | Unlikely | Major | 12 | All electrical works to only be conducted by licenced/ authorised electricians. Electrical supervision to all be licenced/ authorised electricians. Visual inspection of all equipment for damage and correct tagging quarterly requirements. Check all items comply with relevant standards Safety Management Plan | Administration | Rare | Major | 16
Electrical isolation | Electricity Electric shock Electrocution Electrical burns |  | Lock out and isolation procedures not correctly followed and implemented Unqualified personnel carrying out electrical isolations Human error | Safety | Unlikely | Major | 12 | Approved isolation officers Lock holder training Monford isolation permit and SWP Site compliant locks and lockout procedures Lock holder and permit training Isolation training for specific services (i.e. electrical) Isolations only by licenced / authorised electricians Safety Management Plan | Isolation | Rare | Major | 16
Setting up of water after installation on building | Incorrect connection of potable and grey water to buildings Contaminated water lines |  | Incorrect labelling to grey water and potable water piping | Safety / Environment | Unlikely | Minor | 21 | Certified licensed plumber to complete all connections All personnel to be approved through the Monford Project Mobilisation Process, be suitably trained and competent All piping to be labelled at each connection point Environmental Management Plan | Administration | Rare | Minor | 23
Plumbing Fitout - External Plumbing e.g. Potable water tanks | Heavy / Large (MC) Vehicle Movements Delivery interface with members of public Use of cranage on site Vehicle / Person interface Vehicle / structure, P and E or materials contact Unstable loads Failure of lifting device Failure of load restraints Incorrect rigging of loads Weather conditions Manual handling Personnel exposed to wildlife (snakes etc) Fatigue |  | Asset damage Personal injury dropped loads etc. damage to roadways / infrastructure Negative reputation Community complaints Project delays Environmental risks of weed transfer. | Safety / Environment | Likely | Major | 5 | • TMP produced and submitted by Monford with approved accredited Roadworks Traffic Manager • Prior consultation with haulers with regards to sire access, delivery and site requirements. • Crane lift studies completed prior to lifts being undertaken • Confirm personnel completing lifts are ticketed and VOC'd to complete works • Pre-delivery survey for heavy/ oversize load • Internal roads build to standard • trained & competent personnel • Minimise delays - review delivery schedule • Manage Delivery Times • SWMS for all activities • Use appropriate exit requirements as per TMP (Inbound vehicles have priority tight of way • Personnel delivering to site-- sign in at office - temp induction - BAC Test wear Hi Vis -hardhat- long sleeves- long pants --follow instruction from Monford Supervisor. • Clear Communication - use of radios etc. • plant pre starts • Spotter required at al times when trucks or plant reversing • Positive contact prior to approach / arrival with supervisor. • Where possible use designated access roads only • Confirm area of drop off prior to arrival • Designated / demarcated load and unloading areas • Clear Signage - Contact Numbers | Engineering | Possible | Moderate | 18
Major Hazard Facility Specifics
Fire Risk | Fire and/or explosion through incorrect storage, handling, labelling or mixing of chemicals Poor housekeeping Hot work being carried out without clearance Lack of fire fighting equipment Bushfire |  | Personal injury Delays to job Damage to equipment Environmental damage Damage to reputation IR issues | Safety / Environment | Possible | Major | 8 | Engineering - Welding habitats in place for works near chemical plant Plant designed with mechanical ventilation, extraction and atmospheric monitoring controls Restricted access to authorised personnel Purpose built storage areas for cylinders and compressed gases Chemical management process - SDS for chemicals, risk assessments, notifying DG holder of quantities Licensing agreements and requirements (YARA) Personal Protective Equipment • AS 1216 Class Labels for Dangerous Goods • AS 1940 The Storage and Handling of Flammable and Combustible Liquids • AS/NZS 1596 The Storage and Handling of LP Gas • AS 1345 Identification of the Contents of Pipes, Conduits and Ducts | Engineering | Unlikely | Major | 12
Working around chemical processing plant | Chemical exposure - acute (inhalation, absorption, ingestion) |  | Personal injury Damage to reputation IR issues | Safety / Environment |  |  |  | YARA 250-508-PRO-YPF-0009 Actions in the Event of a Chemical Release. YARA ERT will notify workers in the event of a chemical release that could impact MFG workers *Note - follow up on requirement to carry TAN Carriers for anyone accessing the TAN Plan (including delivery drivers) - clarify for perimiter works near TAN - Dangerous Goods Security Card (DGSC) for any TAN entry required (not forseeable) - Requirement for Police Clearance
Emergency escalation (third party activation) | Specific chemicals - Chlorine and Ammonia, Nitrogen Oxides Contractor does not understand YARA Emergency and Evacuation Procedures: |  | Personal injury Damage to reputation IR issues | Safety / Environment |  |  |  | YARA 250-508-PRO-YPF-0009 Actions in the Event of a Chemical Release. YARA ERT will notify workers in the event of a chemical release that could impact MFG workers Emergency Escalation Process Employees aware of Emergency requirements
Hazardous Areas (contraband items) | Use of items that are not intrinsically safe |  | Personal injury | Safety / Environment |  |  |  | Mobile phones: mobile phone use is limited to the Blue zone unless authorised (HESQ-YP-FRM-092-03).  Cameras: are prohibited to be bought onto site by all employees, visitors, contractors, and consultants. Cameras permitted to be used on site are those owned by Yara. Prior permission to use cameras must be obtained from the Plant Manager or Delegate (HESQ-YP-FRM-092-03).  Any device that may be used to strike, or could create, an open flame, arc or spark; some examples are matches, lighters (both portable and in vehicle lighters), explosives, firearms, fireworks. Items of clothing that can create static electricity such as nylon clothing are prohibited on site.  Electronic car keys are prohibited to be carried or used in the hazardous area.  Two Way Radio’s that are not intrinsically safe are prohibited from being taken into the hazardous area.  Mobile Equipment/vehicles are prohibited from entering the hazardous area – exception to this is emergency vehicles (Ambulance, Fire Tender, Western Australian Police). Vehicle access to site is to be in accordance with the Site Access Procedure. | Substitute
Site Storage and Housekeeping |  |  | Damage to equipment
Sewerage spills | Effluent exposure |  | Failure of pump station or sewer piping Faulty alarm and inadequate maintenance of storage tanks Overflow of temporary toilets | Environmental | Possible | Moderate | 13 | Spill response training Daily inspections of temporary facilities Plumbers/Plumbers apprentices repairing spills are to be immunised appropriately. Environmental Management Plan | Administration | Unlikely | Moderate | 17
Chemicals / hydrocarbon use, storage and handling | Exposure to chemicals Spills Incorrect or incompatible chemical and hydrocarbon storage |  | Inadequate or unsuitable storage containers used Inadequate management of risks associated with transport / storage and handling Incorrect PPE use leading to chemical exposure | Safety / Environment | Possible | Moderate | 13 | New chemical request form to be completed for approval prior to being brought onsite - SDS Chemical Risk Assessment for chemicals classed as hazardous or dangerous goods Specified PPE to be available to users All chemicals are managed using ChemAlert Approved Chemical Storage bunded (110% capacity of stored goods) areas with segregation of incompatible chemicals / flammable goods All chemicals / hydrocarbon storage vessels to be clearly labelled All chemical storage areas require sufficient ventilation Personnel will be trained via toolbox topic on the safe use of chemicals First aid / Eye station to be available Environmental Management Plan | Engineering | Unlikely | Moderate | 17
Chemical transportation / hydrocarbon use and refuelling | Exposure to chemicals Spills, Incorrect / incompatible chemicals / hydrocarbon storage Hydrocarbon spills |  | Poor work practice Incorrect storage containers Collision during transportation Poor refuelling techniques used | Safety / Environment | Possible | Moderate | 13 | All relevant licenses required to be completed Designated storage areas identified for non-hazardous and hazardous chemicals Hazardous chemical storage shall be restricted and stored in lockable cabinets All chemicals / hydrocarbon storage vessels to be clearly labelled Chemical handling, storage, segregation training First aid trained personnel (1:10 ratio) First aid Kits and Eye wash sya=tions to be available Mobile refuelling activities to be risk assessed SDS to be available Chemical Risk Assessment for chemicals classed as hazardous or dangerous goods Use specified PPE Approved Chemical Storage bunded (110% capacity of stored goods) areas with segregation of incompatible chemicals / flammable goods. Safety Management Plan | Administration | Unlikely | Moderate | 17
Waste management | Waste / rubbish littering onsite (potential for trapped wildlife ,wind blown rubbish, etc.) |  | Poor housekeeping Incorrect segregation and disposal of waste | Environmental | Possible | Minor | 18 | All rubbish to be disposed of in labelled designated skip bins to ensure effective segregation and compliance Separate hazardous waste skip bin provided onsite Waste skip bins shall be covered at all times or have hinged lids Bins emptied frequently Provision of recycling bins - reuse and recycle where ever possible Maintain housekeeping Waste management contractors compliant with local regulations and use government approved disposal sites Scheduled clean up site sessions Secondary containment provided to prevent contamination Environmental Management Plan | Administration | Unlikely | Minor | 21
Earthworks
Establish permanent survey and set out contracted works | Faulty / non-calibrated equipment - incorrect AS-Built data |  | Poor asset management and record keeping Facilities / Services placed in incorrect position / locaion Produced plans / As Builts incorrect | Environmental / Community | Possible | Minor | 18 | Site mobilisation process Pre-start checks of equipment by qualified and competent surveyors Calibrated survey equipment is used Viewpoint is used to maintain all details of the survey equipment | Administration | Unlikely | Major | 12
Unloading Plant / equipment | Personal Injury to person whilst unloading delivery trucks due to – Unprotected truck sides Unstable truck loads Failure of load restraints Inadequate work methods Failure of lifting apparatus Incorrect rigging of load Unlevel work site Weather conditions Manual handling |  | • Asset damage • Personal injury • Dropped loads etc. • Damage to roadways / infrastructure • Negative reputation impact • Community complaints • Project delays • Struck by plant • Environmental risks of weed transfer. |  | Possible | Major | 8 | • TMP produced and submitted by Monford with approved accredited Roadworks Traffic Manager • SWMS for activities • Pre-start meetings • Supervision • Plant Pre-start • UHF radio comms • Plant operated by licensed and ticketed operators • Exclusion zones / signage established for area as required • Competent personnel for all plant/crane/lifting operations • Inspection of lifting equipment prior to lifts • Spotter in place for reversing • Ground conditions assessed as part of Pre-Start • Toolbox and Pre-starts to flag hazardous driving areas. • Monitor weather conditions, limit access accordingly mandatory & other PPE used as identified safe manual handling practices understood and applied for activities. | Administration | Possible | Insignificant | 22
Weed and seed management | Vehicle and plant hygiene - introduction of noxious weeds to site Weed and / or Seeds taken off site |  | Vehicles and plant not being adequately cleaned prior to being transported to site Weeds / seeds introduced into previously weed free region / area Environmental incident | Environmental | Possible | Moderate | 13 | Removal of mud, soil and other debris carrying foreign weeds prior to mobilisation to site Weed Hygiene Certificate required prior to operating. Pre-mobilisation mechanical inspections and completion of site approval documentation for all plant and equipment Work site inspections to monitor environment (i.e. identify and action noxious weeds identified on site) Environmental Management Plan | Engineering | Unlikely | Moderate | 17
Earthworks, plant and equipment compliance and operation | Interaction between traffic & pedestrians Accidents involving other plant / vehicles Contact with services or equipment Plant roll over |  | Incompetent and / or inexperienced drivers and operators Unapproved vehicles and plant on site Drivers / Operator's do not hold required Licences and or Certificate of competency Equipment failure / Breakdown No segregation of plant in place | Safety | Possible | Catastrophic | 4 | Mobilisation process to ensure all operators are fully competent to preform tasks. VOC, high risk work license / Competency is required for all operators. Operators to be fully aware of the procedure for operating the item of plant or equipment. Barricading work areas where necessary Traffic controllers as required Monford to ensure all plant and equipment suitable, fully serviced and in good working order. All mobile plant to be fitted with ROPS and FOPS (safety in design). Plant Assessor system to be used for risk assessment of all plant and equipment. Spotters to be utilised as required to ensure safe operation of plant. Where possible segregate plant and pedestrians. 2 way radio used at all times. Make positive visual or radio contact with the operator or spotter prior to accessing area. TMP to be prepared and set up and complied with on site. All vehicles fitted with beacon and reversing alarms. BAC testing daily prior to commencement of work. Safety Management Plan. Reference Risk assesment for ROPS and FOPS requiremnts. Ensure operators manual is in cab of vehicle/pant e.g. minimum/maximum gradients. | Engineering | Unlikely | Catastrophic | 7
Driving on site | Vehicle / Vehicle collision Plant / Vehicle collision Plant / Plant collision Vehicle / Pedestrian collision Train / Vehicle / Pedestrian collision Vehicle/ Plant/ Fauna |  | Non-compliance to Project specific Traffic Management Plans, rules and procedures. Non-competent and inexperienced drivers Fitness for work issues - alcohol and / or other drugs Rail Crossings Loose gravel on road surface Soft edges to carriageway Variations in road surfaces and textures Flood / Road Inaccessible Interaction with Public | Safety | Possible | Catastrophic | 4 | Licenced and competent drivers Drivers of LV to hold vVOC certification Fatigue management. Pre-start check of vehicles prior to usage Abide by all signage and speed limits. Working hours, including travel restricted to a maximum of 12 hours, door to door All employees to be breath tested before every shift commences and after each incident Random drugs testing in line with Monford PSMP requirements (10% per Month) plus causal testing Safety Management Plan | Administration | Unlikely | Catastrophic | 7
Earthworks, plant and equipment | Insufficient splill response kits Mechanical failure Environmental risk of leaks and broken fluid lines Environmental Incident |  | Unapproved vehicles and plant Inadequate maintenance records / maintenance Daily Pre starts not completed Unwanted Environmental incidents Inadequate supplies of spill response equipment | Environmental | Possible | Moderate | 13 | Monford to ensure all plant and equipment is suitable, fully serviced and in good working order. Monford to maintain all service records on VPC Subcontractors to provide all current maintenance and services records for plant and equipment on site. Spill kits to be available on site to deal with spills. Traffic management plan to be in place Environmental Management Plan | Administration | Unlikely | Moderate | 17
Plant Maintenance | Manual handling Mechanical interaction HV interaction, Isolations, Hot works |  | No mechanical aids available, heavy lifting, Lack of appropriate signage, poor communication, inadequate separation, Procedure breach, General housekeeping, No designated hot work area Hydrocarbon spill during works | Safety / Environment | Possible | Major | 8 | Permit procedures in place, Mechanical aids to be available and where required Training on the safe use of mechanical aids, Hot work permit system, a permit isolation procedure to be implemented Designated LV parking area, designated walkways, Environmental Management Plan | Administration | Unlikely | Major | 12
Hydrocarbon storage | Inadequate storage and bunding of hydrocarbons |  | Inadequate maintenance of storage equipment Hydrocarbon / chemical leaks Potential for non compatible chemicals being stored together Environmental incident | Environmental | Possible | Moderate | 13 | Secure storage area Bunding (110% of chemiocal holding capacity) requirements) Correct storage and separation of chemicals Required signage erected SDS training at toolbox meetings Stocked spill kits and spill kit training via toolbox meetings Maintained fire extinguishers - Correct type based on hazard review ENV-PL-003 - Environmental Management Plan | Administration | Rare | Moderate | 20
Compaction of earthworks | Incorrect compaction density resulting in ongoing quality issues Works having to be repeated |  | Inadequate workmanship Inadequate quality fill material Inadequate testing compliance Inadequate delineation and barricading Noise, vibrations, Unauthorised persons entering work area Loss of time / unnecessary expense | Safety / Environment | Possible | Moderate | 13 | Supervision to ensure correct placement of material Compaction records to be recorded in accordance with QA requirements Max. 300mm layer lifts. Conduct initial tests on compaction of material, to develop method spec. All ITP's must be signed off. Daily Inspections must be conducted each day by a competent person. Hard barricade / signage as required. All excavators to be operating with spotter in place Excavation permit to include work area exclusion requirements. Q-PL-001 - Quality Plan OHS-PL-007 - Health and Safety Management Plan | Engineering | Unlikely | Moderate | 17
Rock excavation in trenches | Particles from rock breaking operation striking equipment or personnel Noise and vibrations |  | Incorrect use of rock breaking equipment Mechanical failure leading to environmental incident Noise and Vibration | Safety / Community | Possible | Major | 8 | Exclusion zone from extended excavator jib and rock breaker Hard barricade / signage where applicable Excavation permit to include work area exclusion requirements Correct PPE to be worn (Including correct hearing safety protection) Use of 2 way radio for communication with Spotter and operator. Safety pins on quick hitch to be in place (check to be completed at pre start). When maintenance is to be performed the rock breaker is to be in laydown position. Spill kit to be available. Where necessary guards to be fitted to machine windows to prevent injury to Operator. Safety Management Plan Environmental Management Plan | Administration | Unlikely | Major | 12
Open trenches onsite | Personnel / plant / equipment falling or slipping into open trenches due to unstable ground conditions Fauna falling into / becoming trapped in excavations |  | Excavated trenches not barricaded correctly Edge of trenches not suitable or finished to prevent loose material falling in Escape ramps to be constructed in all trenches < 1 in 4 | Safety | Possible | Moderate | 13 | Safe access and egress to trenches (< 1 in 4 ramps) Excavations > 1.5 meters to be benched or shored Barricading and signage to delineate open trenches Barricade around trafficable areas to have reflective guide posts Daily recorded inspection required on excavations >1.5 by the subject matter expert (Engineer). Environmental Management Plan | Administration | Unlikely | Moderate | 17
Earthwork equipment | Noise - uncontrolled noise impact on people, Noisy working environment Prolonged exposure to vibration |  | Large machinery in operation causing excessive amounts of noise Environmental Impact on local fauna Hand / Arm vibration injuries | Environmental | Possible | Moderate | 13 | Correct PPE Including hearing protection Plant operators to have all doors and windows closed to prevent excess noise from entering the cab Operators to have regular work breaks, or possible job rotation to prevent excessive exposure to vibrations Safety Management Plan Environmental Management Plan | Administration | Unlikely | Moderate | 17
Earthwork equipment | Excessive Dust generation impact to workers and or off site public health. |  | Poor air quality Dust nuisance personnel health and well being impacted | Safety / Environment | Possible | Moderate | 13 | SWMS for activities Pre-start meetings Supervision Minimise the number of new tracks on site. Place road base on soil as quickly as possible. Water cart availability Limit activities on windy days if dust is leaving the site or is a nuisance to workers. speed limits and plant operating speeds monitored and adjusted as req mandatory & other PPE used as identified | Administration | Possible | Insignificant | 22
Excavations | Damage to existing underground services Contact with live inground services Silicia dust |  | Breach of Permit requirements Procedural breaches Machine / Operator injury Damage to existing services Damage to plant / Equipment | Safety | Possible | Catastrophic | 4 | Monford to control internal ground disturbance to prevent contact with pre-installed services Site plans AS BUILT drawings to be referred to Excavation permit required, including survey report of existing in-ground services Where underground services are known to exist erect signage to mark location of and hand digging only within 1 metre of know services. Water cart to be used when required for dust supression P2 masks for personnel shoveling sand in excavations | Engineering | Unlikely | Major | 12
Access to deep excavations | Personnel / plant / equipment falling or slipping into open trenches due to unstable ground conditions Fauna falling into / becoming trapped in excavations |  | Loose material on entrance ramps / batters Exposed edges to deep excavations Spoil not stored >1metre from edge of excavation Trenches not checked for integrity regularly | Safety / Environment | Possible | Major | 8 | Excavation / trench access and egress ramps (4 in 1) Access ramps to be compacted material to reduce slip hazard Hard barricading around edge of deep excavation as to requirement stated in excavation permit Daily inspection of open trenches by supervisors prior to works commencing. Trenches deeper than 1.5 to be benched Safety Management Plan Environmental Management Plan | Engineering | Unlikely | Major | 12
Chemicals / hydrocarbon use, storage and handling | Exposure to chemicals Spills Environmental incident Fire / Corrosion Incompatible goods stored together Personal Injury |  | Inadequate or unsuitable storage containers used Inadequate management of risks associated with transport / storage and handling Incorrect or incompatible chemical and hydrocarbon storage | Safety | Unlikely | Major | 12 | New chemical request form to be completed for approval prior to being brought onsite plus SDS Chemical Risk Assessment for chemicals classed as hazardous or dangerous goods Use SDS specified PPE All chemicals to be managed using ChemAlert Approved Chemical Storage bunded (110% capacity of stored goods) areas with segregation of incompatible chemicals / flammable goods All chemicals / hydrocarbon storage vessels to be clearly labelled Inspection of chemical storage areas All chemical storage areas require sufficient ventilation Personnel will be trained via toolbox topic on the safe use of chemicals First aiders poster displayed in the crib room and offices. Eye wash station and First Aid to be available Fire fighting equipment and Spill kits to be available. Signage to Australian standards Safety Management Plan Environmental Management Plan OHS-RA-001 Chemicals Risk Assessment | Engineering | Rare | Major | 16
Chemical transportation / hydrocarbon use and refuelling | Exposure to chemicals Spills, Hydrocarbon spills Fire / corrosion Environmental Incident |  | Poor work practices Incorrect / Ineffective storage containers Collision during transportation Poor refuelling techniques used Incorrect / incompatible chemicals / hydrocarbon storage | Safety | Possible | Major | 8 | All relevant licenses required to be completed Designated storage areas identified for non-hazardous and hazardous chemicals Hazardous chemical storage shall be restricted and stored in lockable cabinets All chemicals / hydrocarbon storage vessels to be clearly labelled Chemical handling, storage, segregation training First aid trained personnel (1:10 ratio) & First aid Kits Mobile refuelling activities to be risk assessed SDS to be available for chemicals in use Chemical Risk Assessment for chemicals classed as hazardous or dangerous goods Use SDS specified PPE Approved Chemical Storage bunded (110% capacity of stored goods) areas with segregation for incompatible chemicals Eye wash station & first aid kits to be available Fire fighting equipment & spill kits to be available Spillkits to be available Signage to australian standards First aid kits to be available Safety Management Plan Environmental Management Plan | Engineering | Unlikely | Major | 12
Waste management | Waste / rubbish littering site (potential for trapped wildlife ,wind blown rubbish, etc.) Used hydrocarbon filters / products Poor waste segregation practices leading to recyclable waste not being recycled |  | Poor waste management Failure to meet recycling targets Incorrect segregation and disposal of waste hydrocarbon equipment Environmental Incident Procedure breach | Safety / Environment | Unlikely | Major | 12 | All rubbish to be disposed of in labelled designated skip bins to ensure effective segregation and recyclability Separate hazardous waste skip bin provided onsite Waste skip bins shall be covered at all times or have hinged lids Bins emptied frequently to prevent overflow of waste Provision of recycling bins - reuse and recycle where ever possible Maintain housekeeping standards Waste management contractors compliant with local regulations and use approved disposal sites Scheduled clean up site sessions Secondary containment provided to prevent contamination where necessary Safety Management Plan Environmental Management Plan | Engineering | Rare | Major | 16
Install Pipeworks / Conduits using crane and / or IT loader with jib attachment | Crane structural overload or ground bearing instability Rigging gear failure Competency of personnel Equipment failure Equipment / personnel interaction IT operator not licenced to use jib / mast attachment |  | Poor pre-lifting plan leads to crane instability / overtruns Inadequate prestart inspections Out of date / defective / damaged lifting and rigging equipment in use Unqualified / Non VOC'd operators Inexperienced / unlicenced crane or IT operators | Safety | Possible | Catastrophic | 4 | Assess site ground conditions and provide safe access for IT loader / Crane Evaluate Crane set up location regarding ground stability relative to loading Only utilise a registered and inspected crane. Where required, ensure a lift plan is in place Lifting equipment inspections according to schedule and prior to any lift Ensure qualified and licenced operators Install exclusion zones if required Positive communications during lifts Lifting and Rigging equipment to be tagged with current colour Pre Start of IT / Crane top be completed daily Safety Management Plan | Administration | Unlikely | Catastrophic | 7
| Hot working conditions Exposure to extreme UV levels Dehydration |  | Extreme climate / working in hot conditions Inadequate water / food intake Inadequate clothing protection Suffering from fatigue Severe sunburn Heat exhaustion or heat stroke | Safety | Possible | Major | 8 | Provide adequate cool drinking water / ice, First Aid supplies including Fact 35+ Sunscreen Education on controls at Induction and toolbox Regular hydration monitoring Ensure employees have adequate PPE clothing and protection for working outdoors Fatigue management programs implemented Ensure breaks are taken at specified intervals Supply mobile shelters as required Safety Management Plan Environmental Management Plan | Administration | Unlikely | Major | 12
| Manual handling - muscle energy |  | Poor technique and posture used during works Employees lifting objects above capability Lack of mechanical assistance available Team lifting not considered / unavailable | Safety | Unlikely | Moderate | 17 | Use correct manual handling techniques. Team lifts where necessary. Use mechanical lifting aids where possible (Forklifts / Telehandler / IT loader etc.) Use correct PPE including correct gloves for the task Safety Management Plan | Administration | Rare | Moderate | 20
Concrete works Stabilising sand cement mix and placement / Formwork / Reo bars | Chemical burns Silica dust inhalation HV / personel interaction Vibration Pinch points Falling Cuts / line of fire injuries Manaual handling High Speed spinning blades |  | Cement dust / concrete splashes / contact Personel in vicinty of reversing mobile plant / pinch points Concrete Vibrator Hand Arm vibration injury Unexpected movement of pipework / mass concrete / formwork Injuries caused by the incorrect use of handtools OHS-P-007 - Health and Safety Management Plan | Safety | Possible | Major | 8 | SDS Sheets to be available Correct PPE as stipulated on SDS sheet inc. Gloves and Hearing protection positive communication between spotter and truck / plant operators Trained and Competant plant and equipment operator - Competencies / HRWL / VOC's Correct tools for the task, competent operators Secure pipework to prevent movement if required Caps on all starpickets and exposed reo bar Prestarts on tools and equipments Correct PPE to be worn including correct gloves for task Environmental Management Plan Safety Management Plan | Administration | Unlikely | Major | 12
Trench Backfilling | Mobile plant in use Interaction between plant / pedestrian Backfill and compaction Warning tapes not installed as required |  | Poor communications and work plans InadequateSWMS risk assessments Incompetent operators Insufficient delineated work areas Unauthorised personnel in work area Potential crush injuries / line of fire injuries Failure to install services warning tapes leads to future damage to services | Safety | Unlikely | Major | 12 | Review programmes, requirements and scope of works Correct use of machinery - Challenge tests where required Prestarts on machinery to be completed VOC's to be verified and recorded Hearing protection to be worn Operators manual to be in machine Radio Communication and Spotters as required Warning tapes for all services to be installed prior to backfilling activities being completed. Safety Management Plan | Administration | Rare | Major | 16

## Survey
1096-01 Yuri
Activity |  |  | Consequences | Risk | Assessment (before controls) |  |  | Controls | Hierarchy of Control | Assessment (Residual Risk)
Task | Hazard | Critical Risk Icons |  |  | Likelihood | Consequence | Rank |  |  | Likelihood | Consequence | Rank
Survey Set-up and Onsite Works | Slippery or uneven Ground Conditions |  | Personnel Injury Strains and sprains Slips and trips Musculoskeletal injury Plant Damage Environmental Damage | Safety | Possible | Moderate | 13 | Maintain / Inspect site conditions Maintain housekeeping Pre start meetings SWMS in place Correct PPE Clearly delineated work area limits, signage as appropriate communicated via inductions | Administration | Unlikely | Moderate | 17
| Exposure to extreme weather conditions i.e. Heat / UV Radiation |  | Dehydration / heat stress Sunburn | Safety | Possible | Major | 8 | Pre- employment medicals for all site mobilised personnel via the clients mobilisation process Pre-employment Drug and Alcohol tests prior to mobilisation Work Methodologies for high risk activities developed by competent and experienced personnel to suit scope of works (Engineering, Project Management, HSE and Works Supervisors) Implementation of Monfords and our clients safety systems Subcontractor Work Methodologies to be submitted and pre-approved by the client prior to subcontractor mobilisation to site OHS-P-022 Fitness for Work Policy OHS-PL-007 Health and Safety Management Plan PRO-F-008 Subcontractor Pre-Award Evaluation PRO-F-005 Supplier self audit questionnaire | Administration | Unlikely | Major | 12
| Interaction with Indigenous Heritage |  |  | Environmental | Possible | Moderate | 13 | Conduct surveys of the project site to identify surface based sites. Consult with manage,memt plans to determine location and nature of Aboriginal sites or artefacts across the Project site. Plan works to minimise ground disturbance in areas known or potential Aboriginal sites or artefacts. Establish Stop Work procedures for unexpected finds of Aboriginal archaeological remains. Design and plan works to avoid disturbance of buried heritage artefacts. Additional heritage training will be provided through toolboxes or pre-starts where specific location or activities may impact on heritage items. Delineate known heritage zones | Administration | Unlikely | Moderate | 17
| Personal Interaction with Fauna |  | Injury to persons and fauna | Safety/Environmental | Possible | Moderate | 13 | Ensure proper PPE is worn All employees can identify and are aware of poisonous fauna Comply with necessary HSE management plans Use of insect repellents Toolbox talk / Communication / Pre-starts | Administration | Unlikely | Moderate | 17
| Protruding materials e.g.. Survey stakes |  | Injury | Safety | Possible | Moderate | 13 | Install protection measures on anchors, i.e. reo bar caps on pegs, flags Supervise entry to area Maintain housekeeping practices Workplace inspections Site Induction Hazard ID in SWMS | Engineering | Unlikely | Moderate | 17
Survey Set out as per drawings supplied by Site Services | • Survey Work is substandard • Surveyor exposed to wildlife (snakes etc) • Interaction with mobile plant / vehicles |  | Causes: - Un accredited and untrained surveyors - Equipment not calibrated - Incorrect site area - surveyor not visible in work area resulting in Interaction with mobile plant / vehicles - grass areas hiding snakes etc Event: - Data provided impacts construction Consequence: - Unable to construct the road causing delays to the project - Incorrect road location causing issues when driving in wet conditions - Potential Injury to personnel |  | Possible | Major | 8 | Procedural: - Work to be conducted in accordance with accepted SWMS - Appoint a control who has surveyors accredited & proficient in the practice of surveying, and is entitled to become registered as a land or mining surveyor, under the register held by the Surveyor General. - Speak to landowner, site manager or property owner, review site maps etc. to determine if there are any hazards e.g. confined spaces, livestock etc - interface between all work groups on activities being performed Active: - Contracting company will ensure that surveyors retain accreditation - annual CPD (competency) - Surveyor location clearly defined and highlighted at all times. high vis markers, barricading if required. Passive: - BOSSI accreditation - surveyors being accredited as being proficient in the practice of surveying | Administration | Unlikely | Major | 12

## Piling
1096-01 Yuri
Activity |  |  | Consequences | Risk | Assessment (before controls) |  |  | Controls | Hierarchy of Control | Assessment (Residual Risk)
Task | Hazard | Critical Risk Icons |  |  | Likelihood | Consequence | Rank |  |  | Likelihood | Consequence | Rank
Piling
Weed and seed management | Vehicle and plant hygiene - introduction of noxious weeds to site Weed and / or Seeds taken off site |  | Vehicles and plant not being adequately cleaned prior to being transported to site Weeds / seeds introduced into previously weed free region / area Environmental incident | Environmental | Possible | Moderate | 13 | Removal of mud, soil and other debris carrying foreign weeds prior to mobilisation to site Weed Hygiene Certificate required prior to operating. Pre-mobilisation mechanical inspections and completion of site approval documentation for all plant and equipment Work site inspections to monitor environment (i.e. identify and action noxious weeds identified on site) ENV-PL-003 - Environmental Management Plan | Engineering | Unlikely | Moderate | 17
EstablishIng work area | Personnel/machinery entering work area |  | Machine to machine contact Machine to personnel contact | Safety | Possible | Minor | 18 | VOC, high risk work license / Competency is required for all operators. Operators to be fully aware of the procedure for operating the item of plant or equipment. Barricading if required Traffic controllers as required Monford to ensure all plant and equipment suitable, fully serviced and in good working order. Spotters to be utilised as required to ensure safe operation of plant. Where possible segregate plant and pedestrians. 2 way radio used at all times. Make positive visual contact with the operator prior to encroaching within 50m. TMP to be prepared and set up and complied with on site. All vehicles fitted with beacon and reversing alarms. BAC testing daily prior to commencement of work. OHS-PL-007 - Health and Safety Management Plan | Engineering | Unlikely | Major | 12
Drilling Operations | Interaction between traffic & pedestrians Accidents involving other plant / vehicles Contact with services or equipment Plant roll over. Use of compressed air. Noise Line of fire. Pinch points |  | Personal Injury; Property damage; Environmental damage; Monford Group reputation | Safety / Environment | Possible | Major | 8 | Operators to be fully aware of the procedure for operating the item of plant or equipment. Barricading if required Traffic controllers as required Monford to ensure all plant and equipment suitable, fully serviced and in good working order. Spotters to be utilised as required to ensure safe operation of plant. Where possible segregate plant and pedestrians. 2 way radio used at all times. Connections to have pins installed and whip checks attached Make positive visual contact with the operator prior to encroaching within 50m. TMP to be prepared and set up and complied with on site. All vehicles fitted with beacon and reversing alarms. BAC testing daily prior to commencement of work. OHS-PL-007 - Health and Safety Management Plan
Stabed sand of drill holes | Pinch / crush points Line of fire Untidy work area Uncontrolled equipment movements Cement burns |  | Personal Injury; Property damage; Environmental damage; Monford Group reputation | Safety / Environment | Possible | Major | 8 | Use a spotter to direct Agi-truck int o position. Spotter to maintain visual contact with truck driver, not to stand directly behind truck, stop truck if visual contact is lost – reposition and continue directions. Clear area of equipment and personnel within immediate operating area of truck Provide suitable access for truck, ie; solid, stable ground in slippery conditions, adequate width to turn, Ensure truck is stationary before extending or attaching chute Wear appropriate gloves for task Obtain and read SDS for chemical products in use. Use of correct PPE including gloves and eye protection
Piling operation | Interaction with people and moving / rotating equipment Crush/caught between injuriy |  | Incompetent and / or inexperienced drivers and operators Unapproved vehicles and plant on site Drivers / Operator's do not hold required Licences and or Certificate of competency Equipment failure / Breakdown No segregation of plant in place | Safety | Possible | Catastrophic | 4 | VOC / Competency is required for all operators. Operators to be fully aware of the procedure for operating the item of plant or equipment. Appropriate guarding in place to prevent crushing Barricading if required Windscreen to be regularly cleaned Monford to ensure all plant and equipment suitable, fully serviced and in good working order. Where possible segregate plant and personnel BAC testing daily prior to commencement of work. OHS-PL-007 - Health and Safety Management Plan | Engineering | Unlikely | Major | 13
| Line of fire Hands/fingers/feet/legs Body position Shifting and swinging loads Sharp edges |  | Inury | Safety | Possible | Catastrophic | 4 | Detailed hazard ID within SWMS Guarding in place Use trained and competent personnel wearing correct PPE Clear communication between parties Use tools that separate hand from impact zone Maintain focus on activity and select correct hand tool Ensure hands are not in the line of fire (pinch points) Wear appropirate gloves | Engineering | Unlikely | Major | 11
| Incorect set up of piling rig |  | Plant Damage/injury | Safety | Possible | Major | 7 | Appropriately qualified persons to identify required equipment Certified Rig/Drilling equipment, tagged and tested equipment SWMS in place for task Check ground conditions for stability | Administration | Unlikely | Major | 12
Operating and moving pile driving machine. Commence Piling Operations. Slotting Piles into Pile Rig Driver Head | Unauthorized personnel entering the area |  | Struck/crushed/run over by travelling pile machine or lowering hammer head causing injury. Flying Debris and or Particles when Hammering Pile into ground. Moving and or rotating parts. Hot Surfaces. movement Sprains and Strains Burred / Sharp edges Pinch Points / Line of Fire, Lifting with 2T Girder Clamp Personnel lifting Piles with 2T girder Clamp inappropriately attached to pile. 2T Girder Clamp damage. Uneven ground, Trip hazard Manual handling, Hand injuries, Sprains & strains Repetitive Bending / Body Pinch & Crush points, Fauna - Spiders, Snake bites | Safety | Possible | Major | 8 | Refer to original equipment manufacturer manual for operating instructions. Personnel to approach machine from rear driver’s side. Do not stand in front of machine in direction of travel. Maintain 5m exclusion zone Avoid additional personnel being close to piling machine – layout and distribution crews should be ahead of piling machine work front. Rotate Task(s) between Crew Personnel to communicate with the Operator, Identify Pinch Points & Hot Surfaces using SWMS. Follow lifting pile instruction and training provided to crews. Only use demonstrated method to attach 2T Girder Clamp. Seek appropriately trained rigger if any concerns with 2T girder Clamp i.e. any damage or distortion noticed at daily pre use inspection. Any damage identified shall result in 2T Girder Clamp to be removed from service immediately and presented to Supervision. All lifting gear needs to be approved and tagged RGBY test tag system and included in equipment register. Personnel to assess ground conditions – eyes on path, Avoid walking backwards when possible, carrying Piles, proactive use of warm up stretches before work commences. Only standard array piles to be manually lifted, wear Gloves when handling Piles, consider posture when handling Piles, straight back, bend Knees and keep weight close to body. Never place any body part between the hammer head and the top of the post. No hands/fingers on top of post while post is in the piling position. Job Rotation Rotate task between crew members have regular breaks as required. Personnel to maintain positive coms with Operator and approach only when machine is stationary, Personnel on foot not to walk behind machine and be aware of line of fire, Do a visual inspection around under material stacks. If Snake is seen stay clear and notify Supervision/ HSE. | Administration | Unlikely | Major | 13
Application of paint on piles | Chemical Paint |  | Chemical exposure. Aerosol use | Safety | Likely | Minor | 14 | Ensure SDS in place Workers need to read, understand and adhere to SDS Wear PPE – gloves (chemical resistant), eye protection, long pants and long shirt. P2 Mask Wash hands and before eating, smoking and using the lavatory and at the end of the working period.
| Noise from Hammer |  | Disturbance of flora and fauna Hearing loss Personnel injury Damage to flora & fauna Noise complaints from stakeholders | Safety | Possible | Moderate | 13 | Correct PPE - double hearing protection for operator and spotter (ear buds and muffs over) Warning Signs requiring Hearing Protection Ensure all plant and equipment is maintained and serviced Pre-mob Risk Assessments and inspections of plant/equipment SWMS in place | Administration | Unlikely | Moderate | 17
| Fall from height |  | Inury | Safety | Possible | Major | 7 | Only qualified personnel to access heights, safe work at heights training where required SWMS for task No personnel to work at heights unless fall protection is provided and WAH permit has been issued where required | Administration | Unlikely | Major | 13
Plant Maintenance | Manual handling Mechanical interaction HV interaction, Isolations, Hot works |  | No mechanical aids available, heavy lifting, Lack of appropriate signage, poor communication, inadequate separation, Procedure breach, General housekeeping, No designated hot work area Hydrocarbon spill during works | Safety / Environment | Possible | Major | 8 | Permit procedures in place, Mechanical aids to be available and where required Training on the safe use of mechanical aids, SWMS Competent persons only to perform maintenance on any plant Hot work permit system, a permit isolation procedure to be implemented ENV-PL-003 - Environmental Management Plan | Administration | Unlikely | Major | 12
Waste management | Waste / rubbish littering site (potential for trapped wildlife ,wind blown rubbish, etc.) Used hydrocarbon filters / products Poor waste segregation practices leading to recyclable waste not being recycled |  | Poor waste management Failure to meet recycling targets Incorrect segregation and disposal of waste hydrocarbon equipment Environmental Incident Procedure breach | Safety / Environment | Unlikely | Major | 12 | All rubbish to be disposed of in labelled designated skip bins to ensure effective segregation and recyclability Separate hazardous waste skip bin provided onsite Waste skip bins shall be covered at all times or have hinged lids Bins emptied frequently to prevent overflow of waste Provision of recycling bins - reuse and recycle where ever possible Maintain housekeeping standards Waste management contractors compliant with local regulations and use approved disposal sites Scheduled clean up site sessions Secondary containment provided to prevent contamination where necessary OHS-PL-007 - Health and Safety Management Plan OHS-PL-003 - Environmental Management Plan | Engineering | Rare | Major | 16

## Mechanical - Solar
Construction Risk Assessment Workshop
1096-01 Yuri
Activity |  |  | Consequences | Risk | Assessment (before controls) |  |  | Controls | Hierarchy of Control | Assessment (Residual Risk)
Task | Hazard | Critical Risk Icons |  |  | Likelihood | Consequence | Rank |  |  | Likelihood | Consequence | Rank
Activity
Personal Protective Equipment | Exposure to flying objects; UV and heat exposure; Sharp edges; Noise; |  | Personal Injury; Monford Group reputation. | Safety | Possible | Moderate | 13 | 100% cotton Hi Vis long sleeve with reflective strips. Shirt sleeves to be rolled down and buttoned at cuff and tucked in to pants. 100% cotton full length pants. Safety ankle high lace up boots. Medium impact safety glasses clear and tinted. Hard hat (sun brims are available), Gloves, suitable for the task being undertaken carried on person, worn when manual tasks are being conducted. Hearing protection, on person and worn as required. Wet weather and cold weather wear will be made available to all workers before weather conditions require it. Sunscreen is to be available in crib rooms, amenities and vehicles. Correct PPE at all times. SWMS’s must be adhered to at all times. |  | Unlikely | Moderate | 17
General Activities | Exposure to flying objects; UV and heat exposure; Sharp edges; Noise; Collision with mobile plant; Collision with vehicles Injury from poor housekeeping; Slips, Trips and Falls; Sharp objects; Pinch Points; Faulty electrical equipment. |  | Personal Injury; Property damage; Environmental damage; Monford Group reputation | Safety / Environmental | Possible | Moderate | 13 | Correct PPE at all times. SWMS’s must be adhered to at all times.Good housekeeping is to be maintained, all tools and equipment are to be placed away or in relevant toolboxes when not in use, and access ways are to be kept clear of debris, leads and rubbish. Approved Lead stands, insulated cable hooks, etc. are to be used to raise leads and or data cables off the ground when being run more than 10 metres from power source or generator. Run leads and cables away from vehicle and pedestrian trafficable areas. Site delineation through use of barricading, fencing and or signage, danger signage and flagging and barricades are to be erected. Remove trip hazards as they are identified, erect signs and barricading to warn others of dangers if hazards cannot be rendered safe. Report all hazards to your Supervisor. Electrical equipment to be tested and tagged as per guidelines. | Administration | Unlikely | Moderate | 17
| Driving / operating light vehicles |  | Interaction with people -Interaction with other plant & equipment -Interaction with wildlife -Drive Fatigue -equipment failure -Hydrocarbon/ Chemical spill -Road Conditions/dust | Safety / Environmental | Possible | Catastrophic | 4 | Regular maintenance and servicing of vehicles Light Vehicle (LV) driving procedures Site induction Adherence to site road rules & speed Vehicle pre-starts to be conducted Comply with site TMP. Valid Drivers licenceLicenced and competent drivers Drivers of LV to hold vVOC certification Fatigue management. Pre-start check of vehicles prior to usage Abide by all signage and speed limits. Working hours, including travel restricted to a maximum of 12 hours, door to door All employees to be breath tested before every shift commences and after each incident Random drugs testing in line with Monford PSMP requirements (20% per Month) plus causal testing Safety Management Plan | Administration | Unlikely | Catastrophic | 7
| Hydrocarbon / Chemical spill |  | Environmental damage Injury to personnel/ illness Soil and Water Contamination Harm to Fauna | Safety / Environmental | Possible | Moderate | 13 | Equipment Inspections/Maintenance, Equipment Risk Assessments and Pre-start checks SDS and chemicals identified Provide Spill kits Comply with Environmental Management Plan Provide Hazardous Materials Storage Correct transportation as per TMP | Administration | Unlikely | Moderate | 17
| Mixed waste streams - waste management |  | Uncontained spread of litter across the site and adjoining properties pest species entering the work site Unnecessary material going to landfill | Environmental | Possible | Moderate | 13 | Bins shall be delivered and collected from nominated work front areas Some waste materials can be sorted and placed in separate bins on site for recycling (e.g. steel and concrete off cuts). Covers to be placed on bins to prevent airborne debris Bins to be labelled | Engineering | Rare | Moderate | 20
Cultural Heritage | Interaction with Indigenous Heritage |  | Invasive and disturbing ground works in Indigenous areas on site | Environmental | Unlikely | Major | 12 | Conduct surveys of the project site to identify surface based sites. Consult with Aboriginal groups to determine location and nature of Aboriginal sites or artefacts across the Project site. Plan works to minimise ground disturbance in areas known or potential Aboriginal sites or artefacts. Establish Stop Work procedures for unexpected finds of Aboriginal archaeological remains. Providing an opportunity for Aboriginal community to inspect areas prior to construction to salvage artefacts; Providing an opportunity for the Aboriginal community to monitor selected construction works; Design and plan works to avoid disturbance of buried heritage artefacts. Additional heritage training will be provided through toolboxes or pre-starts where specific location or activities may impact on heritage items. Delineate known heritage zones | Isolation | Rare | Major | 16
Maunal Handling | Manual handling injuries; Serious injury; Permanent damage. Muscular over exertion |  | Personal Injury; Strains and sprains Slips and trips Musculoskeletal injury | Health / Safety | Possible | Major | 8 | All workers and contractors to attend Prestart to document controls and hazards of manual handling tasks. Mechanical aids, team lifts to be used as much as possible to avoid manual handling. Approved gloves carried on person and worn during all manual handling tasks. designed for 2 men lift. Personnel shall be trained project specific to individual panels used for correct lifting techniques and body positioning.Correct analysis of job requirements SWMS in place for task Rotate tasks where possible Use of lifting equipment if required Plan course of travel Adequate stretching prior to task Assume correct posture (bend knees, straight back, etc.) Use mechanical aids where possible Assisted two person lifts Assess and select the correct gear Correct tool for task | Administration | Unlikely | Minor | 21
Cleaning/Sweeping out container | Mould particles Dust Slips/Trips |  | Personal Injury; Health/Breathing issues Environmental damage; . | Health / Safety | Possible | Major | 8 | Ensure dust masks are worn at all times minimum P2 mask when working in containers Ensure mask fits close on the face to prevent breathing in dust | Administration | Unlikely | Major | 12
Truck Positioning | Plant collision; Plant, personnel collision. |  | Personal Injury; Property damage; Environmental damage; Monford Group reputation. | Safety / Environmental | Possible | Major | 8 | Delivery trucks must be placed once to ensure correct unloading once unrestrained. Only Truck drivers are to unrestraint and restrain loads. Truck drivers must have complete PPE to get on the site through security. | Engineering | Rare | Major | 16
Loading/Unloading trucks. | Plant roll over; Plant, vehicle collision; Plant, personnel collision. Crushing/Unstable loads |  | Personal Injury; Property damage; Environmental damage; Monford Group reputation. | Safety / Environmental | Possible | Catastrophic | 4 | Use spotter if required. Ensure load is secured on forks before moving, ensure work area is clear of non-essential personnel. Ensure work area is free of obstructions. Ensure clear direction hand signals. Unauthorised persons keep out. No lifts to commence until all personnel are well clear and in eyesight of operator. Ensure all communications are clear and understood. Qualified VOC’d people only to operate plant. Plant Pre-Start to be completed prior to any works commencing. Reversing beeper and flashing light must be operable. All mobile plant to be fitted with ROPS and FOPS (safety in design).All persons entering laydown yard to notify by calling up on channel 12. No lifts to commence until all personnel are well clear and in eye sight. Ensure good clear positive communications at all times. All entries into laydown yard must call up on channel 12. Operator to realign before lifting | Engineering | Unlikely | Major | 12
Stacking in the lay down. | Plant roll over; Plant, vehicle collision; Plant, personnel collision. |  | Personal Injury; Property damage; Monford Group reputation. | Safety | Possible | Major | 8 | Ensure load is secure on forks of plant, drive to conditions, use spotter if required. Ensure packs are strapped and stable before stacking. Unauthorised persons keep out. Qualified VOC’d people. Plant Pre-Start must be completed prior to works commencing. All plant and vehicles to do 10kph only in the laydown area. All mobile plant to be fitted with ROPS and FOPS (safety in design). Reversing beeper and flashing light must be operable. | Administration | Unlikely | Major | 12
Placement of load. | Plant roll over; Plant, vehicle collision; Plant, personnel collision. |  | Personal Injury; Property damage; Monford Group reputation. | Safety | Possible | Catastrophic | 4 | Use spotter if required. Ensure load is placed on level and even surface. Unauthorised persons keep out. Qualified VOC’d people. Plant Pre-Mobilisation Form. | Administration | Unlikely | Major | 12
Loading & unloading tubes | Plant roll over; Plant, vehicle collision; Plant, personnel collision. Crushing/Unstable loads |  | Personal Injury; Property damage; Monford Group reputation. | Safety | Possible | Major | 8 | Use spotter if required. Ensure load is secured on forks before moving, ensure work area is clear of non-essential personnel. Ensure work area is free of obstructions. Ensure clear direction hand signals. Unauthorised persons keep out. No lifts to commence until all personnel are well clear and in eyesight of operator. Ensure all communications are clear and understood. Qualified VOC’d people only to operate plant. Plant Pre-Start to be completed prior to any works commencing. Reversing beeper and flashing light must be operable. All persons entering laydown yard to notify by calling up on channel 12.No lifts to commence until all personnel are well clear and in eye sight. Ensure good clear positive communications at all times. All entries into laydown yard must call up on channel 12. All mobile plant to be fitted with ROPS and FOPS (safety in design). Reference Risk assesment for ROPS and FOPS requiremnts. Operator to realign before lifting | Engineering | Rare | Moderate | 20
Uncontrolled Movement of load on tines | Uncontrolled Movement of load on tines |  | Swinging loads Dropped objects Crush Injuries Falling loads Damage to surrounding structures | Safety | Possible | Major | 8 | Certified & competency assessed operators to be used. Assess weather conditions & continuously monitor. SWMS completed. Lifting chains and swift lifts to be certified and tagged (if jib attachment in use) Use spotter when travelling in congested areas Keep hands off all loads | Administration | Unlikely | Moderate | 17
Distributing loads in the field. | Plant roll over; Plant, vehicle collision; Plant, personnel collision. |  | Personal Injury; Property damage; Environmental damage; Monford Group reputation. | Safety / Environmental | Possible | Moderate | 13 | Use spotter if required. Ensure load is secured on forks before moving, ensure work area is clear of non-essential personnel. Ensure work area is free of obstructions. Ensure clear direction hand signals. Unauthorised persons keep out. No lifts to commence until all personnel are well clear and in eyesight of operator. Ensure all communications are clear and understood. Qualified VOC’d people only to operate plant. Plant Pre-Start to be completed prior to any works commencing. All mobile plant to be fitted with ROPS and FOPS (safety in design). Reference Risk assesment for ROPS and FOPS requiremnts. Reversing beeper and flashing light must be operable. | Administration | Unlikely | Moderate | 17
Unloading Telehandler/Skid steer in the field | Manual Handling Pinch points Crush zones Snakes |  | Personal Injury | Safety | Possible | Major | 8 | Ground person to be aware of telehandler movements at all times, positive communications and remain in line of sight at all times. Use rods to unload piles to prevent pinch point and crush injuries. Stand clear of piles when dropping onto ground, and two person lifts when required. Be aware of surrounding and native fauna.Radio/Visual Communications Inspect the load for movement/uncontrolled condition Compliance with vehicle speed limits SWMS in place VOC/Licensing of operators & riggers Equipment Inspections/Risk Assessments and Pre-start checks Inspection, Testing and Tagging of Lifting and Rigging Equipment (daily, quarterly) Use suitable tag lines Work at Heights Training Provide suitable access equipment to loads with fall protection. Correct PPE Suitable preparation to land items | Administration | Unlikely | Moderate | 17
Loading & Unloading Torque tubes from flat bed truck | Plant roll over; Plant, vehicle collision; Plant, personnel collision. Pinch points Crush zones |  | Personal Injury; Property damage; Environmental damage; Monford Group reputation. | Safety | Possible | Catastrophic | 4 | Use spotter if required. Ensure load is secured on forks before moving, ensure work area is clear of non-essential personnel. Ensure work area is free of obstructions. Ensure clear direction hand signals. Unauthorised persons keep out. Qualified VOC’d people to operate and spot loads. All loads to be strapped down before truck moves Plant Pre-Start and Pre-Mobilisation Form. All mobile plant to be fitted with ROPS and FOPS (safety in design). Reversing beeper and flashing light must be operable | Administration | Unlikely | Moderate | 17
Laser Levelling for bracket install/Tracker align | Strains & Sprains Eye Damage |  | Personal Injury; | Health / Safety | Possible | Moderate | 13 | Proper Manual handling techniques moving laser Don’t stare into laser (for class 3 R there is low risk of eye injury. Wear eye protection and correct PPE. | Administration | Rare | Moderate | 20
Install brackets | Strains & Sprains Pinch points Hearing damage Sharp edges Fauna Dehydration |  | Personal Injury;; | Safety / Environmental | Possible | Moderate | 13 | Use mechanical aids where required, avoid overreaching and over stretching. Be aware of pinch points when placing and tightening brackets. Hearing protection must be worn when rattling up bolts and clamps. Correct gloves for the task. Keep eyes on path & keep work areas clean to prevent snakes. Take regular breaks and rotate tasks as required | Administration | Unlikely | Moderate | 17
Install motors | Strains & Sprains Pinch points line of fire Sharp edges plant personnel collision |  | Personal Injury; Property damage; Environmental damage; Monford Group reputation. | Safety | Possible | Catastrophic | 4 | Use of mechanical aids when required. Certified lifting equipment; Competant VOC'd operator. Pre-start cpmpleted. Possitive communiication. Clear understanding of task. Ensure load is secure before moving. Ensure work area is free of obstructions. Agree on hand signals prior to comencing works. Correct PPE. Keep out of the line of fire at all times | Administration | Unlikely | Moderate | 17
Positioning torque tubes into brackets and stands. | Manual handling Mobile plant Strains & Sprains Pinch Points Line of fire Dehydration Sharp Edges |  | Personal Injury; Property damage; Monford Group reputation. | Safety | Possible | Moderate | 13 | Mechanical aids such as Tele handlers, Skid Steer Loaders will be used where ever access is available. Pre start inspections to be completed prior to works commencing. Positive communications to be maintained at all times/Line of sight. Ensure flashing amber light and reverse alarms are operational. Pre plan job so mechanical aids have access to areas. Two person lifts if torque tubes needed to be lifted by hand. Ground personnel to be aware of machine movements. Gloves to be worn at all times. Work crews to have regular drink breaks and rotate jobs as needed | Administration | Unlikely | Moderate | 17
Straightening & Tightening bracket bolts | Pinch points Sharp Edges Hearing Damage |  | Personal Injury; Property damage; Monford Group reputation | Safety | Possible | Moderate | 13 | Use mechanical aids where required, avoid overreaching and over stretching. Be aware of pinch points when placing and tightening brackets. Hearing protection must be worn when rattling up bolts and clamps. Correct gloves for the task. | Administration | Unlikely | Moderate | 17
Instalation: springs, dampers | Cluttered / Congested Work Site (Poorly maintained worksite) |  | Injury to personnel (slips, trips, and falls) | Health | Possible | Moderate | 13 | Ensure good clean housekeeping practices Pre start meetings Supervision inspect work place daily Use designated lay down areas Ensure a SWMS in place Restricted work access areas in accordance with SWMS | Administration | Unlikely | Moderate | 17
| Interaction with people and moving / rotating equipment |  | Potential fatality Personal Injury Equipment damage | Safety | Possible | Moderate | 13 | Drivers/Operators to be competent Ensure good visibility Use of spotter (if required) Use mirrors Windscreen to be regularly cleaned Radio communications Maintenance program Maintenance by trained and competent person Check ground condition Restricted work access in accordance with SWMS Delineation and signage in place Correct PPE for the task | Administration | Unlikely | Moderate | 17
| Noise |  | Disturbance of flora and fauna Hearing loss Personnel injury Damage to flora & fauna Noise complaints | Safety / Environmental | Possible | Moderate | 13 | Correct PPE Toolbox Training - Hearing Protection Warning Signs requiring Hearing Protection Ensure all plant and equipment is maintained and serviced Pre-mob Risk Assessments and inspections of plant/equipment Prestart Meetings Correct PPE Adequate SWMS in place | Administration | Rare | Moderate | 20
| Open excavations (Falling, slips, engulfment) |  | Personnel Injury Strains and sprains Slips and trips Musculoskeletal injury Plant Damage Fauna entrapment | Safety / Environmental | Possible | Moderate | 13 | Define and install access / egress points for workers and fauna Establish adequate barriers and signage Adhere to excavation procedures Undertake regular fauna inspections Maintain regular housekeeping Complete and adhere to Permit to Work Benching, Batter or shoring as per requirements Complete SWMS | Engineering | Unlikely | Moderate | 17
| Setting up equipment on unsuitable ground |  | Personnel Injury Plant Damage | Safety | Possible | Moderate | 13 | Ensure adequate stability of ground prior to commencing works Radio/Visual Communications Inspect the load for movement/uncontrolled condition SWMS in place / Work Method Statements VOC/Licensing of operators & riggers Equipment Inspections/Risk Assessments and Pre-start checks Inspection, Testing and Tagging of Lifting and Rigging Equipment (daily, quarterly) Use suitable tag lines Correct PPE Suitable preparation to land items (method statement plans) | Engineering | Unlikely | Moderate | 17
| Line of fire • Hands/fingers/feet/legs • Body position • Shifting and swinging loads Sharp edges |  | Personal Injury | Health / Safety | Possible | Moderate | 13 | Detailed hazard ID within SWMS Use trained and competent personnel wearing correct PPE Clear communication between parties Careful hand placement • Use tools that separate hand from impact zone • Maintain focus on activity and select correct hand tool • Ensure hands are not in the line of fire (pinch points). Syay out of the line of fire.Correct PPE for the task e.g. gloves | Administration | Unlikely | Moderate | 17
| Protruding materials e.g.. Survey stakes |  | Impalement Personal injury | Health / Safety | Possible | Moderate | 13 | Install protection measures on anchors, i.e. reo bar caps on pegs, flags Supervise entry to area Maintain housekeeping practices Workplace inspections Site Induction Hazard ID in SWMS | Administration | Unlikely | Moderate | 17
| Use of power & hand tools |  | Potential Injury Damage to equipment | Health / Safety | Possible | Moderate | 13 | Correct tool selection for task Fit for purpose All power tools to have dead mans switch Regular maintenance of equipment Pre-inspection Review SWMS Follow Work method statement | Administration | Rare | Moderate | 20
Use of CAT Vacuum Solar Panel attachment | Limited work area Pallets in the working area Vacuum not attached correctly |  | Crush injuries Dropped loads Striking Torque Tubes | Safety | Possible | Moderate | 13 | • Pre start excavator and attachment for function and oil leaks • Visual inspection of attachment for damage • Zero Tail swing excavator • Ensure light activation system is working RED Low Vacuum AMBER Load Switch BLUE Vacuum Applied • Check vicinity is clear before slewing left or right • Correct PPE is worn • Ensure no workers under panel • Ensure WWL of 50KG per panel is not exceeded • Remove pallet when empty | Administration | Unlikely | Moderate | 17
PV Panel Installation | Manual handling Mobile plant Strains & Sprains Pinch Points Line of fire Dehydration Sharp Edges |  | Personal Injury; Property damage; Environmental damage; Monford Group reputation. | Health/Safety | Possible | Major | 8 | Use mechanical aids where required, avoid overreaching and over stretching. Be aware of pinch points when placing and tightening brackets. Hearing protection must be worn when rattling up bolts and clamps. Operators of mobile plant to have possitive comms with personnel on the ground. Correct gloves for the task. Keep eyes on path & keep work areas clean to prevent snakes. Take regular breaks and rotate tasks as required. Keep area clear and clean / Remove used panel boxs and pallets as soon as possible | Administration | Unlikely | Minor | 21
Adequate Breaks, Rest, Food and Water intake. | Onset of tiredness; Fatigue; Lack of energy; Dehydration; Fitness for work. |  | Personal Injury; Property damage; Environmental damage; Monford Group reputation. | Health | Possible | Moderate | 13 | Supervisors MUST ensure that their workers are getting enough rest time during the day, especially on days over 32 degrees. All workers are responsible for taking breaks and bringing enough food for the day. Keep taking in water, even in the colder months to make sure you don’t dehydrate. Persons who are feeling dizzy or light headed are to rest and advise their Supervisor immediately. Someone must let Monford Group HSEQ ASAP. Supervisors and work colleagues are to be vigilant for fatigued persons and report it immediately. Look after your mates. Correct PPE at all times. | Administration | Unlikely | Minor | 21
Emergency. | Personal Injury; Emergency on site. |  | Personal Injury; Property damage; Environmental damage; Monford Group reputation. | Health / Safety | Possible | Catastrophic | 4 | Emergency, Emergency, Emergency called on UHF 12 in the case of an emergency including dehydration, Muster point and closest emergency phone to be relayed to work team including Site Emergency No. All incidents injuries to be reported immediately to the Supervisor or the Monford Group HSEQ Team. Cease work wait for next instruction, Keep radio silence at all times. | Administration | Rare | Catastrophic | 11
Clean up on completion | Trip hazards; Rubbish build-up; Inappropriate disposal; Rats and vermin. |  | Personal Injury; Property damage; Environmental damage; Monford Group reputation. | Safety | Possible | Moderate | 13 | All personnel to be responsible for clean up and removal of all equipment, tools and spoil in the correct environmental segregated recepticals. All work areas to be thoroughly checked to ensure that all tools and equipment are accounted for before leaving site. Correct PPE. All waste, spoil and recyclables are to be disposed to a licensed facility and dockets returned to Monford HSEQ. Talk to Supervisor if unclear on designated areas for material disposal. Utilise rubbish bins. Waste must be segregated. Environmental Procedures shall be followed at all times. | Administration | Unlikely | Moderate | 17

## Electrical
Construction Risk Assessment Workshop
1096-01 Yuri
Activity |  |  | Consequences | Risk | Assessment (before controls) |  |  | Controls | Hierarchy of Control | Assessment (Residual Risk)
Task | Hazard | Critical Risk Icons |  |  | Likelihood | Consequence | Rank |  |  | Likelihood | Consequence | Rank
Cable trays and cables
Istallation of Cable Trays | Manual handling - strains, sprains, strike injuries |  | Personal injury | Safety | Possible | Moderate | 13 | SWMS to be developed Correct PPE including site specific clothing, gloves and any other PPE specific to the task and / or conditions. Correct manual handling techniques Use of mechanical aids where applicable Due to restrictive height of the cable trays work at ground level to minimise bending | Administration | Unlikely | Moderate | 17
Pulling cables | Manual handling - strains, sprains, strike injuries |  | Personal injury | Safety | Possible | Moderate | 14 | SWMS to be developed Correct PPE including site specific clothing, gloves and any other PPE specific to the task and / or conditions. Correct manual handling techniques Use of mechanical aids where applicable Due to restrictive height of the cable trays work at ground level to minimise bending | Administration | Unlikely | Moderate | 18
Install pits and conduits | Working in trenches : Poor trench conditions, Trench/hole cave in, no clear access or egress, poor planning, FFW - fatigue, dehydration. Cold weather conditions during winter months. Silica sand placement in trench |  | Personal injury slips trips back injury musculoskeletal hand injuries personal injury, Long term health issues | Safety | Possible | Moderate | 13 | Hard barricades, inspection of trench prior to entry, trench is sufficiently shelved or sloped, hazards to be communicated during pre start and tool box talks, SWMS / JSEA to be completed and reviewed prior to work commencement, avoid working after dark, pre start inspections on equipments, routine maintenance of equipments, respiratory protection, dust suppression where required, Access and egress, placement of spoil. Monitor hydration levels - drink water, wear site required PPE - wide brim on hard hat. During winter months (cold climate) additional clothing maybe required. Monford/Risen to provide sand testing report. PPE - P2 dust mask at all times when working in the trenches where sand is being layed | Engineering | Unlikely | Moderate | 17
| Manual Handling injuries : Over exertion no clear access failure to stretch prior to lifting incorrect posture failure to use appropriate PPE |  | Personal injury slips trips back injury musculoskeletal hand injuries | Safety | Likely | Moderate | 9 | Manual handling training, Report recording & investigation etc. of any personal injuries through manual handling, Regular breaks with workforce and rotation of workforce, PPE (Gloves), Development of work plan / standard work practices, SWMS / JSEA to be completed and reviewed prior to work commencement, Hazards to be communicated in Toolbox talks and Pre start meetings, Availability of winching equipment if required, Field inspections, Three points of contact when climbing ladders, Keep hands clear of pinch points, Use sufficient personnel to share the load if appropriate, Fatigue awareness training | Administration | Possible | Moderate | 13
| Interaction with moving vehicles : Working in open areas Unsecured vehicles |  | Injury / fatality | Safety | Possible | Major | 8 | Barricades / signage. Immobilise / isolate vehicle,, SWMS / JSEA, Work planning, Communication. Hazards to be communicated in Toolbox talks and Pre start meetings, Spotters. Demarkation. Isolation of personnel from min 50m of moving plant. | Isolation | Unlikely | Major | 12
| Environmental hazards e.g.-solvents, cable lubricant, glue: Uncontrolled use Incorrect disposal Incorrect use of PPE Dispersion Spills |  | Environmental contamination Damage to Personnel health/safety | Enviromental | Possible | Minor | 18 | Designated lay down areas, Ensure that hazardous materials are secured and stored in proper containers, Provision of spill kits in storage area, training in spill response, Hazards to be communicated in Toolbox talks and Pre start meetings, SDS to be easily accessed and followed by employees, Training on hazards of chemicals for personnel involved, Maintain proper housekeeping, correct PPE, SWMS / JSEA to be completed and reviewed prior to work commencement | Administration | Unlikely | Minor | 21
Cable Install preparation using trailer & tractor | Roll out of cable using cable trailer / tractor : Line of fire, Incorrect manual handling technique, Twisting & straining, Damage to trailer, removal of safety guards, slips , trips & falls, struck by projectiles from vehicles, collision with other vehicles, pedestrians and fauna, Lose of load, damage to cable / drum |  | Personal injuries - short & long term issues Damage to materials & equipment Additional replacement costs | Safety | Possible | Moderate | 13 | Inspection of trailer and tractor for faults - report faults to supervisor and tag Out of Serice if required. Drive to site conditions adhering to site rules - speed limits. Radio communication with other vehicles / plant. Secure load to trailer conduct inspection of load before moving. Ensure all safety guards are in place and secure. Position trailer in predetermined position ensuring that brakes are secure before releasing trailer. Use spotter if required ensuring that the operator has full visual contact with spotter at all times. Work must cease if spotter is out of line of sight. | Engineering | Unlikely | Moderate | 17
| Manual handling - cuts, strains, pinch/crushing injuries : Incorrect lifting technique Not using lifting aids Not asking for assistance to lift & carry Twisting/straining during lift Not keeping fingers out the way of pinch points or when setting down the load Poor housekeeping - trip hazards Not using gloves |  | Personal injuries - short & long term issues Damage to materials & equipment Additional replacement costs | Safety | Possible | Moderate | 13 | Correct analysis of requirements SWMS / JSEA Training in Toolbox and pre-start meetings & safety topics Use of lifting equipment if required, Plan course of travel Adequate stretching Keep fingers clear of pinch points - watch your hands Assume correct lifting technique Mechanical assisted or two person lifts Assess and select correct lifting aids and PPE | Administration | Unlikely | Moderate | 17
| Chemical exposure - PVC solvent cement joints : Non compliance with SDS Non compliance with chemical approvals Incorrect PPE |  | Skin damage Airway damage Environmental Spill | Enviromental | Possible | Moderate | 13 | Pre plan Work Methodology for use and storage of chemicals, Chemical Substance procedure, designated smoking areas, chemical approval process, PPE, SWMS / JSEA, Adhere to SDS requirements; spill response training, spill kits | Administration | Unlikely | Moderate | 17
Install Underground Cable | Manual handling : Over exertion no clear access failure to stretch prior to lifting incorrect posture failure to use appropriate PPE |  | bodily injury slips trips back injury musculoskeletal hand injuries | Safety | Likely | Moderate | 9 | correct analysis of requirements SWMS / JSEA, use of lifting equipment if required, Work Method Statement. defined course of travel adequate stretching assume correct posture(bend knees etc) analyse mechanical assisted two person lifts assess and select correct gear | Administration | Possible | Moderate | 13
| Installation of cables - Winching : Poor rigging practices, Unauthorised people in winch/pull zone |  | bodily injury slips trips back injury musculoskeletal hand injuries | Safety | Likely | Moderate | 9 | Maintenance schedule, Pre start checks, Exclusion zones where cable pulling is occurring, Use spotters where required, Competent personnel (Operator, Rigger, dogger) (VOC), SWMS / JSEA to be completed and reviewed prior to work commencement, Close supervision, Inspections, registers, tags of rigging equipment, Barricades and signs used to demarcate the pull zone, Onsite inspections of equipment prior to performing pulls, PPE, Hazards to be communicated in Toolbox talks and Pre start meetings, Establishment of good communications. Radios, hand signals. Signals clear to whole work team, Intermediate riggers. | Administration | Possible | Moderate | 13
| Personnel and fauna Interface with plant and equipment : lack of communication, Fauna refuge |  | Personnel and fauna injury, equipment damage | Safety and Environmental | Possible | Minor | 18 | Radio communication, Visual warning systems, barricading, delineation, all personnel stay out of slew radius' and blind spots , prestart and ongoing fauna inspection | Administration | Unlikely | Minor | 21
| Noise, Vibrations and emissions : Faulty non serviced plant and equipment |  | disturbance of Flora and fauna, manual handling injuries, hearing loss | Safety and Environmental | Possible | Moderate | 13 | ensure all plant and equipment is maintained and serviced. Ensure prestart are undertaken, job rotation. Check electrical tools for current test and tagging requirements | Administration | Unlikely | Moderate | 17
| Dust : Material supplied having high fine content |  | disturbance of Flora and fauna, Dust Inhalation, | Environemtal | Possible | Minor | 18 | Material to be supplied conditioned with limited fines | Administration | Unlikely | Minor | 21
| Plant failure : Hose rupture, mechanical failure Rigging failure |  | personnel injury - fatality, environmental impact | Safety and Environmental | Possible | Moderate | 13 | Plant pre-start inspections and schedule maintenance. all personnel to stay out of pulling area - Work Method Statement. Permit to work if required. Spill kits available, spill response, ensure appropriate waste segregation of hazardous material | Administration | Unlikely | Moderate | 17
Electrical Connection | Manual Handling : Poor Planning, Lack of Supervision, Incorrect lifting technique, Lack / incorrect use of mechanical lifting equipment, Inadequate work space / access Uncontrolled movement of equipment Equipment not correctly positioned Poor communication |  | Injury or asset damage Potential fatality | Safety | Possible | Moderate | 13 | Planning the lifts by personnel (Pre-start / Stepback 5x5 / SWMS / JSEA), WMS , SWMS / JSEA Prestart, Use appropriate mechanical / lifting equipment , Supervision Work procedures identifying the correct method of lifting, Use Team Lifts where possible, Training , Stretching / warm up at pre-start, PPE, Two way Radios / comm's | Administration | Unlikely | Minor | 18
| Terminations/Hand Tools : Rotating equipment, Sharp tools, Battery / electrically powered equipment |  | Injury or potential fatality | Safety | Possible | Moderate | 13 | PPE, Training / VOC, WMS / SWMS / JSEA, Equipment maintenance, Guarding of tools Use in accordance with Project requirements, Housekeeping, Lighting of work area, Planning of work, Supervision, Pre-start checks, RCD protection, Testing & tagging | Administration | Unlikely | Moderate | 17
Testing and Commissioning | Electricity : Poor planning, lack of supervision, lack of testing procedure. |  | Injury or asset damage Potential fatality | Safety | Possible | Major | 8 | SWMS / JSEA to be completed and reviewed prior to work commencement, Control of drawings to ensure the latest revision is used, Licensed competent personnel, Lock out tag out procedures. Permit to work, Hazards to be communicated in Toolbox talks and Pre start meetings to all contractors, completed ITP work packs,Verify Isolations with certified equipment | Isolation | Unlikely | Major | 12
| Energisation of equipment, MV/LV switching : Faulty equipment, lack of QA, inadequate pre-commissioning checks, Failure of isolation procedures, Poor communication, |  | Injury or asset damage Potential fatality | Safety | Possible | Major | 8 | SWMS / JSEA to be completed and reviewed prior to work commencement, Licensed competent personnel, Lock out tag out procedures. Permit to work, Hazards to be communicated in Toolbox talks and Pre start meetings to all contractors, completed ITP work packs, Verify Isolations with certified equipment, Test of equipment to relevant procedures, switching procedure, switching to be carried out by competent and authorised personnel | Isolation | Unlikely | Major | 12

## Concrete
Construction Risk Assessment Workshop
Project: | 1096-01 Yuri
Activity |  |  | Consequences | Risk | Assessment (before controls) |  |  | Controls | Hierarchy of Control | Assessment (Residual Risk)
Task | Hazard | Critical Risk Icons |  |  | Likelihood | Consequence | Rank |  |  | Likelihood | Consequence | Rank
Concrete works
Chemicals / hydrocarbon use, storage and handling | Exposure to chemicals Chemical Spills Incorrect or incompatible chemical and hydrocarbon storage Inadequate or unsuitable storage containers used Inadequate management of risks associated with transport / storage and handling Incorrect PPE use leading to chemical exposure No SDS available to users |  | Explosion Fire Chemical Burns Poisoning Personal Injury from chemical contact | Safety / Environment | Possible | Moderate | 13 | New chemical request form to be completed for approval prior to being brought onsite - SDS Chemical Risk Assessment for chemicals classed as hazardous or dangerous goods Specified PPE to be available to users All chemicals are managed using ChemAlert Approved Chemical Storage bunded (110% capacity of stored goods) areas with segregation of incompatible chemicals / flammable goods All chemicals / hydrocarbon storage vessels to be clearly labelled All chemical storage areas require sufficient ventilation Personnel will be trained via toolbox topic on the safe use of chemicals First aid / Eye wash station to be available Safety Management Plan Environmental Management Plan | Engineering | Unlikely | Moderate | 17
Chemical transportation / hydrocarbon use and refuelling | Exposure to chemicals Spills, Incorrect / incompatible chemicals / hydrocarbon storage Hydrocarbon spills |  | Poor work practice Incorrect storage containers Collision during transportation Poor refuelling techniques used | Safety / Environment | Possible | Moderate | 13 | All relevant licenses required to be completed Designated storage areas identified for non-hazardous and hazardous chemicals Hazardous chemical storage shall be restricted and stored in lockable cabinets All chemicals / hydrocarbon storage vessels to be clearly labelled Chemical handling, storage, segregation training First aid trained personnel (1:10 ratio) First aid Kits and Eye wash stations to be available Mobile refuelling activities to be risk assessed SDS to be available Chemical Risk Assessment for chemicals classed as hazardous or dangerous goods Use specified PPE Approved Chemical Storage bunded (110% capacity of stored goods) areas with segregation of incompatible chemicals / flammable goods. Safety Management Plan Environmental Management Plan | Administration | Unlikely | Moderate | 17
Steel and anchor cage materials delivery | • Materials weight • Lifting • Plant and materials movements • Drivers unfamiliar with area and procedures |  | • Crush injuries • Plant overturning/roll over | Safety | Possible | Major | 8 | 1. SWMS in place 2. All people involved to understand, sign onto the SWMS and comply 3. Delivery driver induction 4. Escort fulltime in place 5. Spotter in place 6. Follow site TMP 7. Be aware of Emergency evacuation procedures 8. Follow all other site rules incl. speed limits 9. Licensed crane driver and dogman fully inducted 10. All plant accepted on site through yuwi system. 11. All lifting gear registered and recently inspected | Administration | Unlikely | Major | 12
Anchor Bolt Assembly Assembly of bottom and top ring segments Fixing of top anchor ring onto feet Inserting bolts into position | • Exposure to hot weather • Manual handling • Weight of materials |  | • Sunburn • Crushing injuries | Safety | Likely | Major | 5 | • Area deligniated and SWMS in place Adequate drinking water available • Use sunscreen • Ring sections to be lifted only by crane • Spotter in place to guide the crane (Dogman) • Positive comms between workers and operator • Use forklift where possible • Keep all body parts away from heavy movement as far as possible • Two men lifts where required • Do NOT lift anything over 20kg by yourself alone | Substitute | Unlikely | Major | 12
Placing formwork | • Manual handling • Concrete release agent |  | • Fingers and/or hands in pinch points • Skin irritations/ allergic reactions • Twisting | Safety | Possible | Minor | 18 | • Correct quality gloves • Correct lifting techniques • Positive communication between workforce | Administration | Unlikely | Minor | 21
• Lifting anchor bolt into position • Lifting in Precast, bolt and upstand • Stripping top ring components • Lifting steel into the assembly area | Suspended loads |  | Crushing | Safety | Possible | Major | 8 | • Ref: 3 – Cranes and lifting operations • Crane prestart • Cranes to hold current crane safe documentation • Crane to display SWL • All slings and chains to have current tag and all lifting gear inspected • Lift with a lift study in place • Area barricaded • Operators to be trained/ticketed/VOC’d for the class of crane operating • Ensure surface stability before setting up. Ensure ground conditions testing and compliance according to crane manufacturer’s specifications • Operator and dogman to be fit for work • Operate the plant within specified limits • All equipment rated and load within SWL • Only lift with a qualified dogman securing the load • No crane operations during unsafe weather conditions |  | Unlikely | Major | 12
Cleanout and conduit install | Excessive noise from compressor |  | • Ear damage | Safety | Likely | Moderate | 9 | Wear the correct ear protection | PPE
Storage | • Untidy area • Heavy load • Manual handling |  | • Sprains • Strains • Over exertion | Safety | Likely | Moderate | 9 | • Ensure steel is stacked up tidily. • No loose materials laying around. • Steel should not be placed directly onto the ground. Use chocks to avoid rusting and for easy lifting. • Steel should be straight and clutter free. • All delivered items should be stacked in an orderly manner as unloaded. • All scrap offcuts to be placed in bins or piled up so it can be removed in future for disposal • Good manual handling practices • Correct gloves always | Administration
Cut open bundles of steel | • Unstable packs • Heavy steel • Steel rolling • Manual handling |  | • Cuts and scratches • Entrapment • Broken ankles or bones | Safety | Likely | Moderate | 9 | • Site specific PPE to be worn always • Minimum cut rate 3 gloves • Prevent uncontrolled movement by placing chocks under both ents • Stay clear in case it rolls
Building of steel tower base | • Manual handling • Heavy steel • Suspended loads • Hot work |  | • Strains • Crush injuries • Ignition of fires | Safety | Likely | Moderate | 9 | • Maintain good housekeeping practices. • Follow Manual handling procedures. • Plan all movement of steel prior lifting • Lift steel bundles with crane • Never go under suspended loads • No Hot works without a permit and SWMS in place • Follow Work methodology as specified by engineer • At no time is anybody to be working on the top inner section (where hole is exposed) of the ring before stage 7 has been constructed. • Standing on the top outer section of the top inner ring is to be done with extreme caution whilst reo is being landed on the top ring to place onto the structure. • The exposed hole in centre of top inner section shall have steel placed across it at the earliest opportunity to minimise time of that section being a hazard for the workers. • Care to be taken whilst walking on partially built base – place each foot across a minimum of two metal reo rods whilst walking on the base at any time during construction. • Only experienced steel fixing workers to access the partially completed base until the steel fixing supervisor informs others requiring access that the structure is safe to walk on without falling through any of the steel openings.
Tying Steel | • Heavy or awkward lifts • Repetitive lifting and bending • Inclement weather • Sharp edges • Bending for long periods of time |  | • Muscle strain / ligament injury. • Personal injury or crush injury Wet and slippery steel or other materials being handled. • Cuts & Abrasions • Pinch points • Entrapment | Safety | Likely | Moderate | 9 | Long or heavy bars should be team lifted. Good manual handling techniques shall be used. Rebar fixing which is low to or in the ground, necessitating bending should be rotated with standing/carrying work to minimise the risk of injury. Steel fixers should carry out stretching periodically during work. Rebar is to be stacked as close as is practicable to fixing locations. Trestles or supports to be used to elevate rebar cages for waist high tying where possible. Bundles of rebar to be arranged and spaced such that stepping over one bundle to get to another is minimised • No work during rain. • A risk assessment shall be completed after rain to ensure that the site is safe to continue work or to mitigate the situation otherwise. • Completed rebar cages shall be stored such that they cannot roll and do not impede walkways or traffic ways. • Minimum cut 3 gloves to be worn per task. Safety bar caps should be fastened on all exposed reinforcing especially where personnel may be cut or impaled. (E.g., starter bars). Tie-wire ends to be bent over to one side or bent inside cage as much as possible to minimise sharp ends. Ensure employees are toolbox talked and competent on the use of the guillotine. • Gaps in reo to be minimal throughout the build process of the base structure. Quick cut saw to be available to cut reo if needed to gain access in a hurry to inside of steel structure. Access to be gained through low section of WTG Reo base, wide enough for recovery dependant on situation i.e. stretcher Any gaps with the potential hazard of falling into a WTG reo base are to be closed ASAP whilst building WTG to specification
Concrete prep works | Exposed reinforcing bars and tie wire presenting slips trips falls hazards |  | Injury to personnel | Safety | Possible | Moderate | 13 | Clear away unnecessary materials from the area SWMS for activities / Take 5's Pre-start meetings Supervision Provide bar caps to exposed bars. Steel fixers cut off excess tie-wire. Take care around reo-wear gloves and protective clothing. mandatory & other PPE used as identified Caps to be used as required PPE Gloves Pre activity work area inspection and approval for start
Working with wet concrete | Chemical burns from contact with the skin |  | Injury to personnel | Safety | Possible | Minor | 18 | Protect the skin from contact with wet concrete. mandatory & other PPE used as identified Eye wash Water supply – 1st Aid SDS SWMS for activities Pre-start meetings Supervision
Moving concrete with a barrow Shoveling Concrete | Manual handling - weight, balance, access route, effort, loss of control, spillage, wasted concrete |  | loss of control, spillage, wasted concrete injury to personnel | Safety / Environment | Possible | Moderate | 13 | Clear away unnecessary materials from the area Pre activity work area inspection and approval for start SWMS for activities / Take 5's Pre-start meetings Supervision Provide a well-defined, clear and smooth path for the barrows consider an adequate tip-off point. Assign the task to personnel of adequate strength and agility. Do not overload barrows. mandatory & other PPE used as identified
Pouring concrete from the delivery truck | Delivery chute: strike personnel as it moves-injury. Manual handling - weight, balance, effort, loss of control, spillage, wasted concrete |  | loss of control, spillage, wasted concrete injury to personnel | Safety / Environment | Possible | Minor | 18 | • Always keep control of the chute. • Communicate with the driver. • Driver to clean out chute at concrete plant not on site. • SWMS for activities / Take 5's • Pre-start meetings • Supervision • Protect the skin from contact with wet concrete. • Mandatory & other PPE used as identified
Pumping Concrete (associated tasks) | Manual handling - weight, balance, effort, loss of control, spillage, equipment impact Delivery hose under pressure: sudden or violent movements |  | Delivery chute: strike personnel as it moves-injury to personnel loss of control, spillage, wasted concrete plant equipment damage | Safety / Environment | Possible | Major | 8 | Pre activity work area inspection and approval for start SWMS for activities / Take 5's Pre-start meetings Supervision clear area for work Keep control of the chute at all times. Communicate with the driver. Concreters keep away from the discharge point. Driver to clean out chute at concrete plant not on site. nozzle positioning using two persons where necessary only authorised persons in area mandatory & other PPE used as identified Operator licensed with High Risk license. Pump certification. Daily inspections Competent operator Plant maintenance records Exclusion Zones
| Uncontrolled release of concrete washout water |  | Sedimentation and or contamination of water or land Contractual / Environmental legislative breaches | Safety / Environment | Unlikely | Moderate | 17 | SWMS for activities Pre-start meetings Supervision Concrete washout contained in a centralised lined pit (washout facility), which will be monitored and maintained as required.
Wash out after delivery | Incorrect/ non compliant Disposal of washout water and waste concrete- |  | environmental hazard / impact/breach | Safety | Possible | Moderate | 13 | Provision of an adequate, accessible and compliant wash-out and waste concrete area. Concrete Pump Operators to be briefed on requirements. SWMS for activities Pre-start meetings Supervision Traffic control diagrams / vehicle movement plans
Operating the vibrator | Manual handling - weight, balance, effort, loss of control, equipment impact Extended time of operating: tiredness. Noise: hearing damage to personnel Concrete splashes: concrete in eyes. |  | injury to personnel loss of control, | Safety | Possible | Minor | 18 | Pre activity work area inspection and approval for start SWMS for activities / Take 5's Pre-start meetings Supervision clear area for work Keep control of the vibrator at all times. using two persons where necessary only authorised persons in area mandatory & other PPE used as identified Daily inspections Competent operator Plant maintenance records Exclusion Zones Rotate personnel for the task. Stretch and bend often. Wear hearing protection as necessary. Mandatory if the level > 85dBA. | Administration | Unlikely | Minor | 21
Refuelling Vibrator | Fuel |  | • Fuel splash • Fire • Fuel in the eyes | Safety | Possible | Moderate | 13 | • Ensure personnel working with the substance have read and understand the contents of the SDS and that a copy of the SDS is easily accessible to personnel. • Wear the correct PPE as per site requirements and as stated in the SDS. • Check that fire extinguisher is available and in service. • Keep fuel away from hot surfaces. • Turn off the motor before refuelling. • Only refuel in designated refuelling bunts. • Check that there are no ignition sources near before refuelling. • Notify supervisor if fuel supply is getting low at refuelling area. • Always replace fuel container caps as soon as you have finished refuelling.
Concrete finishing / troweling / screeding | Manual handling - Concrete splashes: concrete in eyes. |  | injury to personnel | Safety | Possible | Minor | 18 | • Pre activity work area inspection and approval for start • SWMS for activities / Take 5's • Pre-start meetings • Supervision • Clear area for work • Only authorised persons in area • Mandatory & other PPE used as identified • Stretch and bend often. • Arrange for task rotation or breaks. • Discharge and move the concrete to minimise the volume at the screed. • Use helicopters where possible to minimise over exertion. • Avoid over stretching
Curing the concrete | Manual handling- wind blows the plastic about; slips on slippery plastic-injury. |  | Manual handling injuries from applying covering and weights Injuries as a result of wind blowing the plastic about; slips on slippery plastic, and finished concrete surfaces. | Safety | Possible | Minor | 18 | Pre activity work area inspection and approval for start SWMS for activities / Take 5's Pre-start meetings Supervision clear area for work only authorised persons in area mandatory & other PPE used as identified Stretch and bend often. Arrange for task rotation or breaks. 2-man task to handle large rolls. Move carefully when walking on the plastic. Take care when cutting.
Curing the concrete | Use of chemicals, use of spray unit, climbing onto the finished work - slip, trip, fall |  | Exposure to curing chemicals Injuries as a result of slips on slippery plastic, and finished concrete surfaces. | Safety | Possible | Minor | 18 | Pre activity work area inspection and approval for start SWMS for activities / Take 5's Pre-start meetings Supervision clear area for work only authorised persons in area mandatory & other PPE used as identified Move carefully when walking on finished surface. Refer to SDS for chemical properties – avoid skin and eye contact. Provide good access to the site. Minimise walking backwards.
Access for concrete delivery trucks | Access for concrete delivery trucks-spotting, reversing, personnel in the vicinity, drivers not familiar with the site-confusion, collision, crushing |  | Damage to existing infrastructure Equipment damage Delays to work schedule at critical phase truck gets bogged, collision with formwork, collision with personnel-serious damage or injury | Safety | Likely | Moderate | 9 | Clear away unnecessary materials from the area SWMS for activities Pre-start meetings Supervision UHF radio comms restricted access areas Provide sound access for the truck, with visible markers for reversing. Traffic control diagrams / vehicle movement plans pedestrian pathways delineated amenities established for convenience at work fronts if possible mandatory & other PPE used as identified Plan rotation of personnel stagger starting times Pre activity work area inspection and approval for start separate briefing for delivery drivers, spotters, and workers as required to present the traffic and site plans. Exclusion Zones for non-operational personnel Spotters in place and in direct contact with all drivers Spotters always to be seen by drivers and safe from reversing traffic
Set up Boom Pump | Moving parts Environmental Reversing truck |  | Cutting Crushing Spills Reversing into pour area | Safety | Likely | Moderate | 9 | • Ensure pump truck is parked and isolated • Set up is on a level, firm surface • Use outriggers on pads for stability • Provide a physical barrier for protection against the moving parts of the hopper • Operate according to manufacturer’s specifications. • Spotter always in place |  |  |  | 21
Concrete Pumping | Concrete Pumping Overhead powerlines |  | Fatal / serious injuries caused by pump section moving unexpectedly Death / Injury caused by blockage being ejected at high speed Electrocution | Safety | Unlikely | Catastrophic | 7 | Eye Protection to be worn Eye wash station to be available SWMS SDS and chemical risk assessment Correct PPE including site specific clothing, gloves and any other PPE specific to the task and / or conditions. Guarding, Barricading, Signs and Housekeeping Workers operating the concrete pump to hold PB High RIsk Work Licence and have a current VOC Wherever possible persons are not to work under the concrete pump boom Concrete pump to be set up as per manufacturers specifications with outriggers extended and packed as required. OHS-P-005 Cranage and lifting OHS-P-006 Personal Protective Equipment Safety Management Plan Spotters to be used and signage for overhead powerlines 1084-02-OHS-F-005 Danger Zones Overhead Power Lines | Administration | Rare | Catastrophic | 11
Operation of Boom systems | • Overloading • Failure of components • Manual handling • Slips and trips • Boom pump blocked and under pressure |  | • Injury • Damage of equipment • Suspension of works • Tripping • Twisting • Cuts • Muscular stress/musculoskeletal disorder (MSD) | Safety | Likely | Moderate | 9 | • SWMS in Place • Operator licensed with High Risk license. (PB) • Operate according to manufacturer’s procedures • Correct PPE • Ensure all whip slings are attached to the pump and discharge hose • Hose hand to be on the boom line at all times • Pump certification yearly • Work according to AS 2550.15 - 2019Cranes, hoists and winches - Safe use Concrete placing equipment • Clean up after use • Pack away materials when not in use or finished using • Concreters to stay away from the line
Concrete works Stabilising sand cement mix and placement / Formwork / Reo bars | Chemical burns Silica dust inhalation HV / personnel interaction Vibration Pinch points Falling Cuts / line of fire injuries Manual handling injuries High Speed spinning blades |  | Cement dust / concrete splashes / contact Personnel in vicinity of reversing mobile plant / pinch points Concrete Vibrator Hand Arm vibration injury Unexpected movement of pipework / mass concrete / formwork Injuries caused by the incorrect use of handtools Strains sprains Cuts lacerations caused by contact with sharp edges / reo bar | Safety | Possible | Major | 8 | SDS Sheets to be available Correct PPE as stipulated on SDS sheet inc. Gloves and Hearing protection Positive communication between spotter and truck / plant operators Trained and Competent plant and equipment operator - Competencies / HRWL / VOC's Correct tools for the task, competent operators Secure pipework to prevent movement if required Caps on all star pickets and exposed reo bar Prestarts on tools and equipment's Correct PPE to be worn including correct gloves for task Use of mesh sheets rather than reo bar wherever possible Precast concrete structures wherever possible fabricated offsite Management Standards Safety Guidelines Safety Management Plan | Administration | Unlikely | Major | 12
Penetrations not covered. | 1. Penetration/s not covered or cover not secured forming “trap” 2. Tip on bar chair ends missing. 3. No signage or barricading. 4. Fall from one level to another. |  | Serious injury | Safety | Likely | Major | 8 | Barricading. Signage. SWMS Signed and approved by the Supervisor Good Communication. Pre-Starts. Fix down covers and label "hole below" with size & what type of hold down being used. | Engineering | Rare | Major | 12
Use of concrete retarder | 1. Slippery surfaces |  | Injury | Safety | Likely | Moderate | 13 | SDS less than 5 years old and remain with the chemical on site Correct PPE. Spill Kits SWMS Signed and approved by the Supervisor Approval of chemical and entry onto register. | Substitution | Unlikely | Moderate | 13
Trowel Machine (Helicopter Float). | 1. Operator not trained. 2. Operator not watching. 3. Blade hits object. 4. Momentum throws operator 5. Machine coming off edge of slab 6. Rotating machine Blade. 7. Lifting the machine. 8. Poor machine maintenance. 9. Person / machine contact. 10. Hydrocarbon spill |  | Serious injury | Safety | Likely | Moderate | 13 | Regular maintenance carried out on equipment Pre-start meeting Correct PPE to be worn Area barricaded where required. Experienced Operator. VOC'd Pre job planning SWMS Use mechanical device to lift where required. Use other personnel where required. Spill Kits available | Administration | Unlikely | Moderate | 13
Re-Fueling machine. | 1.1. Poor fuel storage container. 2. Inadequate funnel for refueling. 3. Smoking near fuel. 4. Refueling when motor is still in operation. 5. No PPE or incorrect PPE for the required task. 6. Spill onto open ground. 7. Wrong type of fuel used. |  | Explosion Fire Chemical Burns Poisoning Personal Injury from chemical contact | Safety | Likely | Moderate | 13 | Spill trays for all re-fueling. All fuel cans labelled. No ignition sources within the vacinity. Correct PPE supplied and worn. Machine turned off before re-fueling. Funnel to be with fuel. Spill kits available | Administration | Unlikely | Moderate | 12
Clean up and finish | Manual handing Environmental spills Trip hazards |  | Injury to personnel Damage to completed works Slips trips falls | Safety / Environment | Possible | Minor | 18 | Pre activity work area inspection and approval for start SWMS for activities / Take 5's Pre-start meetings Supervision only authorised persons in area mandatory & other PPE used as identified Move carefully when walking on finished surface. Provide good access to the site. Minimise walking backwards. Remove rubbish and trip hazards as you go. Concrete wash water is to be contained. Concrete residue to dry out with the dried-out mix being recycled on site as road-base or backfill. All vehicle and pump washouts to take place Designated wash down area.
Stripping Formwork

## LISTS
Likelihood | Consequence | Hierarchy | Risk
Almost Certain | Insignificant | Eliminate | Safety
Likely | Minor | Substitute | Environment
Possible | Moderate | Engineering | Community
Unlikely | Major | Separate | Health
Rare |  | Administration | Safety / Environment
|  | PPE | Safety / Community
Safety / Health
Environment / Community
Environment / Health
Community / Health